DEMOCRATIC  REPUBLIC  OF  CONGO

WOMEN  AND  CHILDREEN  WELFARE  ACTION

(A.F.E)

ACTIVITY  TITLE

P. Oc: NYABENDA  BUNAME

Tél.: O99 890 0687

E-mail: afe72002@yahoo.fr

Activity  total cost: 9.796,00 Euros

April 2012

Women and children welfare Action

“NGO/ASBL – AFE”

PROJECT TECHNICAL FILE

Project title:

Sensitization of women on family planning in Kalamu  I  and Kasa-Vubu health Zones.

I.CONTEXT AND JUSTIFICATION

The fifth pillar of the millennium objectives aims to reduce to ¾ the death rate of women reproduction between 1990 and 2015, but the development indicators evaluation report of 2011 shows that the death rate of pregnant women has globally decreased.

It is important to mention that the Sub-Saharan region has the highest death rate of pregnant women with 87% death rate of women in the world according to the OMD evaluation report of 2011. The main causes remain have many children (lots of deliveries);

Early deliveries ( too young to have babies ); Shot time between pregnancies; and sometimes too late pregnancies ( too old to be pregnant ). Despite the progress made in the reduction of the mortality rate of pregnant women in the world, the 2015 rendez – vous will not be met if no additional efforts one made.

This project aims to sensitize groups of women in schools, churches, markets place and other areas in Kalamu I and Kasa – Vubu health zones to pratise family planning. These two health zones were selected because Matonge and Kasa – Vubu areas a well known as hot zones where women and mostly teenagers operate like six workers.

The majority of women do not use the family planning services, therefore we think that it is urgent to sensitize women on family planning and the usage of contraceptives to reduce pregnancies to teenagers and prevent unwanted pregnancies to adult women. This will not only impact on women reproduction health and improve children’s life, but it will also contribute to reduce poverty, at a high level of sex equilibrium, thus creating self dependant women.

Besides it will help women or teenagers who dropped out of schools to resume school and who have finished school to seek for jobs.

The NGO Action for women and children welfare has a long and rich experience on sensitization of women on reproduction health and family planning funded by the UNFPA.

N°2, av. Bongandanga, Commune de Kasa – Vubu, Ville province de Kinshasa/DRC

Phone : (+243) 998900687 ; E-mail : afe72002@yahoo.fr

- Strategies of implementation:

Following strategies will be implemented for activities: Meetings with team leaders of the two health Zones to agree on strategies:

- Recruit community “Relais”;

- Train community “relais”;

- Identification and invite of Reproduction health women for the sensitization sessions.

- Expected Results:

500 women divided into the two health Zones (are) will be sensitized on practice of family planning and the usage of contraceptives.

- Location of Activity implementation:

The activity will be implemented in the two health Zones of Kalamu I and Kasa – Vubu.

- Project duration:

15 days.

- Implementation period:

From April 1 to April 15, 2012.

- Responsible for Action/Implementation

The National Director of the NGO AFE.

|  | 7. Budget: | 9 796,00 € |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| N° | Post/budget | Unit | Frequency | Quantity | Unit Price | Total Cost |
| 1 | Coordination meeting with Kalamu I and Kasa - Vubu health Zones | Meeting | 6 | 1 | 80,00 € | 480,00 € |
|  | S/Total 1 |  |  |  | 80,00 € | 480,00 € |
| 2 | Community "Relais" recruit | people |  |  |  |  |
|  | Vehicle Rent | day | 5 | 1 | 120,00 € | 600,00 € |
|  | Recruit team perdiem | people | 5 | 3 | 40,00 € | 600,00 € |
|  | S/Total 2 |  |  |  | 160,00 € | 1 200,00 € |
| 3 | Identification of reproduction health women to invite for sensitization | people | 2 | 335 | 1,00 € | 670,00 € |
|  | S/Total 3 |  |  |  | 1,00 € | 670,00 € |
| 4 | Organization of sensitization sessions on family planning |  |  |  |  |  |
|  | Room Rent | day | 2 | 5 | 200,00 € | 2 000,00 € |
|  | Coffee break |  | 6 | 70 | 5,00 € | 2 100,00 € |
|  | Perdiem for facilitators team | people | 12 | 3 | 20,00 € | 720,00 € |
|  | Participants transport | people | 12 | 67 | 3,00 € | 2 412,00 € |
|  | S/Total 4 |  |  |  | 228,00 € | 7 232,00 € |
| 5 | Office equipment |  |  |  |  |  |
|  | Reams of papers | piece | 1 | 10 | 5,00 € | 50,00 € |
|  | Pens | box | 1 | 3 | 8,00 € | 24,00 € |
|  | Reproduction of invite | copy | 1 | 1000 | 0,04 € | 40,00 € |
|  | S/Total 5 |  |  |  | 13,04 € | 114,00 € |
| 6 | cards of communication | pièce | 20 | 1 | 5,00 € | 100,00 € |
|  | S/Total 6 |  |  |  | 5,00 € | 100,00 € |
| 7 | Project Total cost |  |  |  |  | 9 796,00 € |

# Text boxes

Sensitization of women on Family planning in Kalamu I   and Kasa-Vubu Health Zones