**General Report June 2014 A.D.**

***Thanks For All Donors and Global Giving Team for this possible.***

**Project Name :** HOPAD Children and Women Capacity building Project.

**Partnership :** Global Giving USA and HOPAD Child and Women Promotion Society, Nepal.

**Project Completed** :

* 31 Marginalized women 6 months tailoring.
* 30 Marginalized one month's advanced course women Tailoring Training.
* 20 Orphan children (three + two) = 5 months educational support.
* 75 children received School Tie and belts with educational materials.
* 60 Women needy women completed Embroidery professional three months training.

**Ongoing Training:**

* 18 School stationary materials for needy children.

**Project Directed By:** Purna Bahadur Khatri

Dear Sir/ Madam

Namaskar

First of all HOPAD give more Priority to do effective project management for the target group of the project. On the reporting process, in our project evaluation, it is good and effective. It is in the rural mid western area of Nepal, where our Global giving projects is ongoing.

Thanks to great generous donations, we were able to run our project permanently on the Global Giving website, which will hopefully help us to keep up sustainable help for needy women and children in the rural areas of Nepal. It is only possible from your support with love. It is effective for the empowerment women and support needy children educational development of Nepal. Now, HOPAD has not fund further run this project. So, please try to contribute for this project. **Only we are supporting for the 18 children educational support in rural area of Dang.**

1. **A. Women Project**:

a. **6 Months Tailoring Training:**

A (Women participant swing cloths for her personal uses) and for their evaluation we provide them a pair of cloths to them for sewing for themselves. They finished it in time. They are all total 31 in two groups. It was successfully completed as first group. They spent 6 hours per day for effective practice.

1. **3 Months Advanced Course professional Tailoring Training ( Changed One month's Training) :**

20 women completed one month's advanced course training for their professional work. This tailoring project was professional and selected best for their business development in the rural area of Dang. Due to the cause of financial problem we make it only one month.

**B. a. First and Second 3 months Embroidery Training Completed:**

60 women completed for their professional capacity building embroidery training program. They are happy in their achievement. They were in two groups with 15 -15women /participant per groups.

It was fruitful for their betterment. HOPAD is impressed from their development of Technical knowledge. They are really excellent in their training. The farewell program also completed.

**2. Children Educational program:**

**a. Rural area children education program:**

Our children Education program is going well for 16 poor and needy children in rural area Government school with necessary materials for like English Books and stationary, as well as classroom equipments in front of their poor parents.

**HOPAD children education Support:**

Due to the lack of support for HOPAD children are also facing financial problem since last January. HOPAD used some donation for orphan children educational fee for their quality education. It helps to attain their final exam for 20 children new grade.

Your donation is great to change lives of Nepali women and children. We are waiting for your next support and valuable suggestions for better work.

**Note: Now, we are unable to continue women project because of insufficient fund for this project. Please, donate now.**

Finally, please try to support more. We have not for finished this program and continue further service. Thanks

Sincerely,

Purna Bahadur Khatri .

Program Director

10 June 2014 A.D. Kathmandu, Nepal.