Kitui Spring Project

A Proposal from the Kenya Water, ENergy, Cleanliness and Health (KWENCH) Project

Kitui is in a semi-arid region of Kenya where water scarcity poses a constant hardship. KWENCH’s local partner in the proposed project, the Muvua Self-help Group, has identified a spring that has been used by generations of local people as a source of water for drinking and cooking. Mvua has requested KWENCH’s assistance in collecting the water from the spring in a large tank so that it can be properly treated and then distributing the water to a series of four points where it can be sold. The spring is located in Kitui West District, Mutongi Division, Usiani location, Kavalo sublocation.

In addition to the development of the spring, KWENCH and Muvua propose including sanitation, hygiene and livelihood components in the Kitui project. The sanitation component would comprise composting toilet blocks constructed at three schools near the spring: Kavalo primary school (900 students), St. Mary’s secondary school (300 students) and Kakulunga primary (780 students . The composting toilets would be based on the Fossa alterna model, in which each toilet stall contains two composting pits. One, already full pit is covered and allowed to compost as the second pit is used and begins to fill. Once the composting pits are dug, a layer of dried leaves, ash and clean soil will be placed in the bottom of the first pit to be used. After each use, the user will add a handful of a mixture of leaves, ash and soil. When the first pit is full, it will be covered and left to compost for about six months while the second pit is in use. The compost generated in the pits will be clean, fluffy and odour-free!  Each composting toilet bock will contain four stalls-two for boys and two for girls. The boys’ side will also have a urinal.

As per the hygiene component, each toilet block will be equipped with a handwashing station with a water dispenser that will use water from the spring and with soap. The dispensers will be made from reusable, plastic jugs and will cost almost nothing to make. The staff and students at each school will be provided with hygiene education so that they can understand how important it is to wash their hands after each visit to the toilet.

As per the livelihood component, The Muvua Self Help Group will use the compost from the toilets to grow seedlings for sale to the surrounding community. Some trees, donated by the NGO Trees for the Future, have already been planted!

KWENCH proposes developing the water supply system in three phases. The first phase involves directing water from the spring into a large tank and constructing a housing for the tank, generator and water pump. The second phase involves the construction of two tank stands with kiosks and installation of two, smaller water tanks both for selling water and for distributing it to tanks that will be installed in the third phase. The third phase involves the construction of two additional tank stands and kiosks and installation of two additional water points. Each of the project’s phases will result in a subproject that will be useful in its own right and allow time for sufficient funding to be raised to complete the project. The project beneficiaries include approximately 300 families and a primary school with 900 students.

Phase 1

Description: Construction of a small dam with a pipe leading from the spring to a 50 cubic meter masonry tank. The tank will be constructed on a concrete platform in a dip in the landscape that is at a lower elevation than the actual spring, allowing for filling of the tank by gravity. In addition, a brick structure will be constructed to house the tank, generator and water pump. A door will be installed in the housing for maintenance purposes and a window for ventilation.

Budget:

Materials for dam, pipe and housing for generator and pump.

- Generator and water pump @ 360,000

- Water meter @ 12,000

- Pipes 3 pieces-(2 Inches) G1 @ 4000 =12,000

- Gate valves (2 pieces) @ 3,500 = 7,000

- Timber (4 ×4) 400 feet =36,000

- Iron sheets 18 pieces @1,000 =18,000

- Nails (4 inches×5 kgs) & (3 inches×5 kgs) = 2,500

- Union (2 pieces) @ 250 =500

- Steel door (1 piece) @ 12,000

- Steel window @ 9,000

- Elbows (6 pieces) @ 200 =1,200

- Sockets (6 pieces) @ 200 =1,200

- Boss white 1 piece@ 500

- Transport @ 50,000

Subtotal		521,900

Labour

2 masons (1,000 per day x 6 days per week x 4 weeks) = 48,000

1 plumber (1,500 per day x 6 days per week x 4 weeks) = 36,000

5 labourers (300 per day x 6 days x 4 weeks) = 108,000

John Mwangangi, KWENCH Supervisor (1,500 x 6 days x 4 weeks + 500 x 4) = 38,000

Subtotal		230,000

Materials for a 50 cubic meter masonry tank

Cement 150 bags @ 800 = 120,000

Y 12 metal 35 pieces @ 1,800 = 63,000

Y 8 metal 40 pieces @ 1,200 = 48,000

Binding wire 25 kg @ 300 = 7,500

Lime 2 25 kg bags @ 500 = 1,000

1 ½ GI pipe (1.8 meter) = 1,500

¾ GI pipe (3.4 meter) = 1,800

1 ½ Gate valve = 4,800

1 ½ Socket = 200

1 ½ Nipple = 200

Tap = 1,500

3 Ply 12 pieces @ 800 = 9,600

2x2 Timber 100 ft @ 50 = 5,000

Waterproof cement 150 bags @ 500 = 75,000

3-inch Nails 8 kg @ 300 = 2,400

2-inch Nails 10 kg @ 300 = 3,000

Compacting machine/vibrator to be hired 10 days @ 1,500 = 15,000

Subtotal		359,500

Labour

4 masons (1,000/day x 6 days a week x 5 weeks) = 120,000

15 labourers (300 x 6 days x 5 weeks) = 135,000

John Mwangangi, KWENCH Supervisor (1,500 x 6 days x 5 weeks) + (500 x 5) = 47,500

Subtotal		302,500

Water testing = 15,000

Training in financial management = 55,000

Subtotal (materials + labour + water testing + training)  = 1,483,900

Administrative costs (15%) = 222,585

Contingency (10%) = 148,390

Phase 1 Total = 1,854,875

Community contribution

Land = 75,000

Bricks (400 pieces) = 9,750

Sand (30 tonnes) = 45,000

Ballast (30 tonnes) = 45,000

Total community contribution = 174,750

Phase 2

Description: Construction of a tank stand 40 feet high, installation of two, 10 cubic meter water tanks both at the top of the tank stand and construction of a water vending kiosk at the bottom of the stand. The tank stand will be constructed at 850 meters to the east of the 50 cubic meter water tank installed during the first phase of the project. The pump installed during the first phase will be used to pump water from the 50 cubic meter water tank to the first, 10 cubic meter tank. A pipe will connect the first 10 cubic meter water tank to the second 10 cubic meter water tank so that overflow from the first tank will fill the second tank. Both tanks will be used to supply water vendors in the kiosk until the construction of the third project is complete.

Budget

Materials for the plumbing

- Pipes 200 pieces-(2 Inches) G1 @ 4000 = 800,000

- 2 Water Tanks (10,000 liters) @78,000 = 156,000

- Unions 3 pieces (2 inches) @ 250 = 750

- 3  ½ Pegler Tap @ 800 =2,400

- ¾ Gate valves (4 pieces) @3,500 =14,000

- 3  ¾ Gate valves @ 2,500 = 7,500,

- 6  1 ¼ Gate valves @2,300 = 13,800

Subtotal = 994,450

Materials for the tank stand and kiosk

- 16 pieces (4×4) @ 8,840 =141,440

- Angle line 100 pieces (2×2) 3,400 = 340,000

- Beam (4×6) 15 pieces @ 10,000 = 150,000

- Bolts 200 pieces @ 150 =30,000

- Pipes 65 pieces- G16 @1,500 = 97,500

- Round 16 (1 piece) @ 3,600

- Flat bars 1¼ × ¼ (35 pieces) @ 1,400 = 49,000

- Timber 6×1 (900 feet) @ 60 =54,000

- Timber 2×6 (124 feet) @120 =14,880

- Timber 3×3 (100 feet) @40 =40,000

- Ground bolts (40 pieces) @500 = 20,000

- Welding rods (10 packets) @200 = 2,000

- Grinding disk (30 pieces) @ 300 = 9000

- Cutting disk (50 pieces) @200 =10,000

- Paint (10 litres) @ 1,800 = 18,000

- Thinner (20 litres) @ 6000 = 6,00

- 1 steel door @ 12,000

- 1 steel window @ 9,000

- 100 bags of cement @ 800 = 80,000

- Transport @ 50,000

Subtotal = 1,138,920

Total for materials = 2,494,370

Labour:

2 masons (1,500×6) × 8 weeks =144,000

1 welder (1,500×6) × 8 weeks = 72,000

1 carpenter (1,500×6) × 8 weeks = 72,000

1 Painter (1,500×6) × 8 weeks =72,000

1 plumber (1,500×6) × 8 weeks =72,000

3 labourers (300×6) × 8 weeks =43,200

John (1,500×6) x 8weeks + (500× 8) = 76,000

Total amount of labour = 	479,200

Subtotal =  2,973,570

Administrative costs = 446,036

Contingency = 297,357

Phase 2 Total = 3,716,963

Community contribution

Bricks (6,000 pieces) = 180,000

Sand (20 tonnes) = 56,000

Ballast (20 tonnes) = 249,600

Total community contribution = 389,600

Phase 3

Description: Construction of two tank stands 20 feet high, one at a distance of 1,000 meters to the west of the 50 cubic meter storage tank installed during phase 1 and one at a distance of 1,000 meters to the east of the 40 foot high tower constructed in phase 2. Installation of a 10 cubic meter water tank at the top of each stand and construction of a water vending kiosk at the bottom of each stand. Water pipes from the first, 10 cubic meter tank installed during phase 2 will transport water from the phase 2 project to the phase 3 tank to be installed 1,000  meters to the west of the 50 cubic meter storage tank installed in phase 1. Water from this tank will also continue to supply the kiosk constructed during phase 2. Pipes from the second 10 cubic meter tank installed during phase 2 will transport water to the phase 3 tank to be installed 1,000 meters to the east of the tank stand constructed during phase 2. This tank will no longer supply water to the phase 2 kiosk.

Budget

Materials for plumbing

- 2 water tanks (10,000 liters) @78,000 = 156,000

- 600 pieces (4 mm) PPR Pipes @ 1,400 = 840,000

- 400 pieces (4mm) PPR Sockets @ 120 =48,000

- 50 pieces (4mm) PPR Elbow @ 120 = 6,000

- 1 piece PPR Machine (HD) @ 4,500

- 10 pieces 1¼ × ¾ Reducer PPR 100 =1,000

- 3×3 ¼ Ball Valve @ 1,500 = 4,500

Subtotal 1,060,000

Materials for the stand and kiosk

- Angle line 20 pieces (2×2) 3,420 = 68,000

- Beam (4×6) 10 pieces @ 10,000 = 100,000

- Bolts 100 pieces @ 150 =15,000

- Nails (4 inches×15 kgs) & (3 inches×15 kgs) @250 = 7,500

- Wire mesh 16 pieces (8×4) @ 4,500 = 72,000

- Iron sheets (50 pieces) @ 1000 = 50,000

- Square Tube (4×4) 8 pieces @8,840 =70,720

- Timber: 6×1 (900 feet) @ 60 =54,000

- “            2×6 (124 feet) @120 =14 880

- “             3×3 (1700 feet) @40 =68,000

- “             6×1 (120 feet) @ 90 =10,800

- Thinner (20 litres) @ 6,000

- Paint 20 tins (each 4 litres) @ 1,800 = 36,000

- Brushes (10 pieces) @ 250 = 2,500

- (2pieces) Steel doors @ 12,000 =24,000

- (3pieces) Steel windows @9000 = 27,000

- 200 bags of cement @ 800 =160,000

- Transport @ 50,000

Subtotal 736,400

Total for materials = 1,796,400

Labour:

3 masons (1,500×6) × 8 weeks = 216,000

1 welder (2,000×6) × 8 weeks = 96,000

1 Carpenter (1,500×6) × 8 weeks =72,000

1 Painter (1,500×6) × 4 weeks =36,000

1 plumber (1,500×6) × 8 weeks =72,000

6 labourers (300×6) × 8 weeks =86,400

John (1,500×6) x 8weeks + (500× 8) = 76,000

Total amount for  labour = 654,400

Subtotal = 2,450,800

Administrative costs  = 367,620

Contingency  = 245,080

Phase 3 Total = 3,063,500

Community contribution

Bricks (6,000 pieces) = 84,000

Sand (20 tonnes) = 56,000

Ballast (50 tonnes) = 620,400

Total community contribution = 760,400

Phase 4

Description: Construction of composting toilet blocks at three schools that will receive water from the spring, hygiene (handwashing stations at each toilet block) and hygiene education and livelihood enhancement for members of the Muvua self-help group (growing seedlings to sell using the compost produced by the toilets). Each toilet block will contain two stalls for boys plus a urine diverting urinal and two stalls for girls. Each stall will contain two composting pits in a fossa alterna design. As one of the pits is in use, the other will be covered with a concrete slab and left to produce compost.

Budget for one composting toilet block

Iron sheets 8, 3-meters @ 800			  6,400

Bricks 1,500 @ 10					15,000

Cement 10 packets @ 800				  8,000

Sand 2 tonnes @ 1,500				  3,000

Ballast 2 tonnes @ 1,800				  3,600

Wire mesh 2 pieces @ 2,500				  5,000

Timber 2x2 96 foot @ 50				  4,800

Nails 3” 3 kg @ 120					     360

Iron nails 2 kg @ 180					     360

Paint 5 tins @ 1,900					  9,500

Doors 6 @ 15,000					90,000

Labour							90,060

Subtotal				          236,080

x 3 composting toilet blocks	          708,240

Contingency (10%)					70,824

Administrative costs (15%)			          106,236

Phase 4 Total			         	         	          885,300

Community contribution:

Tree seeds and seedling sacks have been contributed by the international NGO Trees for the Future.

Handwashing stations will consist of reusable plastic bottles, string and soap and will be virtually free of cost.

Hygiene education will be provided by a volunteer.

GRAND TOTAL KITUI SPRING PROJECT =  9,520,638

# Footnotes

1Food supplement