Reforestation Project Summary -

- Presentation of the Organization -

AFKB is a peasant organization with 155 members as of today and it started on March 3, 1996.  The Organization has these objectives:

- Improve the social and economic conditions of it’s' members and the rest of the population of Bayonè through a series of small development projects;

- Raise awareness about the problem of environmental degradation in Bayonè

- Problems the project wants to address -

With the passage of Hurricane Jean, all the communities of the area suffered great damage (animals died, people died, farms were ravaged, many trees were uprooted, houses were ruined) Members of AFKB thought deeply because Bayonè was hit especially hard.  The analysis of the organization members ended and they declared:

- The Vesan Valley is totally deforested so that all you see is rocks

- The soil has completely washed away into the sea because when the water fell in the rainy season, there were no plants to hold the water in the land.  So, now there is no infiltration of water in the soil.

- The dead animals and people, and broken houses that all washed away in the flood are now in many nooks, ravines, in Bayonè.

AFKB asked for a little hand from Lambi Fund to help the Organization reforest three of Vesen's valleys.  After many discussion sessions with the Organization, Lambi Fund decided to give AFKB a hand in addressing the solution of environmental degradation.

- Project Objective -

a) General Objective -

Improve the environment of the quarter and principally the Vesan Valleys.

b) Specific Objective -

- Produce 120,000 seedlings – fruit and forest trees– over two years that will permit the reforestation of 3 Vesan valleys.

- Permit the members to practice sustainable agriculture (an agro forestry garden).

- Sensitize the AKFB members on the causes and consequences of  environmental degradation and begin to bring the necessary solutions

- Increase members' knowledge of seedling production and reforestation

- Project Strategy -

Lambi gave the Organization money necessary to buy tools like a wheelbarrow, shovel, rake, pick, sprinkler, aspersion pump, plastic bags, pesticide, seeds, etc.

Normally in all Environmental projects Lambi finances, it always plans on a training that is principally about the techniques of sustainable agriculture.  In this way, it organized a 5 day seminar for 30 AKFB members.  The principle technical themes were: Composting, Greenhouse, Agro forestry, Reforestation, the structure of soil conservation, etc.

As the organization and Lambi had already in the meantime produced 30,000 seedlings in 1 semester (2 greenhouses with 15,000 seedlings in each) they started to put up a greenhouse during the technical training.  In this way, AKFB can produce 60,000 seedlings in a year, with 120,000 seedlings over two years.  In the seedling production operation, the Organization is using 4 greenhouses to care for all the seedlings.

Then, Lambi planned a training on education techniques and Organizational reinforcement to address the weakness in the structure of the organization.  The training lasted 5 days.  In the seminar, there was a diagnostic of Organizations (functioning, structure, completing activities....)

Finally, Lambi helped the Organization to put in place all the structure necessary to conduct all the project activities well.

Lambi is following up with the project for two years.

| Budget for the AFKB Environmental Project |  |  |  |  |
| --- | --- | --- | --- | --- |
| FIRST YEAR | UNIT | Quantity |  |  |  |  | Total |
|  |  | P. Inite | Kantite | Kant. Jou | Pat.Lokal | Og.Finans | In Goudes |
| 1.- Launch |  |  |  |  | 8500 |  | 8500 |
| 2.- Materials bought: |  |  |  |  |  |  |  |
| . Wheelbarrow |  | 2500 | 4 |  |  | 10000 |  | 10000 |
| . Drum |  | 500 | 4 |  |  | 2000 |  | 2000 |
| . Rake |  | 100 | 6 |  |  | 600 |  | 600 |
| . Shovel |  | 175 | 6 |  |  | 1050 |  | 1050 |
| . Hoe |  | 100 | 6 |  |  | 600 |  | 600 |
| Sprinkler |  | 300 | 4 |  |  | 1200 |  | 1200 |
| . Aspersion Pump | 2250 | 2 |  |  | 4500 |  | 4500 |
| . Bucket |  | 60 | 6 |  |  | 360 |  | 360 |
| . Pesticide |  |  |  |  |  | 5000 |  | 5000 |
| . Plastic bags | 0.7 | 65000 |  |  | 45500 |  | 45500 |
| . Transport |  |  |  |  |  | 10000 |  | 10000 |
| Total |  |  |  |  |  | 80810 |  | 80810 |
| 3.- Shed Construction |  |  | 21000 |  |  | 21000 |
| 4.- Seeds |  |  |  |  | 10000 |  | 10000 |
| 5.- Training |  |  |  |  |  |  |  |
| a) Sustainable Agriculture Techniques: |  |  |  |  |  |  |
| . Food |  | 150 | 30 | 5 |  | 22500 |  | 22500 |
| . Trainer |  | 3000 | 6 |  |  | 18000 |  | 18000 |
| . Rental car | 6562.5 | 6 |  |  | 39375 |  | 39375 |
| . Hand outs |  |  |  |  | 1500 |  | 1500 |
| b) Education Techniques |  |  |  |  |  |  |
| . Food |  | 150 | 30 | 5 |  | 22500 |  | 22500 |
| . Trainer |  | 3000 | 6 |  |  | 18000 |  | 18000 |
| . Rental car | 6562.5 | 6 |  |  | 39375 |  | 39375 |
| . Hand outs |  |  |  |  | 1500 |  | 1500 |
| Total |  |  |  |  |  | 162750 |  | 162750 |
| 6.- Greenhouse set up: |  |  |  |  |  |  |
| . Work crew |  | 100 | 30 | 6 |  | 18000 |  | 18000 |
| . Greenhouse worker Salary | 750 | 4 | 12 |  | 36000 |  | 36000 |
| Total |  |  |  |  |  | 54000 |  | 54000 |
| 7.- Follow up |  | 5000 | 5 |  |  | 25000 |  | 25000 |
| 8.- Internal Evaluation |  |  |  | 25000 |  | 25000 |
| TOTAL |  |  |  |  | 21000 | 366060 |  | 387060 |
| Staff time |  |  |  |  |  |  | 68059 |
| Grand Total Gdes |  |  |  |  |  |  | 455119 |
| Grand Total US $ |  |  |  |  | US $ | 13003 |
| Second Year Budget- |  |  |  |  |  |  |
| 1.- Seeds |  |  |  |  | 10000 |  | 10000 |
| 2.- Pesticide |  |  |  |  | 5000 |  | 5000 |
| 3.- Plastic Bags | 0.7 | 65000 |  |  | 45500 |  | 45500 |
| 4.- Work crew | 100 | 30 | 6 |  | 18000 |  | 18000 |
| 5.- Greenhouse worker salary | 750 | 4 | 12 |  | 36000 |  | 36000 |
| 7.- Follow up |  | 5000 | 5 |  |  | 25000 |  | 25000 |
| 8.- External Evaluation |  |  |  |  |  |  |  |
| . Rental car | 6562.5 | 3 |  |  | 19687.5 |  | 19687.5 |
| . Gas |  |  |  |  |  | 3000 |  | 3000 |
| .Hotel |  | 2250 | 2 |  |  | 4500 |  | 4500 |
| . Food |  | 750 | 3 |  |  | 2250 |  | 2250 |
| . Consultant salary |  |  |  |  | 50000 |  | 50000 |
| Total |  |  |  |  |  | 79437.5 |  | 79437.5 |
| Second Year TOTAL |  |  |  | 218937.5 |  | 218937.5 |
| Staff time |  |  |  |  |  |  | 32840.63 |
| GRAND TOTAL Second Year | Goudes |  |  |  |  | 251778.1 |
| Grand Total |  | US $$ |  |  |  |  | US $ | 7193.661 |
| TOTAL FIRST AND SECOND YEAR |  |  |  | US $ | 20,196 |