**Support to 12 informal schools with local volunteers’ project in Ruaraka, Nairobi.**

**LOGICAL FRAMEWORK**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **Intervention logic** | **Objectively measurable** **and verifiable indicators**  | **Sources of verifications**  | **Important assumptions**  |
| **Development objective/goal** | Improve educational standards in the informal schools in Ruaraka. |  Attendance at informal schools / Success rate of informal schools’ students | Schools’ registers / Public recordsAd-hoc survey / interviews with local people. |  |
| **Project objective/purpose** | To increase ratio of teacher to student from 1:60 to 1:25 in informal schools.  | School recordsTeachers records | School registersTeachers profile document | Cooperation between the school management and PV-Kenya |
| **Results/outputs** | 1. 12 informal schools benefit from volunteer teachers for one year. --------------------------------------- 2. 100 volunteer teachers and mentors teach and mentor pupils in the informal schools for one year ---------------------------- 3. 12 school reading and mentorship clubs established in each of the informal schools | Three way partnership agreement between PV, Volunteer and school-----------------------------------50% of pupils in each of the informal schools is mentored through this project----------------------------------- Reading clubs of 100 pupils in each school established-  | Project personnel will visit all schools and monitor project progressMonthly progress reports from volunteer teachers.End of school term reportsAnnual school reportsEnd term examination results | Healthy partnership agreement between schools management and PV-KenyaQuality service from volunteer teachers |
| **Activities** |  | **Project costs:** | **Necessary capital goods, materials and local financing** |
| Provide local informal schools with skilled volunteer teachers ---------------------------- provide 1-to-1 mentorship for a most in need child in public and informal schools----------------------------Establish school reading and mentorship clubs in each of the 12 informal schools. | Volunteer teachers allowances $ 60 for one month for 60 volunteers  Total cost = **$ 3,600.00**-----------------------------------Volunteer mentors allowances $ 25 for one month for 40 mentors  Total cost = **$ 1,000.00**------------------------------------Establish school clubs$50 for 12 informal schools for one term. Total cost for 3 terms. **$ 600 X 3 =$ 1,800.00**-----------------------------------Administrative cost for the project **$ 100****Total cost for the project** **$ 7,500.00** | Curriculum books from PV-Library.Local financing:* Monitoring and Evaluation of the project
* Teachers Teaching Guide and Curriculum books to be provided by informal schools
*

. |