**LURDES MUTOLA FOUNDATION**

**Quarterly REPORT OF ACTIVITIES**

**Period: September to December 2011**

|  |  |
| --- | --- |
| **Project name** | More School For Me |
| **Location** | Magude – Mozambique |
| **Number of girls (9th and 10th grade)**: | **35** |
| Monthly Budget: | **USD3000,00** |
| **Date** | **29th December´11** |
| **Reported By** | Victorino Adriano, CFO |

1. **INTRODUTION**

This report aims to update information on the progress of program activities more school for me during the period that lasts from September to December 2011. It brings an analysis of the progress that has been done and achievements of activities planned.

1. **PLANNED ACTIVITIES (September to December)**

|  |  |
| --- | --- |
| **Planned Activities** | **Achievements** |
| Actividades extra curriculares *(Sport & HIV Aids) – trainings per month (1)* | 70% |
| Melhorar a higiene e limpeza*Improve hygiene and cleanliness* | 70% |
| Reabilitar a sala de cozinha*Renovate the kitchen room* | 90% |
| Mais dedicação no estudo*More dedication in the study* | 90% |
| Bom relacionamento entre as meninas*Good relationship between the girls* | 90% |
| Boa saúde para as meninasGood health and medication for girls | 95% |
| Other activities/ Unplanned* Training the girls to use the Sewing machine
 | 20% |
|  |  |

* 1. **Implementation of Regular Activities**

|  |  |
| --- | --- |
| **Planned Activities** | **Achievments** |
| Acompanhamento Académico (1º, 2º e 3º trimestre)*Academic monitoring (1st, 2nd and 3rd quarter)* | 100% |
| Saúde e Saneamento;*Health and Sanitation* | 95% |
| Actividades Extracurriculares e Tempos Livres.*Extracurricular Activities and Leisure* | 50% |
| Monitoria e avaliação*M & E* | 100% |
| Logística e compra de comida*Logistics and purchasing food* | 100% |
| Logística, Equipamentos e Estruturas*Logistics and House rennovations* | 50% |
| Segurança (2 guardas)*Security (2 guard)* | 100% |
|  |  |

* 1. **Special Events:**
* 2 days visit in the homes of girls´s parents.
	1. **Major Challenges / Constraints**
* Lack of car to transport the girls in case of illness;
* Lack of money to pay all operating costs of the project
* Lack of money to attract more girls to project;
1. **General situation of girls in school**

|  |  |
| --- | --- |
| **Grade** | **Achievments** |
| Grade 9 | 100% passed with average of 13 marks |
| Grade 10 | Not published. We´re waiting for the final results |