# III. Project timeline and Budget

3.1 project log frame

| Global objective: To increase women’s capacity to prevent and respond to Gender Based Violence |
| --- |
| Specific objectives | Activities | Expected results | Indicator | Period |
| To identify project beneficiaries and develop the activity detailed program | Field plan visits to women with women council representatives and Associations commits | Appropriate project beneficiaries identified and plans of action finalized | Project beneficiaries in each district available and activity program | 1st – 2nd Month |
| To improve women’s knowledge on types and extent of gender based violence and is consequences | Training on nature and extent of sexual and gender based violence and its consequences as a human rights and development issue | Women s improved understanding on Gender based violence and its consequences | Training manual developed and training undertaken | 3td – 4th Month |
| To increase women’s awareness on their legal rights | Training on women’s legal rights in relation to gender based violence | Increased awareness on women’s rights | Training undertaken and guidelines on different laws developed | 5 --6th Moth |
| To develop women’s skills in sports for improved health and team spirit for prevention and response to sexual and gender based violence | Training of trainers teams and sports teams in different fields | Sports training team in place and sports teams established | Training undertaken and teams established | 7th – 8th month |

# Project Budget (amount in Rwandan Francs)

| Rubric | Quantity | Period | Unit cost | Total cost |
| --- | --- | --- | --- | --- |
| Note Books | 100 | - | 1,000 | 100,000 |
| Flip charts | 9 | - | 10,000 | 90,000 |
| Pens | 3 packets | - | 4,000 | 12,000 |
| Markers | 6 packets | - | 10,000 | 60,000 |
| Reams of paper | 10 | - | 3500 | 35,000 |
| Transport costs for Preliminary field visits for project beneficiary identification and program development | 1 vehicle | 6 days | 60,000 | 360,000 |
| Field allowances for the planning team during planning phase | 4 people | 6 days | 50,000 | 120,000 |
| GBV manual Development fee | 2 people | 5 days | 50,000 | 500,000 |
| Women’s rights guidelines | 2 people | 5 days | 50,000 | 500,000 |
| Photocopying and binding training modules for GBV | 100 copies |  | 3000 | 300,000 |
| Photocopying women’s legal rights guidelines | 100 copies |  | 3000 | 300,000 |
| Participants meals | 100 people | 30 days | 2,500 | 7,500,000 |
| Participants transport | 100 people | 30 days | 3000 | 9,000,000 |
| Venue | 3 halls | 30 days | 100,000 | 900,000 |
| GBV facilitators allowances | 1 | 30 days | 50,000 | 1, 500,000 |
| Women’s legal rights facilitators allowances | 1 | 30 days | 50,000 | 1,500,000 |
| Photocopying sports guidelines | 50 Copies | - | 3000 | 150,000 |
| Sports coaches training allowances | 2 | 30 days | 50,000 | 3,000,000 |
| Transport for facilitators | 1 Vehicle | 20 days | 60,000 | 1,200,000 |
| Accommodation and meals for facilitators | 4 | 30 days | 10,000 | 1,200,000 |
| Coordination costs including communication and transport within |  |  |  | 573,000 |
| Total |  |  |  | 30,000,000 |