PROJECT      DOCUMENT

FOR

LUUKA YOUTH DEVELOPMENT ASSOCIATION AND ADVISORY CENTER – UGANDA

P.O.BOX 437 JINJA . UGANDA

E-mail:luyudaac@yahoo.com

A Joint  Project of :

LUUKA YOUTH DEVELOPMENT ASSOCIATION AND ADVISORY CENTER , LUYUDAAC in Partnership with

GlobalGiving & Other Donors.

July  , 2009

# TABLE OF CONTENTS

1.0	Project description…………………………….……………	5

1.1	Introduction				…………………………...	5

2.0	Contextual Analysis………….……. ………………………..	8

3.2	Luuka Youth Development Association and Advisory Center…… .10

3.3	Formulation process of the project……………………………….	11

4.0	PROJECT JUSTIFICATION ………………………………	12

4.1       Problem statement…………………..………………………………12

4.2       Project area and Approach…………………….……… ……………14

4.3       Target Beneficiaries ………………………………………………...14

5.0	PROJECT OBJECTIVES ………………………………….	14

Outputs                                                                                               14

5.0	Project Implementation frame work………………………..……….14

7.1	Sustainability of the project………………………………………....19

8.0	Project Organization and Management ….………………….……...19

Inputs………….……………………………………….……………21

9.0	Monitoring, Reporting and evaluation ………………..……….…...21

10.0	Budget and Budget Break down.…………………………………21

Abbreviations

LUYUDAAC :……Luuka Youth Development Association and Advisory Center.

AIDS…….……….Acquired Immuno Deficiency Syndrome.

HIV………………Human Immuno Deficiency Virus.

ARVs…………….Antiretroviral Drugs.

EHIP……………...Empowerment of HIV/AIDS Affected and Infected Project.

GDP……………...Gross Domestic Products.

MOLSD………….Ministry of Gender Labour and Social Development.

ASU………………Agricultural Services Unit.

T.O.Ts…………….Training of Trainers.

# A. INFORMATION ON THE IMPLEMENTING PARTNER

# Full legal name:	          LUUKA YOUTH DEVELOPMENT

ASSOCIATION AND ADVISORY CENTER.

Postal address:		P.O. Box 437 Jinja –Uganda East Africa.

E-mail address: luyudaac@yahoo.com

Contact person responsible for the Project:

Kyayi  Moses   Coordinator

# LUUKA YOUTH DEVELOPMENT

ASSOCIATION AND ADVISORY CENTER

E-mail: kyayimoses@yahoo.com

Date of establishment:	1999

Legal status: 			Registered in Local Government Act

Iganga District Administration

Community Development Department .

Nature of the organization:	LUYUDAAC is a community Organization and

formed by the Community as an umbrella Organization

to serve all the Community Groups, Association and clubs in Luuka County/ Sub district in Iganga District.

Vision:

Development of all youth, males and females as activities of importance both to the members and to national economy.

Mission:

Alleviate poverty, conserve and sustain ably manage the environment in partnership with the neighbouring communities and other stakeholders for the benefit of the global community.

Values of the organization: Honesty, dedication, transparency, integrity

Main areas of activity:

The traditional roles of the LUYUDAAC   included advocacy, member education, training  and spokesman ship. These have since broadened to include catalyst for change and mobilizer of resources. Specifically LUYUDAAC engages in technology transfer from research institutions to farmers in order to improve productivity and incomes,  business advisory services, development ,environmental management, education and awareness, creation of self-employment by the Community members , youth and women empowerment.

Number of staff: 		4 full time and 5 part time field trainers.

PROJECT FACT SHEET

COUNTRY:                 UGANDA

SECTOR:                     HEALTH & ECONOMY

IMPLEMENTTER:     LUUKA YOUTH DEVELOPMENT

ASSOCIATION AND ADVISORY

CENTER

LUYUDAAC

CONTRIBUTION:    INKIND

DURATION:           2 YEARS.

REQUESTED GRANT:  32,500 US DOLLARS.

1.0 PROJECT DESCRIPTION.

Empowerment of HIV/AIDS affected and infected ( EHAI) project has three objectives:-

Promotion of Psycho-Socio counselling of the HIV/AIDS affected and infected persons, marginalised and disadvantaged Orphans affected by HIV/AIDS.

It also aims at sustainable income improvement at household level by 40 percent  through purchase and distribution of 10 In-calf Frisians Dairy Cows to the affected homes.

Purchase and distribution of 40 Exotic goats to the affected and infected persons who have limited land and can not afford to look after the Frisian Dairy cows.

Capacity building awareness and sensitization on modern animal production technologies so that the targeted  beneficiaries can enjoy higher sustainable income from milk sale and goat breeding.

The off-springs of the Cows and the goats will be passed onto the next HIV/AIDS affected and infected 10 for the cows and 40 for goats in the next 2 years of the project.

( EHAI) project also aims at Purchasing  and distribution of 200 Blankets to 200 HIV/AIDS affected and infected  Orphans .

The project aims at reducing  the spread of HIV/AIDS in Bukooma Sub County communities with a population of 15,000 people and among 9000 students  of 30 secondary School students with in the Sub County.

1. INTRODUCTION

The youth in Uganda constitute more than 30 percent of the population.

The most challenging problems facing the youth and the residents of  Bukooma Sub County is  AIDS / HIV which is as a result of unemployment, prostitution, un protected sex with infected partners and some cultural practices.

About 15% of the youth are attached with HIV/AIDS. 50% of the youth live under the poverty line. Most of the youth live in the rural areas where information on HIV/AIDS services relating to HIV/AIDS is required mostly but do not reach those in the rural community of Bukooma Sub County.

AIDS is the 6th leading cause of death for persons between 15 - 24 years of age. By 2010 one of every four youth in Uganda will be orphans.

The challenge of HIV infected adults are youth and women.

The assessments survey carried in November and the long term perspective study 2008 in Sub county community, secondary schools and other secondary information available clearly indicate a serious problem of increase in the number of HIV / AIDS effected persons, Orphans and spread of HIV / AIDS among male and female adults and the youth.

●About 60% of the children under the age of 5 years are affected with HIV / AIDS, 5% under nourished with 47% stated 16.5% under weight. About 84% of a house holds experience food shortages.

●About 15percent of the youth are also affected with HIV/AIDS.

●78 percent of the whole population of Uganda are youth.

● Only 21.3% of women and 18.6% of men have ever tested for HIV like wise the youth.

●58 percent of them are irritate.

●90 percent of the children between the age of 15-24 years of age are infected through vertical ( parent to child).

●1.1 million people live with HIV/AIDS .

●135,000 Ugandans get infected every year and less than 20 percent of the population are aware of their sero status.

●1.8 million Orphans have lost one of both parents to HIV/AIDS.

●135,000 are in need of ARVs.

● 80% of the youths and women sale the labour for food during periods of food shortage not because they do not have land but because of limited accessibility to agricultural extension services to them  in the agricultural business

●Death to HIV/AIDS is 80,000 people every year.

●80% of the youth and women are depending on subsistence Agriculture.

●Only 17.8% of the house holds are keeping local cows.

●About 84% of the community members are experiencing food shortages. During periods of food shortages 50% of the members sell their labour for food of 4.4% secure wild food.

The Long Term Perspective study  carried out in November 2008 in Bukooma Sub county and other secondary information available clearly indicate a serious problem of massive poverty among the rural women, youth and Orphans and inadequate food supplies in the entire Subcounty and Luuka county as a whole.

This document is  the out come of those efforts and represents a pragmatic stage towards addressing the problems facing the HIV/AIDS affected and infected  in Bukooma Sub county by LUYUDAAC and its donor partners, using LUYUDAACs extensive gross root net work.

Bukooma is a Sub county in Luuka County/ Sub District . The population of  Luuka is over 250,000 people with only 2 health Centre at  the Sub county level, but there is no any single hospital .In addition, Luuka County has a very high fertility rate. The recent Uganda Demographic and Health Survey, 2006 gives the following selected facts about Busoga region where LUYUDAAC lies.

From the above, it is clear that   Luuka County is in a very serious health crisis which has implications to all other sectors, namely education, production, and gender and rights issues, and others. Given the magnitude of the problem visa avis the available human, infrastructure, and other resources, it is clear that current strategies are not enough, and we need to take use of all possible avenues in trying to address the problem.

BUSOGA region, Mbale and Pallisa districts have the highest concentration of poor people, the Uganda Bureau of Statistics said in a report yesterday. 
It said more than 100 poor people live per square kilometre in the areas. 
In Luuka County of Iganga district, the poverty density per sub-county is more than 100 people, compared to Kibaale, Ssembabule, Mbarara and Kiboga which have less than 20 percent.

The gap between the rich and the poor is highest in central and lowest in northern Uganda.. 
Poverty density is the number of poor people (those living on less than a dollar a day) Unlike the central region, poverty rates in Busoga region, range from 27% to 62%. The highest rates are in Luuka( Iganga District) (62%) among other areas .
The report, called The Spatial Trends of Poverty and inequality in Uganda: 2002-2005, was launched yesterday by investments state minister Prof. Semakula-Kiwanuka at the Statistics House in Kampala. 

The data for the study was drawn from the 2005/2006 Uganda National Household Survey, and the 2002 Population and Housing Census. It sampled about 7,426 households in 874 rural sub-counties in 58 districts. 
The causes of the above were identified through a participatory approach and casual model was developed.

The social economical effects of HIV / AIDS manifest themselves in the country in various forms as high infant motility and mobility reduced physical and economical productivity  among the other adult population, stunted growth and low intellectual capacity among others.

The current programmes / activities related to HIV / AIDS prevention in the county, have had very low coverage and impact. So HIV / AIDS spread has continued to plague the county.

Based on the above, a plan of action has been developed for the county to provide realistic practical guidelines for addressing the HIV / AIDS problem.

The ( EHAI) project  aims at building awareness and reducing stigmatisation of the HIV/AIDS patients in Bukooma Sub County with the population of  250,000 people,

Psycho – Socio Counselling of the HIV/ AIDS infected and affected  persons, Free Condom Distribution and promotion of Voluntary  HIV/AIDS testing and counselling ( VCT) in 30 secondary Schools, training of the affected and infected in modern animal production technologies of   Frisians Dairy Cows and exotic goats .

10 In-Calf Dairy Cows will be purchased and distributed to 10 beneficiaries in the first year. The beneficiaries income will be increased by 40 percent at household level from milk sales.

40 Exotic goats will be purchased and distributed to 40 persons

( affected and infected )  with limited land and can not manage to look after a Friesian Dairy cows.

The beneficiaries income will be increased by 25 percent at household level through exotic goat breeding.

10 off-springs from the cows from the first beneficiaries will be distributed to the next beneficiaries in year 2 of the project who will also do like wise in year 3 and 4 respectively in a revolving system. This will also apply to the off-springs from the exotic goats.

200 blankets will be purchased and distributed to 200 HIV/AIDS affected and infected marginalised as well as disadvantaged Orphans.

Through the project, the community members will be linked to HIV AIDS testing and information centres and hospitals so that they can access the ARV and further to know the Sero status.

2.0 CONTEXTUAL ANALYSIS.

The situation of youths in Uganda.

Over all children and youth in Uganda comprise some 78 percent of the total population of 22.2 million people. However, the youths defined as the segment of the population, female and male, aged between 12 to 30 years constitute about 30 percent of the country's population. Majority of the youths lives in rural areas. It's estimated that more than 50 % of them live below the poverty line. Besides, evidence shows that about 28% of the youth are iliterate,and like in the general population,the female youths are more illiterate at 27% compared to the male youth at about 40%.Since the launch of the Universal primary Education [UPE] enrolment of children in school has greatly improved. Today,some 6.5 million children are enrolled under UPE.However,inspite of the UPE contribution to increase school enrolment,the school drop out rates are still high especially among females.

- About 63.4% of their households use their land for food crops and 6.4% use their land for food and cash crops at the same time.

- The only fertilizer used is farm mature which is used by 40% of the youth.

- Only 3.8% of the house holds are keeping local cows.

- About 84% of the youth are experiencing food shortages. During periods of food shortages 50% of the youth sell their labour for food of 4.4% secure wild food.

- About 80% of the house holds were getting information on modern animal production technologies from their neighbours and only 11% get intervention from extension workers.

- Whereas 10% of the youth reported the introduction of new crops in the farm lands, 70% did not have any new crops introduced.

Youth and women receive less than 5 % of agricultural extension services world wide. Their priorities are rarely reflected in agricultural research or national policies  and when they are, this is not reflected ( translated ) into practice in agricultural development planning.

School drop out youth are excluded from information and decision-making process, they remain invisible and un supported.

Uganda's education system continues to supply labour that targets mainly the "white collar jobs" in the formal sector, particularly in government. This has contributed to a relatively high rural - urban migration in the recent past. Never the less, most of the youth fail to get jobs and end up in urban slums and streets, engaging in anti - social activities like prostitution, sexual abuse, drug abuse which are the main root source of HIV / AIDS. Since 1993, the government of Uganda has taken steps to address the problems of youths.

In June 2001, the government, through the ministry of gender, labour and social development (MOGLSD) formulated a National Youth Policy tithed. A vision for youth in the 21st.Century. The overall great of the policy is to "provide an appropriate frame work for enabling youth to develop social, cultural and political skills so as to enhance their participation in the over all development process and improve their quality of life.

To meet the requirements of the said National youth policy, the government is in the process of finalising the National Action plan on youth. LUYUDAAC is a member of the multi - sectral committee at the District that supplements the role of the ministry of Gender and Social Development.

Ugandan Economy

Compared to the period between early 1970s and 1986 when the economy shrunk by 20%, economic growth has not fallen below 4% in any single year (average real growth of 6.3 per annum) since 1987. Despite concerns of recent slow down in growth, the performance of the economy remained strong in 2004/05, inspite of the adverse effects of the weather on agricultural production for the second successive year. The economy grew by 5.8% in 2004/05 compared to 5.9% in 2003/04 and it is projected that real GDP at market price will grow by 6.8 percent in 2005/06. Strong investment has been the backbone of overall economic growth. Real investment growth has averaged at 9.7% since 1986, with the investment ratio rising from 9.3% of GDP in 1986/87 to 22.3% of GDP in 2004/05. In 2004/05 real investment growth rate exceeded 10% for the fourth successive year. The out look of the economy is positive, with an average growth rate over the period 2005/06 to 2007/08 projected to average 6.2% per annum, compared to 5.5% for the last 5 years.

Industrial growth has averaged 10.2% per annum in real terms since 1986, outpacing growth in both services (7.1%) and Agriculture (3.8%). As a result the size of industry in total output has increased from 11.0% of GDP in 1986/7 to 20.4% in 2004/05, while subsistence Agriculture’s share has fallen from 28.9% to 17.2%. Industrial growth improved from 8.1% in 2003/04 to 9.1%, the highest industrial growth since 1998/99. The above mentioned positive achievements are a result of key economic reforms such as abolition of price controls, liberalization of markets, privatization and public expenditure control which have been successfully implemented and consistently maintained.

# The Agricultural Sector in Uganda

Agriculture is the second largest sector contributing 38.5% to GDP in 2003/04, second to services sector, which contributes 42.5%, having surpassed Agriculture due to emerging informal sectors since Structural Adjustment Programmes (SAPs). The Agricultural sector is dominated by food crop production for own consumption and marketing surplus; Food crops contribute 55% to monetary and 81% to non-monetary agriculture. The sector is the employer of 79% of the entire labour force, originating 32% household income from crop farming and another 26% from other agricultural enterprises; the sector has the largest concentration of the poor who are in rural areas engaged in agriculture.

In spite of its contribution to total GDP, the agricultural sector still has the lowest growth rate of the three major sectors by a considerable margin; the slight rebound in growth in the financial year 2004/05 represents a welcome reversal in the declining trend since 1998/1999.  Agricultural output is expected to grow by at least 3.7 percent in the financial year 2005/06, as food crop production recovers from the poor rains experienced in financial year 2004/05 and cash crop production is boosted by a rebound in coffee volumes.

3.0 Luuka Youth Development Association and Advisory Center

(LUYUDAAC).

LUYUDAAC was established in 1999 by the local community groups Associations and Clubs as an Umbrella body of Associations in Luuka County and a non profit community based organisation. Its mandate is to assist communities in the formation of formal groups, assist them to articulate the missions and visions and also to solicit donor support for these local, formal and informal initiatives at the grass root with no political Affiliations.

LUYUDAAC Constitutes of delegates who represent member associations to the general assembly. However, LUYUDAAC its self is rural based devoted to the promotion of sustainable Development.

LUYUDAAC mission is to alleviate poverty, conserve and sustainable manage the environment in partnership with the neighbouring communities and other stakeholders for the benefit of the global community.

3.1 LUYUDAAC'S Capacity to execute the project.

LUYUDAAC runs a project currently supported by Volunteer trainers from the Netherlands aimed at empowering needy orphans through Education.

Another project is about the Community empowerment through modern

Crop and  animal production technologies hence we have technical expertise in project implementation in rural communities and vast with problems in rural communities

As mentioned, the desire of LUYUDAAC to establish an  initiative for HIV/AIDS persons  started in November 2008 which LUYUDAAC conducted successful meetings on the situation of the HIV/AIDS affected and infected  in Bukooma Sub county. It is not worthy forgetting that besides its membership at the District C.B.O forum, LUYUDAAC is a member of the multi - sectrol committee at the District that supplement the role of the ministry of Gender and Social Development.

The ability of LUYUDAAC to mobilise and organise counsel and sensitise in Luuka county through innovative and proven methodologies and approaches is recognised in the District as well LUYUDAAC has over years build capacity and competence that will make it possible to contribute significantly to the national efforts to address the problem of HIV /AIDS among the Community members  of Bukooma Sub county. LUYUDAAC has an established grass root structure. Hence, it is feasible for LUYUDAAC to employ two main strategies in its quest to address the situation of the Community member.

One to mobilise the community for groups to formation to facilitate the delivery of the desire interventions (Building awareness and reducing stigmatisation of the HIV/AIDS affected and infected ) to them directly through their own structures and then linked to orphanage Education Centres. Two to open a "window" for the community members  in existing grass roots programmes especially those participating in the ( EHAI)  project, through which they will be linked to training and extension services, AIDS orphanage vocational skills development centres in other regions, connected the sick to referral hospitals to access ARVs among other interventions.

3.2: FORMULATION PROCESS OF THE EHAI PROJECT:

In the second half of the year 2008, LUYUDAAC conducted a meeting aimed at identifying the problems facing the community members and the  Secondary School students  in Bukooma Sub County. The most significant of this meeting was held in March 2009. The theme of this workshop reads: " HIV/AIDS and the Economy " .

The main objective of the workshop was to identify the core problem and root causes of HIV/AIDS, its effects to the community members and cause for the low participation of the affected and the infected   not only in local groups but in the national development process in general, suggest solutions and formulate strategies for solving the problems. The meeting identified the root causes of the problem and their effects, where were identified in the said stake holders meeting were enriched with in parts from county wide consultations with the affected and the infected  by other relevant agencies and government ministries.

Subsequently the root causes of the effect of HIV/AIDS to the community members in Bukooma Sub county and Luuka county were summonsed to be; inadequate skills in animal production, lack of HIV / AIDS sensitisation and awareness compaign, marginalization and stigmatisation of HIV / AIDS patients, high poverty among the homes of the affected and infected, Increasing number of Orphans, High prevalence of the HIV / AIDS pandemic  inadequate ideas and lack of effective mobilisation and support to the affected and infected ,lack of access to resources especially capital, negative cultural practices especially HIV/AIDS patients discrimination in social and economic realms.

As a follow up of the meeting, LUYUDAAC held further consultative meetings and later formulated this project document. With the benefit of wider consultations and hence better position of knowledge on the situation of the HIV/AIDS affected and infected persons  in Bukooma and Luuka county.

To further enrich the project document, it was later decided to make field visits to homes of the effected and infected to obtain a synoptic view of the situation.

The document takes into cognisance the on going efforts of the Government to integrate the affected and infected  in the national development process. It also ensures that the draft is coherent with the relevant government policies on HIV/AIDS and unemployment. Synchronise the document with LUYUDAC's current approaches regarding its development programmes.

4.0: PROJECT JUSTIFICATION:

Major issues to be addressed among others include;

- Low  Psycho - Socio - counselling.

- Low Co-operation with community members, youth, School Students in the Bukooma Sub county to access HIV/AIDS services.

- Social-economic problems such as poverty among the HIV/AIDS affected homes.

- Cultural practices which accelerate HIV / AIDS spread.

- Low and poor quality of animal breeds

6. 	Marginalised and disadvantaged HIV/AIDS Orphans.

The youth are energetic to support the Agricultural sector but current 90% of children between 15 - 24 years of age are infected through vertical (Parent to child).

This by 2010 one of every four children in Uganda will be infected or orphan and this affects the agricultural sector hence poverty and unemployment accelerated.

4.1: High Prevalence of HIV / AIDS Care.

About 60% of the children under the age of 5 years are affected with HIV / AIDS, 5% under nourished with 47% stated 16.5% under weight. About 84% of a house holds experience food shortages.

About 15 percent of the youth are also affected with HIV/AIDS.

78 percent of the whole population of Uganda are youth.

Only 21.3% of women and 18.6% of men have ever tested for HIV like wise the youth.

58 percent of them are irritate.

90 percent of the children between the age of 15-24 years of age are infected through vertical ( parent to child).

1.1 million people live with HIV/AIDS .

135,000 Ugandans get infected every year and less than 20 percent of the population are aware of their sero status.

1.8 million Orphans have lost one of both parents to HIV/AIDS.

135,000 are in need of ARVs.

80% of the youths and women sale the labour for food during periods of food shortage not because they do not have land but because of limited accessibility to agricultural extension services to them  in the agricultural business

Death to HIV/AIDS is 80,000 people every year.

80% of the youth and women are depending on subsistence Agriculture.

Only 17.8% of the house holds are keeping local cows.

About 84% of the youth are experiencing food shortages. During periods of food shortages 50% of the youth sell their labour for food of 4.4% secure wild food.

The Long Term Perspective study  carried out in November 2007 in Luuka county and other secondary information available clearly indicate a serious problem of massive poverty among the rural youth and women and inadequate food supplies in the entire subcounty and Luuka county as a whole.

About 63.4 % of the youth and women house holds use their land for food crop and 6.4 % use their land for both food crop and cash crops at the same time.

Bukooma Subcounty has a population of 50,000 and Luuka County has a population of over 250,000 people with only 2 health Centre at  the Sub county level, but there is no any single hospital .In addition, Luuka County has a very high fertility rate. The recent Uganda Demographic and Health Survey, 2006 gives the following selected facts about Busoga region where LUYUDAAC lies.

From the above, it is clear that  Bukooma which is party of Luuka County is in a very serious health crisis which has implications to all other sectors, namely education, production, and gender and rights issues, and others. Given the magnitude of the problem visa avis the available human, infrastructure, and other resources, it is clear that current strategies are not enough, and we need to take use of all possible avenues in trying to address the problem.

The causes of the above were identified through a participatory approach and casual model was developed.

The social economical effects of HIV / AIDS manifest themselves in the country in various forms as high infant motility and mobility reduced physical and economical productivity among the other adult population, stunted growth and low intellectual capacity among others.

The current programmes / activities related to HIV / AIDS prevention in the Sub county, have had low coverage and impact. So HIV / AIDS spread has continued to plague the county.

Generally, the female youth have high cases of infection and are more vulnerable than the male youth. The basic of this is partly because youth exhibit early sexual debate, averaged at 16 years for girls and 17.6 years for boys.

The root causes of this situation is poverty, unemployment, and drug abuse and peer pressure.

With high school drop out cases and violence in some marriages , women and female youths become vulnerable to such as prostitution, early marriages, crime, drug use and abuse and generally being exposed to insurmountable despondency and hopelessness in relation to economic prospects.

The  EHAI will contribute towards mitigation of the problems arising from the HIV/AIDS presence among community from the following main intercentions.

- Facilitate the mobilisation of youth, community women  groups , school going children and students from their schools on HIV/AIDS awareness and HIV management program in the organisation activities.

- Facilitate the collection and promote information sharing from international, national and local levels on HIV/AIDS through the study circle methodology.

- Organise willing members to serve mobilises and information agents to the peers in relation to HIV/AIDS pandemic through popular theatre, groups/drama, sports, choirs and relevant events. The objective of this is to promote social interactions, cohesion and spirit of solidarity and sharing not just among the youths but the entire members.

- Establish networking systems with leading NGOs /service providers working on combating the AIDS pamdermic to enhance mugigation and sensitisation efforts.

- The EHAI project will encourage community groups to link with NGOs agencies to establish health insurance programs for the youth group members.

  - The project areas and approach.

During the initial three years, the project will operate in Bukooma Sub county of Luuka County / Sub district comprised of 7 sub counties  in Iganga district.

4.3 Target beneficiaries

Male and Female Adults ,Orphans , Female and Male students.

Beneficially:	House holds

5.0 PROJECT OBJECTIVES

1. Increase awareness. Increase community awareness about HIV / AIDS among 15,000 community members and in 9,000 school Students of 30 Senior secondary  in order to reduce the spread by 99% in Bukooma Sub County .

2. Improve production of animal protein (milk) by 40% on average in homes of the HIV/AIDS affected and infected persons.

3. Improve the social welfare of the HIV/AIDS affected and Infected marginalised

Orphans by providing them with blankets as well as improving their Nutrition

by feeding them on milk just like any other child with  parents.

. Expected Outputs

ACTION PLAN:

For each broad objective, specific objectives, strategies and activities have been developed as indicated in the action plan and the detailed of the action are given in the planning matrix. The planning index below gives the planned coverage of the activities in the community and schools with in the Sub County.

5). 1 Action plan showing objectives, proposed activities and expected output.

General objectives 01: Promote psycho - Socio counselling.

Specific objective: Increase awareness. Increase community about HIV / AIDS among the community members and senior secondary school youth  in order to reduce the spread by 99% in Bukooma Sub County .

Activity 1. Establish a community HIV/AIDS counselling centre at the Sub County

level  where the youth and the local communities are to be met &

counselled against HIV / AIDS and against unfair youth related actions.

Activity 2. Create  awareness campaigns on HIV/AIDS among the community

members and  in 30 Secondary Schools of Luuka County through

mobilization and sensitization on the causes ,spread, effects and ways to

avoid the disease.

Activity 3. Educate the causes, spread, signs and effects of HIV/AIDS among the

community members and the secondary school students.

Activity 4. Encourage Voluntary HIV / AIDS testing and Counselling

and free contributions of condoms.

Activity 5. Promote and encourage abstinence, faithfulness among married couples

Condom use .

Activity 6. Free Condom distribution  to the targeted beneficiaries.

Activity 7. Training of 150 Community group  mobilizers and 150 School students

In issues of  HIV/AIDS awareness responsible to continue with the project   after in their school even after the end of this three years project within their communities and schools

Activity 8. Conduct  workshop on HIV/AIDS aimed at training of 150 Community

group mobilizers and school students  leaders in HIV/AIDS awareness groups.

Activity 9.Training 3 counsellors in refresher trainings  to impart skills and provide

personal services.

Activity 10. Printing sign posts carrying warning message to the youth about

HIV/AIDS.

Activity 11. Plant these sign posts along the compounds of these 30 secondary

schools.

Activity 12. Printing and publishing leaflets and brochures among community

members and the targeted.

Activity 13. Composing of interesting HIV/AIDS drama shows carrying messages on

spread, effects, mistreatment of Orphans and widows of HIV/AIDS with

in the community and the targeted schools.

Activity 14 Sensitize members on the effects and prevent  stigmatization of

HIV/AIDS  affected persons.

Activity 15.Composition of HIV/AIDS drama shows

This is an episode/play which carries a message on HIV/AIDS

The language in which it is composed is a mixture of both English and the

local languages.

There a number of episodes in different sub topics ie.

- What is HIV/AIDS

- Causes and Spread

- Effects on the Widows, widowers, Orphans and the Economy

- Also an episode on how to mitigate the spread and the effects.

Activity 16: Referring  and as well as links HIV/AIDS affected persons to referral

hospitals for ARVs.

Activity: 17. Procure one small  motor cycle to easy mobility in the community and

the 30 secondary School during implementation of all the above

activities .

Target Group: Community members and Secondary School Students.

Beneficiaries:  House holds.

OUTPUT: -

-    15,000 community members (females and male  adults and youth made

aware of  HIV/AIDS, its effects, its spread and how to reduce its spread

among the fellow community members.

-     9,000  Secondary school  students  made aware of HIV/AIDS

-    One HIV / AIDS youth counselling  centre opened in the entire County.

- Increased awareness as regards the issues of sex and sexuality.

- Positive behaviour change as a result of good sexual behaviours imparted.

- Reduced incidence of Sexually transmitted infections and HIV/AIDS.

- Increased awareness, knowledge, attitude of HIV/AIDS.

- Increased demand for counselling and testing services.

- HIV/AIDS complaint desks established at Sub County levels where Counselling  where youth services and activities are offered.

-    3 Counsellor trained in 10 refresher trainings.

-    Reduced incidents of HIV/AIDS among students of Bukooma Sub County.

-   150 School students mobilizers  equipped with skills on HIV/AIDS.

-   150 Community group mobilizers  equipped with skills on HIV/AIDS

-    30 Secondary School Headmasters equipped with skills on HIV/AIDS

and are  capable of carrying on the message among the fellow school    students and the community group members respectively .

-    Composed HIV/AIDS drama package/CDs  on HIV/AIDS effects

- Reduced stigma and increased demand for the counselling and testing services.

- HIV/AIDS drama groups/ actors composed of 10 persons formed and capable of carrying on the message even after the project.

- Increased abstinence, faithfulness, increased condom use

- Reduced incidence of unsafe abortions

- Evaluation and monitoring reports.

- Monthly reports.

5.2.	Specific Objective. 2

Improved production of animal protein (milk) by 40% on average in homes of the HIV/AIDS affected and infected persons.

Activity 1.      Promote specific activities which are intergrable like zero grazing &

encourage consumption of animal products.

Activity 2.	Training the targeted beneficiaries in improve on fodder and pasture

management .

Activity 3.      Train in use, preparation and management of farm yard and compost

Manure.

Activity 4.      Train members in the Zero – grazing concept and Exotic goat rearing.

Activity  5.     Train the HIV/AIDS affected and infected persons in Yoghurt making.

Activity  6.      Train in basic animal disease management and practices.

Activity  7.      Routine animal husbandry practices.

Activity   8.     Purchase of 10 In-Calf  and distribution of In-calf Frisian Dairy Cows

to improve their economic empowerment through milk production and

sales.

Activity   9.     Purchase of 40 exotic/improved goats and distribution to 40

HIV/AIDS affected and infected persons through goat breeding and

Sales.

.

Activity  10.    Purchase 200 blankets and distribute them to 200 HIV/AIDS affected

and infected Orphans.

Activity  11.   Train 10 livestock breeders at group level 4 for Frisian Dairy Cows and                     .                      10 for the Exotic goats who will be breeding goats for other members

to buy the good/improved breeds.

Out puts:

-    Begin with provision of 10 heifers 10 house holds will benefit in 1st year,

years implying increased production and consumption of milk and milk sales.

-    30 beneficiaries will receive cows in 3 years from the revolving system

( send a gift ).

-    40 HIV/AIDS persons receiving Exotic goats in year one of the project.

-    120  HIV/AIDS persons receiving Exotic goats in year 2&3 of the project.

-     40 HIV/AIDS affected and infected Orphans given blankets and are using them.

-     30 house holds with cows should have improved pastures and make fodder

leading to  reduce incidences of animal diseases in the 2nd year while other 50 also

planting improved pasture in preparation to receive the off-springs in the 3rd year.

- Increased income level of the targeted beneficiaries  from milk sales at farm level.

- Increased milk production and consumption.

- Increased adoption of improved animal breeds ( Dairy Cows ) the HIV/AIDS affected and infected persons

- House holds will be trained in modern animal production

- Reduced incidence of disease due to malnutrition and poor feeding.

- Improved protein in-take in the targeted homes.

Target: Female and Male Adults ,Orphans, Youth and Seconadry School Students

Beneficially:	House holds and Schools.

Other Indicators:

● 60% of the targeted persons  achieve 40% increase in animal production technologies, milk production and productivity hence income increment from milk sales.

● 60% of community groups record at least 40% increase in membership.

●Reduced incidences of HIV/AIDS infections.

●Increased number of persons going for voluntary HIV/AIDS Counselling .

●Percentage  increase in income earned by the HIV/AIDS affected and infected homes from milk sales and exotic goat breeding.

● 15,000 community members and 9,000 Secondary students made aware of

HIV/AIDS ( how it is caused, spread, its effects to human life and economy  and

how to reduce its spread ) and they will be going for voluntary Counselling and

testing and the infected  accessing ARVs from referral hospitals .

● Number of beneficiaries ( 20 ) receiving In-calf Friesian dairy cows in year 1 and 2.

● Number of beneficiaries ( 80 )  receiving Exotic Goats in year 1 and 2.

● Educational HIV/AIDS drama composed and exhibited  in the community and schools.

●Number of schools participating in the programme ( 30 Secondary Schools )

●Number of   HIV/AIDS affected and Infected Orphans given blankest and are using

them.

● Number of activities reported on and number of patients liked to referral hospitals.

● Number of participants getting involved in the training sessions.

●The percentage of the community members and students with improved health,

●Improved access to education/information in respect to HIV/AIDS.

6.   1 : Other Activities

Programme Management

- Procure one computer

- Procure one small motor cycle for easy mobility during implementation of the activities and throughout the 30 secondary schools

- Procure Stationery

- Selection of external facilitators

- Meetings and Networks

- Procure  motor cycle consumables & services

- Selection of 3 competent HIV/AIDS counsellor and one Animal Husbandry trainer.

- Selection of School  and HIV/AIDS affected and Infected persons   to participate in the project..

- Conduct special general meeting with these groups.

- Carry out monitoring and back stopping.

- To select  10 animal breeders for the goats and the cow to undergo training in animal breeding.

- Sensitize parish chiefs, sub county chiefs, Local council authorities and option leaders about the programme.

## SUSTAINABILITY OF THE PROJECT

7.1.1	Sustainability of the Project Activities

Luuka Youth Development Association and Advisory Center will continue being responsible for the successful management of the project activities after the completion . The Agricultural Services Unit ( ASU) will directly be responsible for ensuring that this is done. The activities to be managed will include provision of capacity building services, Zero-grazing and the Zero-grazing concept  with emphasis to animal husbandry, supervision,  and mobilization of the HIV/AIDS affected and  infected  in the formation of Savings and Credit Associations by contributing to share purchase, savings and credit extension to them selves since they will be income improvement  from milk sales and Goat breeding  . Mobilizing the members about savings and credit mobilization will start as soon as the project starts such that by the end of two years, the beneficiaries from the project  are aware of the importance of saving and credit services.

Under the Project, the ASU  staff capacity in animal product services, group business planning, capacity building, audit and supervision, membership mobilisation and training, monitoring and evaluation and group management , etc. will be built. After the project has ended, the Unit staff will continue undergoing refresher training programmes in the same fields to keep them abreast with the developments in Agricultural Business with particular emphasis to animal production,  micro finance industry and HIV/AIDS.

The technological needs of the  Agricultural Services Development Unit  are simple (a few computers and data processing and reporting  systems). These will be simple to maintain and operate even after the project has ended.

Luuka Youth Development Association and Advisory Center will manage the Project throughout its implementation and completion phases. This will be assured through the ownership of HIV/AIDS counsellors (staff and assets), which will be charged with its implementation and supervision thereafter. All the adult beneficiaries supported by the project will also become members of LUYUDAAC.

This will further cement and strengthen the relationship between LUYUDAAC .

8.0	Project Organisation and Management.

The following are strategic consideration regarding the organisation and

Management of ( EHAI) project.

- LUYUDAAC has on going developmental programme i.e. the send a Cow and the Empowerment of HIV/AIDS Orphans through Education. Hence, the ( EHAI) project will be integrated in existing LUYUDAAC structure and field net work.

# IMPLEMENTATION STRUCTURE

Any well wishers/good Samaritans

CO-ORDINATOR

HIV/AIDS Counsellors and Animal Husbandry / Trainers,

Community members, Groups and Secondary Schools

Community members, Groups and Secondary Schools

General objective  03

To monitor and evaluate all the planned activities.

3.1 Specific objective

1: Monitor the progress of the activities of programme per month.

Activity 1: Prepare monitoring reports as well as quarterly reports.

Activity 2: Collect the data on all the implemented activities.

4. Specific objective 4.

Evaluate the impact of the interventions.

Activity 1: Conduct a mid - term evaluation workshop to establish the changes in house hold health.

Activity 2: Conduct a terminal Survey with an up dated questionnaire to determine

the level of which beneficiaries are at the end of the Action plan.

Activity 3: Conduct a terminal evaluation workshop.

Output: - Representative samples selected for each activity implemented to use in

Collection of evaluation data.

- 1 stakeholder participating in evaluation.

- HIV / AIDS assessment report compiled.

- List of recommendations (corrective measures) drawn for activity improvement report.

- A final evaluation report prepared.

- Impact assessment report made.

Report on future prospects / sustainable measures (way forward) compiled.

10.BUDGET.

The project budget / amount requested is  32,500  US Dollars for two years

EMPOWERMENT OF  HIV/AIDS AFFECTED/INFECTED PERSONS

ACTIVITY PLANNING MATRIX AND BUDGET

General Objective 1: Promote Psycho-Socio Counselling

| Specific Objective | Strategy | Activity | Time Frame | Responsible officer | Location | Out put | Indicators | Inputs | Cost In US Dollars |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ●.Promote Psycho-Socio Counseling | ●.Create awareness among community HIV/AIDS affected and infected | 1. .Educate the HIV/AIDS affected and infected , community members on causes, signs and spread of HIV/AIDS plus the effects. | Begin 2009 -2011 | LUYUDAAC Staff and the Counsellor s | Bukooma Sub county | i). 15,000 Community members made aware of HIV/AIDS, causes , spread and effects and marginalization effects | i). 15,000 Community members (HIV/AIDS affected and infected ) made aware about HIV/AIDS, causes , spread and effects. ii) Attendance lists | i) Trainers ii) Training materials iii) Stationary iV) Facilitation v) Transport | 8,800 |
|  |  | 2.Educate the HIV/AIDS affected and infected , Secondary School Students on causes, signs and spread of HIV/AIDS plus the effects. | Begin 2009 -2011 | LUYUDAAC Staff and the Counsellor s | Bukooma Sub county | i). 9,000 Students made aware of HIV/AIDS, causes , spread and effects. | ii) Attendance lists ii)Number of participants mibilised, sensitized and trained . | i) Trainers ii) Training materials iii) Stationary iV) Facilitation v) Transport | Included in activity No. 1 |
|  |  | 3. Establish Community HIV/AIDS counselling Center at Sub county lever where the affected and infected will be accessing services at the end of the project. 4. Establish partnerships and networking Activity | Begin 2009 -2011 Begin 2009 -2011 Time Frame | LUYUDAAC Staff and the Counsellor s Responsible officer | Bukooma Sub county Location | Community HIV/AIDS counselling Center Established to bring services near to people Partnership agreement in place Out put | One HIV/AIDS counselling Center established Networking with Donor support Organizations Indicators | i) Trainers ii) Training materials iii) Stationary v) Transport Inputs | Included in activity No. 1 Included in activity No. 1 Cost In US Dollars |
|  |  | 4) Training Headmistress and Headmasters of 30 of Schools on issues of HIV/AIDS . | Begin 2009 -2011 | LUYUDAAC Staff/ Counsellors | Bukooma Sub county | 30 both Headmistress and Head teachers. sensitised, trained and made aware of all issues regarding HIV/AIDS. ( spread, causes, effects, how to avoid the spread and how to avoid stigma and marginalization of the affected and infected | i) Sensitization /mobilization trainings, seminars and meetings. Held. ii) Attendance list iii) 30 Headmistress and headmasters trained and in place . iv) Number of participants trained v) Project record | i) Trainers ii) Training materials iii) Stationary v) Transport | Included in activity No. 1 |
|  |  | 5) Training Teachers of 30 Secondary Schools on issues of HIV/AIDS . | Begin 2009 -2011 | LUYUDAAC Staff and the Counsellor s | Bukooma Sub county | 300 teachers. sensitised, trained and made aware of all issues regarding HIV/AIDS. ( spread, causes, effects, how to avoid the sread and how to avoid stigma and marginalisation of the affected and infected | i) Sensitization /mobilization trainings, seminars and meetings. Held. ii) Attendance list iii) 30 Headmistress and headmasters trained and in place . iv) Number of participants trained v) Project record | i) Trainers ii) Training materials iii) Stationary v) Transport | Included in activity No. 1 |
| Specific Objective | Strategy | Activity | Time Frame | Responsible officer | Location | Out put | Indicators | Inputs | Cost In US Dollars |
|  |  | 6) Training of 150 community mobilizers Schools on issues of HIV/AIDS . These will carry on the message among the community members on issues regarding HIV/AIDS even after the end of the project. | Begin 2009 -2011 | LUYUDAAC Staff/ HIV/ AIDS Counsellors | Bukooma Sub county | 150 mobilizers trained 7 parishes from one parish in 21 training sessions . | i) Sensitization / mobilization trainings, seminars and meetings. held ii) Attendance list iii) 150 mobilizers ( T.O.Ts) trained and in place to carry on the message on issues regarding HIV/AIDS among the fellow community members even after the end of the project iv) T.O.Ts trained and in place. | Trainers, Training materials, Stationary, Facilitation. | Included in activity No. 1 |
|  |  | 7) Training of 150 school students mobilizers ( T.O.Ts ) from 30 secondary Schools on issues of HIV/AIDS . These will carry on the message among the community members on issues regarding HIV/AIDS even after the end of the project. | Begin 2009 -2011 | LUYUDAAC Staff/ Counselors | Bukooma Sub county | 150 School Students mobilizers ( T.O.Ts) trained 7 parishes from one parish in 21 training sessions . | i) Sensitization / mobilization trainings, seminars and meetings. held ii) Attendance list iii) 150 mobilizers ( T.O.Ts) trained and in place to carry on the message on issues regarding HIV/AIDS among the fellow community members even after the end of the project | Trainers, Training materials, Stationary, Facilitation. | Included in activity No. 1 |
|  |  | 8) Compose and Exhibit HIV/AIDS Drama shows on the causes , spread, effects , mistreatment of the orphans, widows . ( Educative and interesting Shows ) |  |  |  | 150 drama shows and episodes in 30 schools ( 5 shows in each school) | i) Record of Drama shows / Episodes . ii) Records and attendances | i)Actors , Training materials, Stationary, Facilitation. | Included in activity No. 1 |
| Specific Objective | Strategy | Activity | Time Frame | Responsible officer | Location | Out put | Indicators | Inputs | Cost In US Dollars |
|  |  | 9. Encourage HIV/AIDS voluntary, testing. Counselling, promotion of condoms use, free condom distribution from the Health Department , Avoid stigma of HIV/AIDS patients, Promote abstinence and Faithfulness. | Begin 2009 -2011 | LUYUDAAC Staff and the Counsellor s | Bukooma Sub county | Increased condom use, Increased abstinence, faithfulness, Reduced stigma and Increased demand for counselling and testing services | i) Number Condoms distributed freely. ii) Number of Community member and school students going for testing services voluntarily iii) Stigma reduced iv) Abstinence and Faithfulness on increase. v) Increase in the use of condoms . | i) Free Condoms from District, Red Cross Uganda Health Department, ii) Number of patients tested, iii) Number of condoms distributed and used. iv) Number of Community and Secondary Schools students going for voluntary counselling.. | Included in activity No. 1 |
|  |  | 4. Procurement of 30 poster for planting in 30 Secondary Schools with warning messages . Warning Students about the dangers of HIV/AIDS at a precaution and reminder of this Disease | Begin 2009 -2011 | Coordinator | Bukooma Sub county | 1.30 Metallic posters ( Small bill boards ) planted in compounds of 30 Secondary Schools with messages warning Students about the dangers of HIV/AIDS. | 1. 30 metallic posters planted in 30 secondary Schools. ( one poster per School). | Funds for making 30 posters ( Small bill boards ) | 600 |
|  |  | 10. To select capable Counselors /trainers |  |  |  | 3 trainers | 3 counsellors/trainers selected who are trainable trainers |  | Included in activity No. 1 |
|  |  | 11. Select participating Secondary Schools |  |  |  | 30 Schools selected . | Records reflecting the number of Secondary schools selected and project monthly reports |  | Included in activity No. 1 |
|  |  | 12. To conduct special meetings with the Headmistress/ masters and of selected schools. |  |  |  | Special meetings held & 30 agreements signed & working relationship existing between LUYUDAAC and the Schools | Project agreements & records. |  | Included in activity No. 1 |
|  |  | 13. To hold review meetings |  |  |  | Monthly reports 1 Annual report minutes of meetings | Project records Minutes |  | Included in activity No. 1 |
|  |  | 15. Monthly and quarterly monitoring and progress of the activities being implemented. |  |  |  | At least two visits per month to the field by both coordinator monitoring officer | Project reports Monthly progress, monitoring report and quarterly reporting. |  | Included in activity No. 1 |
|  |  | Procurement of one small motor Cycle for easy mobility in all schools, the community and one computer for report preparation |  |  |  | One motor cycle machines procured and one computer respectively | Project reports in place. One small motor cycle and a computer in place Minutes and monthly report. Procurement documents in place | Funds | 1,250 350 |
|  |  | Sensitization of the School Headmistress and headmasters, and community leaders about the Project. |  |  |  | Teachers and Headmasters, Headmistress and Local council authorities sensitized about the project | Project reports. Minutes and monthly reports. |  | Included in activity No. 1 |

# General Objective 02:	Promote sustainable income & improvement on the sufficiency of food supplies for a

Nutritionally adequate diet for the HIV/AIDS affected and Infected persons.

| Specific Objective | Strategy | Activity | Time Frame | Responsible officer | Location | Out put | Indicators | Inputs | ## Cost In Dollars |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2.Improve production of Animal protein (milk) by 40% on average | 4.Increase adoption of high quality animals breeds and Exotic goat breeding . | 1. Promote specific activities which are integrable like zero grazing and the Zero-grazing concept in relation to Friesian Dairy Cows and Exotic goats and encourage consumption and sell of the subsequent products & grass management. | Begin 2009 -2011 | Animal Husbandry officer and STAFF. | Bukooma Sub county | i). 500 Community HIV/AIDS affected and infected members trained in modern animal production with particular Emphasis to Zero-grazing of Friesian Dairy Cows and Exotic goat breeding. | i). 500 Community members (HIV/AIDS affected and infected members trained in Zero- grazing of Friesian Dairy Cows and Exotic goad raring and breeding . ii) Attendance lists iii) Monthly report. iv) Trained members in place.. | i) Trainers ii) Training materials iii) Stationary v) Transport | 6,500 |
| Specific Objective | Strategy | Activity | Time Frame | Responsible officer | Location | Out put | Indicators | Inputs | ## Cost In Dollars |
|  |  | 2. Procurement of 10 In-Calf Dairy Cows and Distribution to HIV/AIDS affected and infected persons | Begin 2009 -2011 | Animal Husbandry officer and STAFF. | Bukooma Sub county | 1.Begin by providing 10 In-Calf to 10 HIV/AIDS affected and infected persons in year one of the project 2.20 house holds will benefit in the 2 years of the project. 3.increased production, sales & consumption of milk by 40 percent. 4.200 children consuming the products | 1. 20 HIV/AIDS affected and Infected having improved cows by the end of the 2 years of the project. 2.Amount of milk produced, sold & consumed Number of children consuming al least one of the products. 60% of the targeted persons achieve 40% increase in animal production technologies, milk production and productivity hence income increment from milk sales. | 10 In-Calf Friesian Dairy Cows. | 6,000 |
| Specific Objective | Strategy | Activity | Time Frame | Responsible officer | Location | Out put | Indicators | Inputs | Cost in US Dollars |
|  |  | 3. Procurement of 40 Exotic Goats Distribution to HIV/AIDS affected and infected persons | Begin 2009 -2011 | Animal Husbandry officer and Staff. | Bukooma Sub county | 1.Begin providing 40 Exotic Goats to HIV/AIDS affected and infected persons in year one of the project. 2. 80 house holds will benefit in the 2 years of the project. 3.increased production and exotic goat breeding , raring and sales by 40 percent at house hold level in the homes of the HIV/AIDS affected and infected . | 1. 20 HIV/AIDS affected and Infected having improved cows by the end of the 2 years of the project. 2.Amount of milk produced, sold & consumed Number of children consuming al least one of the products. 3. 60% of the targeted persons achieve 40% increase in exotic goat breeding and income from sales . | Fund for buying of 40 Exotic Goats for distribution to the targeted beneficiaries. | 6,000 |
| Specific Objective | Strategy | Activity | Time Frame | Responsible officer | Location | Out put | Indicators | Inputs | Cost in US Dollars |
|  |  | 4. Procurement of 200 blankets for Distribution to HIV/AIDS affected and infected Orphans | Begin 2009 -2011 | Animal Husbandry officer and Staff. | Bukooma Sub county | 1.Begin distributing 200 blankest to 200 HIV/AIDS affected and infected Orphans in year one of the project. | 1. 200 Orphans with given these Blankets and are covering them selves at night hence sleeping comfortably just like how any other child with parents would enjoy the night. | Funds for buying of 200 Blankets | 3,000 |
| 2.Improved pasture & fodder |  | Train the beneficiaries on the best types of animal pasture and fodder types, training in Hey preparations. Provision of resistant pasture seed | Begin 2009 -2011 | Animal Husbandry officer and Staff. | Bukooma Sub county | 1.20 house holds with cows should have improved pastures 2.50 community members making fodder. 3.maintain regular food supplies in the dry period | 1.Number of house holds with improved pastures 2.Number of members making fodder 3.Regularity of animal food supplies & milk out put | Pasture seeds | Included in activity No. 1 |
| 1. Monitor progress of activities per month | 1. To conduct monthly monitoring of the progress of the activities and Back stopping | Monitoring and backstopping | Begin 2009 -2011 | Animal Husbandry officer and Staff. | Bukooma Sub county | 1.reduced incidence of animal disease. 2.Increased milk 3.Improved feeding . 4. Improved Zero grazing shades. | 1.Reduced incidence of animal disease 2.Fence farmers 3.Increased in production of milk | i) Monitoring staff ii) Transport iii) Funds | Included in activity No. 1 |
|  |  | To sensitize and mobilize 90 teachers and 30 school Headmasters on Issues of HIV/ AIDS in the context of Education sector of Uganda. |  |  |  | 90 teachers trained, 30 Headmasters trained | Records reflecting the number of groups selected |  | Included in activity No. 1 |
|  |  | To conduct special general meetings & signing agreements with selected groups and the beneficiaries |  |  |  | 30 special general meetings held & 30 agreements signed & working relationship existing | Project agreements & records. |  | Included in activity No. 1 |
|  |  | To hold monthly meetings to review the progress of the project |  |  |  | Minutes of monthly meeting, Attendance lists 1 Annual report minutes of review meetings | Project records |  | Included in activity No. 1 |
|  |  | To carry out monitoring & back stopping |  |  |  | At east two visits per month to the field by each of the committee member or the coordinator | Project reports |  | Included in activity No. 1 |
|  |  | To train animal breeders in animal production technology . |  |  |  | 10 animal breeders will be trained & will be breeding animals ( exotic goats and cows) | Project reports and a breeding centre in place |  | Included in activity No. 1 |
|  |  | To train on use, formation and management of farm yard/ compost manure |  |  |  | 50% of the Beneficiaries use & are involved in the formation of compost /farm manure 50% of farmers reporting increased productivity per unit area. | Reports, farmers practicing in place. |  | Included in activity No. 1 |
|  |  | To train members in animal husbandry practices. |  |  |  | 500 members trained. | Reports training returns. Farmers practicing |  | Included in activity No. 1 |
|  |  | To arrange study visits for animal breeders to research establishments/centers |  |  |  | 10 animal breeders rained & practicing/adopting technologies learnt | Reports & farmers adopting the technology. |  | Included in activity No. 1 |
|  |  | To sensitize Parishes clients, sub county leaders and local councils about the project. |  |  |  | Clergymen local councils, secretaries for production & Parish clients sensitized about the project | Project reports |  | Included in activity No. 1 |