# PROJECT PROPOSAL DOCUMENT FOR LIVESTOCK REHABILITATION PROJECT PREPARED BY ALISA WOMEN’S FARMING PROJECT FOR FUNDING

Project Summary

## Name of Project	AWFP Livestock Rehabilitation Project

Name of implementing

organization	Alisa Women’s Farming Project ( with the supervision of RIAP – Lunsar

Contact Address	P.O. Box 1225 Siaka Stevens Street Freetown, Sierra Leone

Contact Person					Mrs. Fatmata Fofanah

Position						Project Co-ordinator

Type of Project	Livestock Rehabilitation Project

Location of Project				Panlap, Makarie Gbanti

Chiefdom, Bombali District

Type of Project Beneficiaries	Five Hundred and Eighty Five (585)

Duration of Project				1 (one) year

Legal Status – The project has registered with the Ministry of Agricultural, Forestry and Marine Resources, National Association of Farmers of Sierra Leone (NAFSL), Ministry of Rural Development and Local Government, Ministry of Social Welfare Gender and Children’s Affairs

Community Contribution			$ 1,596.2 (Le 4,790,000)

Amount of Fund requested			$ 61,251.1 (Le 183,754,000)

Total Cost						$ 62,848 (Le 188,544,000)

BACKGROUND AND PROBLEMS ANALYSIS

The war in Sierra Leone in the last decade brought untold suffering to the people and the in the North the people are still suffering under the hands of the armed combatants who will soon give up their weapons.

On the 20th of December 1998 certain Association were badly vandalized. After this date, the A.F.R.C/R.U.F occupies all the areas. Their stories were not good to hear. Among the atrocities committed were houses, school, and other privates and public properties, the scared believes of the people burnt, destroyed, vandalized and looted. The human right of the people completely disregarded. People were killed, hand chopped off, stripped naked, force to eat their feaces and drink their urine, flock publicly and used as labor gang. Raping and force marriages were the other of the day.

The Alisa Women’s Farming Project (AWFP) which is and umbrella organization of four Women’s Association in the Makarie – Gbanti Chiefdom recognizing its role, and aware of the plight of its people consulted with RIAP-Lunsar a local NGO operating in the chiefdom on how to assist it people from the pending doom.

Based on the advise of RIAP-Lunsar series of sensitization meeting and assessment were dome to ascertain the level of commitment and the capacity of the Alisa project executive and participants as well as the needs of the participants from the above certain findings, suggestions and agreement were reached.

- The executive agreed that Alisa Women’s Farming Project would work in collaboration with RIAP-Lunsar in the implementation of the project.

- Livestock (small ruminants), which were owned by participants, have been completely looted by the rebels during the war.

- There is no livestock available within the communities.

- Access to livestock is limited because of lack of funds.

It is in the view of this background that the Alisa Women’s Farming Project in collaboration with RIAP-Lunsar would intervene to alleviate the communities’ dire needs.

The project package also serves as a means of replacement of lost livestock. Since the farm families lack funds and alternative resources to purchase them, this will give back livestock to the participants who have lost everything in life.

PROJECT GOAL

The goal of the project is to improve the livestock level of 585 farm families in five (5) communities in the MAKARIE GBANTI CHIEFDOM, BOMBALI DISTRICT.

### SPECIFIC OBJECTIVES

To help provide 585 farm families with livestock (cows, goats, sheep and pigs) to restart and ensure diversified production by September 2009

To reduce malnutrition and increase livestock cows, goats, sheep and pigs available for 585 farms families.

### PRESENT NEEDS

In order to support our on-going activities, the association organized a general meeting and listed the following:

- To purchase 15 male cows and 60 female cows for the project.

- To purchase 20 boars and 40 soars, for the establishment of a piggery at the project operational areas.

- to purchase 20 male goats and 40 female goats for the project.

- To purchase 20 male sheep and 40 female sheep at the project operational area.

- To construct a pigsty (pen) of 40ftx 20ft in size at the project site.

- To produce animal fed, water well and drugs for verterinary services.

- To achieve the above immediate objectives the organization needs inputs of initial capital to purchase them in order to start these activities.

IMPLEMENTATION STRATEGY

The under-mentioned strategies will be carried out to achieve the set objectives.

- Community mobilization and sensitization for further understanding of the project.

- Purchase and distribution of livestock (cows, goat, sheep and pigs) and feed RIAP-Lunsar and the executive of Alisa Women’s Farming Project will ensure that certified food approval by the board are bought.

- Provision of food for work to assist the farm families in the hunger period and protect the livestock (pigs, goats, and sheep) from being sold RIAP-Lunsar has memorandum of understanding with Alisa Women’s Farming Project (AWFP) to supply food to every certified farm families who is involved in livestock farming.

- Supervision, monitoring, reporting and Evaluation of project activities.

OPERATIONAL COMMUNITIES

| VILLAGES | NO OF FARM FAMILIES TARGETED |
| --- | --- |
| Kerefay Panlap Mayambray Thokonba Balia | 255 55 136 86 53 |
| Total | 585 |

MONITORING AND EVALUATION

The project will be monitored by Alisa Women’s Farming Project trained executives and animators jointly with the beneficiaries under the rebular suprvision of RIAP-Lunsar. Every activities carried out will be monitored to ascertain whether it is done correctly, at the given time frame and whether the desired effect(s) is achieved. A monitoring questionnaire will be prepared with the help of RIAP-Lunsar and used daily by the monitors.

Evaluation would be done from to time at the middle period of implementation and end of each activity.

INSTITUTIONAL CAPACITY

Alisa Women’s Farming Project has carried out similar project in the past in the operational communities. There was a livestock bank project, which involved over 35 cows, 45 pigs, 42 goats and 24 sheep but was destroyed by the war.

The use of RIAP-Lunsar as supervising agency and the training of the executive and animators of AWFP will ensure an effective and efficient delivery system. The capacity of the institution will develop to a high level to be able to handle management of the people.

PROJECT FEASIBILITY AND SUSTAINABILITY

The people in the operational communities are peasent farmers who have been involved in all their lives in livestock (cows, goats, sheep and pigs). The technology is not new, it part of the way of life of the people.

The people are familiar with the raising of cows, goats, sheep and pigs and the breeds that would be selected and bought are suited to the areas.

Also cows, goats, sheep and pigs are easy to raise involving little or no cost and use of locally available materials for food and housing which ensures continuity needs external support.

BUDGET LINE ITEM

DONOR AGENCY’S CONTRIBUTION

| No | Items | Quantity | Unit Cost | Total Cost |
| --- | --- | --- | --- | --- |
| 1 2 3 4 5 6 7 8 9 10 | Cows (female Cows (male) Goats (female) Goats (male) Sheep (female) Sheep (male) Soars Boars Animal Feed Water Well Drugs & Vaccines Transportation of cows, goats, sheep and pigs & other items to project site. | 60 50 40 20 40 20 40 20 120 bags 1 Lump sum Lump sum | 1,500,000 1,200,000 220,000 180,000 250,000 220,000 175,000 160,000 35,000 5,500,000 4,500,000 2,400,000 | 90,000,000 18,000,000 8,800,000 3,600,000 10,000,000 4,400,000 7,800,000 3,200,000 4,200,000 5,500,000 4,500,000 2,400,000 |
|  |  |  | Total | Le 162,400,000 $ 54,133.1 |

DONOR AGENCY’S CONTRIBUTION PIG STY

(BUILDING)

| # NO | # ITEMS | # QUANTITY | UNIT COST IN LEONES | TOTAL COST IN LEONES |
| --- | --- | --- | --- | --- |
| 1 | Corrugated Iron Sheets | 12 bundles | 300,000 | 3,600,000 |
| 2 | Cement | 250 bags | 35,000 | 8,750,000 |
| 3 | Timber: 1” x 12” x12’ | 60 Boards | 14,000 | 840,000 |
| 4 | Timber: 2” x 12” x 12’ | 30 Pieces | 15,000 | 450,000 |
| 5 | Timber: 3” x 4” x 12’ | 10 Pieces | 13,000 | 130,000 |
| 6 | Timber: 2” x 4’ x 12’ | 50 pieces | 6,000 | 300,000 |
| 7 | Timber: 2 x 3 x 12 | 40 pieces | 2,700 | 108,000 |
| 8 | M.S. rods: ½” x 38’ | 55 length | 30,000 | 1,650,000 |
| 9 | M.S. rods: ¼” x 38’ | 10 length | 15,000 | 150,000 |
| 10 | Roofing nails | 40 packets | 5,000 | 200,000 |
| 11 | Head pans | 6 Head pans | 18,000 | 108,000 |
| 12 | Shovels | 5 Shovels | 45,000 | 225,000 |
| 13 | Wheel barrows | 3 wheel barrows | 100,000 | 300,000 |
| 14 | Binding wires | 1 roll | 90,000 | 90,000 |
| 15 | Double steel doors | 2 | 250,000 | 500,000 |
| 16 | Single steel doors | 1 | 175,000 | 175,000 |
| 17 | Window panes | 12 | 4,000 | 48,000 |
| 18 | Wire mesh | 4 roll | 75,000 | 300,000 |
| 19 | Wire nails (Assorted) | 150 packets | 5,000 | 750,000 |
| 20 | Tower bolts | 4 | 40,000 | 160,000 |
| 21 | Lockers | 3 | 30,000 | 90,000 |
| 22 | Paints (Assorted) | 22 gallons | 25,000 | 550,000 |
| 23 | paint brushes (Assorted) | 6 | 5,000 | 30,000 |
| # TOTAL |  |  |  | Le 19,354,000 $ 6,451.1 |

PIG STY BUILDING

LOCAL CONTRIBUTION

| No | Items | Quantity | Unit Cost | Total |
| --- | --- | --- | --- | --- |
| 1 2 3 4 | Land Sticks Food for work Skilled and Unskilled labor | Land 8 dozens lump sum | 2,700,000 40,000 850,000 1,200,000 | 2,700,000 40,000 850,000 1,200,000 |
|  |  |  | Total | Le 4,790,000 $ 1,596.2 |

Project Budget Summary in Leones and Dollars

| No | Items | Total cost in Leones | Donor Contribution In Leones | Local Contribution in Leones |
| --- | --- | --- | --- | --- |
| 1 | Livestock Production | 145,800,000 | 145,800,000 |  |
| 2 | Animal Shelter | 19,354,000 | 19,354,000 |  |
| 3 | Animal Feed | 4,200,000 | 4,200,000 |  |
| 4 | Water Well | 5,500,000 | 5,500,000 |  |
| 5 | Drugs and Vaccine | 4,500,000 | 4,500,000 |  |
| 6 | Transportation of cows, goats, sheep, pigs and other items to project site | 2,400,000 | 2,400,000 |  |
| 7 | Local Contribution | 4,790,000 |  | 4,790,000 |
|  | TOTAL | Le 188,544,000 $ 62,848 | Le 183,754,000 $ 61,251.1 | Le 4,790,000 $ 1,596.2 |