## Cost Estimate
Los Palis Water System Expansion Cost Estimate
| Project Budget |  |  | Material Price/Unit | Labor Price/Unit
| Los Palis, Haiti Water Supply | Quantity | Unit |  |  | Total
Installation of New Piping, Solar Pump, Panels, Tank, and Replacement
of Existing Piping
1. | 3" PVC pipe installation | 7511 | LF | 3.5 |  | 26288.5
2. | 2" PVC pipe installation | 2020 | LF | 2.1 |  | 4242
3. | 1.5" PVC pipe installation | 1670 | LF | 1.8 |  | 3006
4. | 1" PVC pipe installation | 651 | LF | 0.7 |  | 455.7
5. | 3/4" PVC pipe installation | 760.3 | LF | 0.4 |  | 304.12
6. | 1/2" PVC pipe installation | 330 | LF | 0.3 |  | 99
7. | Tees and Valves | 10 | Complete | 60 | $40 total | 100
8. | Trenching | 12942.3 | LF | 5176.92 |  | 5176.92
9. | Pipe fusing | 12942.3 | LF | 431.41 |  | 431.41
10. | Solar Pump/panels/tank | 1 | Complete | 15000 |  | 15000
11. | Contingency |  |  | 10% |  | 5510.365
| Total |  |  |  |  | 60614.015
|  |  | Remaining Funding Needed |  |  | 44500

## Schedule
Project Schedule
Task | Week
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Purchase and delivery of pipe materials
Trenching for piping replacement (roadways and taps)
Replace existing piping (roadways and taps)
Burying for piping replacement (roadways and taps)
Trenching for piping replacement (spring to cistern)
Replace existing piping (spring to cistern)
Burying for piping replacement (spring to cistern)
Clearing for new piping (well to cistern)
Trenching for new piping (well to cistern)
Install new piping (well to cistern)
Burying for new piping (well to cistern)
Solar pump purchase order to contractor
Install solar power pump, panels, tank
System test
Potential system test failure repairs
Contingency
Project Completion