Project proposal for Implementation Method

1.  Based Line Survey:

Give one day Training for School going Girl’s Volunteers and put them to involving the Based Line Survey to find out and register a Pregnant Women in 800 villages.

2. Formation of Pregnant women Club

- To form a 30 Clubs of each Club contain 100 Pregnant Women. In each club select 2 of them as a Head to Execute the Club.

- The main role of the Head of the club members are, Organize to awareness meetings, training programmes and Distribution of healthy noon meals

- Discuss the doubts in care of health.

- Associated with the project staffs

3. Awareness Meeting

- One awareness meeting for one Pregnant Women Club with Health Resource person and Project Staff in the selected villages.

- In the meetings,

  - Care of Pregnant Women and personal Hygiene

  - Necessity of Immunization

  - Clear the doubts of particulars

4. Orientation Training

- With IEC Materials like Pictures, Charts, Flash Cards, Family Welfare Instruments, related diseases training will be on

- Child survival

- Safe Motherhood

- Gender issues

- Family welfare.

5. Distribution of Healthy Noon Meals:

For 10 months, Healthy Noon Meals provided to each club of 100 members totally benefited 3000 Pregnant women members.

6. Monthly Report

Collect the monthly report in the every last week of the month from the concerned project staff and send the report to the donor report contains.

7. Evaluation

- Every 3 months in the year, we evaluate the project outcomes

- Evaluation under external evaluation, project staff

- End of the survey

8. Project Conclusion

- From this project we conclude the “Deathless Pregnancy and Delivery”

| PROJECT BUSINESS PLAN FOR CARE AND SUPPORT FOR 300 PREGNANT WOMEN IN TAMIL NADU Project Activities | 1st month | 2nd month | 3rd month | 4th month | 5th month | 6th month | 7th month | 8th month | 9th month | 10th month | 11th month | 12th month |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Based Line Survey |  |  |  |  |  |  |  |  |  |  |  |  |
| Awareness Meeting For Pregnant Women | 3 meetings | 2 meetings | 3 meetings | 2 meetings | 2 meetings | 3 meetings | 2 meetings | 2 meetings | 3 meetings | 3 meetings | 2 meetings | 3 meetings |
| Orientation Training For Pregnant Women | 2 trainings | 3 trainings | 3 trainings | 3 trainings | 2 trainings | 2 trainings | 3 trainings | 2 trainings | 2 trainings | 3 trainings | 2 trainings | 3 trainings |
| Distribution of Healthy Noon Meal and Medicines |  |  |  |  |  |  |  |  |  |  |  |  |
| Evaluation |  |  |  |  |  |  |  |  |  |  |  |  |
| End of The Survey |  |  |  |  |  |  |  |  |  |  |  |  |

Description of the symbols:

  - -  Based Line survey

    - -  Distribution of healthy noon meal and medicines

- -  Evaluation

      - - End of the survey

Detailed Budget

1. 	Project Co-ordinator Salary @ $250x12months

Including TA+DA+insurance etc..		 		=	$   2500

2. 	Two Assistant Co-ordinatior Salary @ $200 x 12

Months x 2 person including TA+DA+insurance etc..	=	$   4800

3. 	Rent for Electricity one month @ $ 60 x 12			=	$     720

4. 	30 Awareness Meetings (One pregnant Women club

100 members) 1 meeting @ $75 x 30 meetings

(Including organizing charges) 				=	$   2250

5.	30 Trainings (One pregnant Women club

100 members) 1 Training @ $100 x 30 trainings

(Including organizing charges)				=	$   3000

6. 	Distribution of a Healthy Noon Meals and Medicine

Transportations charges (One day @ $ 500 x 3000

Pregnant Women =	$ 15000 x 30 days 			=	$ 75000

7. 	Based line survey, reporting writing documentation

Stationerys, Registeres, Note books, Notice, IEC

Materials , Pictures & Charts etc…				=	$   2000

Total 						=	$ 90270

Grant requested from Global giving = $ 90270.00

Yours in Service,

L. Rajeshkannaa,

Managing Trustee,

WESWA Trust