WWWA FY10 Work Plan and Budget Summary

Objectives: WWWA will use $5,000 from IDEX to create a performance based on poems and stories written by the members of WWWA to combat increased xenophobia. WWWA intends to continue the Life Writing Project, an initiative of WWWA’s Cultural Awareness Program. During the process of producing this performance, participants will learn and refine their skills in community building, writing, editing, storytelling, computer literacy, performance and public speaking and video and film production.

The Cultural Awareness and Integration Program is one of the four key program areas that WWWA works within to mainstream women’s economic development and empowerment within South Africa.  The other three program areas are: HIV/AIDS Awareness and Management; Healing of Memories Training Series and an Advocacy Program.

Target Beneficiaries: 10-15 refugee women directly; audiences around the country indirectly.

Anticipated Outcomes:

As a result of this project, tentatively titled “Breaking New Grounds”, WWWA will:

- Raise awareness about refugee women within the broader South African society

- Raise the profile of the refugee community and their particular struggles

- Give a voice to the stories of refugee women

- Create awareness about the conflicts that often result in the displacement of people

- Create an atmosphere in South Africa of co-existence between refugees and local people thus combating xenophobia

- Create a video product that can be used to generate income to sustain the organization

The women participants will:

- Learn skills in writing, theatre and drama

- Build self-confidence

- Share and exchange cultural knowledge

- Empower themselves and each other

- Learn to document their stories on video and paper

Timeline for Project:

| Activities | Timeline |
| --- | --- |
| Creative writing workshops & training | August – October 2009 |
| Compiling, editing, typing, layout of scripts & rehearsals | November – December 2009 |
| Selection of participants for drama and story telling process | January 2010 |
| Computer literacy training (Facilitated by APC using ICT for social change) | January 2010 |
| Refine scripts with theatre and film director | February 2010 |
| Actual video shoot & marketing of shows | March 2010 |
| Performances begin | June 2010 culminating on World Refugee Day on June 20, 2010 |

WWWA Project Budget

| Budget Item |  |  |  |  | U.S. Dollars |
| --- | --- | --- | --- | --- | --- |
|  | Persons | Per Unit Cost | Days | Total in S. African Rands |  |
| Phase 1: General Training |  |  |  |  |
| Catering | 15 | 30 | 6 | 2700 | $338 |
| Venue |  | 200 | 6 | 1200 | $150 |
| Transport | 15 | 40 | 6 | 3600 | $450 |
| Facilitation |  | 300 | 6 | 1800 | $225 |
| Workshop Materials |  | 407 | 6 | 2442 | $305 |
| Total for Phase 1 |  |  |  | 11742 | $1,468 |
| Phase 2: Rehearsal/Advanced Training |  |  |  |
| Catering | 8 | 30 | 6 | 1440 | $180 |
| Venue |  | 200 | 6 | 1200 | $150 |
| Transport | 8 | 40 | 6 | 1920 | $240 |
| Facilitation |  | 1000 | 6 | 6000 | $750 |
| Total for Phase 2 |  |  |  | 10560 | $1,320 |
| Phase 3: Performance and Video Production |  |  |  |
| Camera person |  | 3000 |  | 3000 | $375 |
| Editing Consultative Workshop |  | 3500 |  | 3500 | $438 |
| Venue |  | 1200 |  | 1200 | $150 |
| Film Stock |  | 1000 |  | 1000 | $125 |
| Posters, flyers, invitation cards |  | 2000 |  | 2000 | $250 |
| Design Artist |  | 2000 |  | 2000 | $250 |
| Director |  | 5000 |  | 5000 | $625 |
| Total for Phase 3 |  |  |  | 17700 | $2,213 |
| TOTAL BUDGET |  |  | R40,002 | $5,000 |
| Global Giving Admin (15%) |  |  |  | $750 |
| IDEX Monitoring & Evaluation (10%) |  |  |  | $500 |
| Total Budget |  |  |  | $6,250 |