THE H.E.L.P PROJECT

Health Education and Liaison Project

### Progress Report

The nutritious meal programme started in villages showing the worst cases of malnutrition has had a very beneficial effect on the children’s health with project staff reporting an almost 90% drop in referrals for malnutrition.

Since the last report the work developing the community groups has continued. The Team has started a more systematic approach to discussions with the community groups identifying a subject for one month, e.g Malaria and trying to identify practical steps to implement in the village to create a Healthier Environment.

The work of starting Women’s Self Health groups in all of the Five Targeted villages has begun. Although this is not strictly health related it is a very important part of empowering the village women and confidence building.

The team now meets monthly, and during the past two Months Nick Hansen has been reviewing and supervising the Project. His recommendations will form part of a new Project plan, to be forwarded separately.

The Team benefited tremendously from our period of Training at MGIMS.

One of the effects of The Nurse’s Clinic’s has been a reduction in the Number of Patients attending the Doctor’s Clinic’s. We have seen a very noticeable reduction in the Number of diarrhoea and hygiene related cases in all targeted villages. We have been able to use the Vaccine Fridge at Kanjiar Centre for Tetanus injections.

The Total number of patients seen at Kanjiar Clinic during the report period was 432, and at Piani, 225.

The Total number of patients seen at the Nurses Clinics during the period was as follows,

##### Village Name

Kanjiar   Vinobapuri	Dadpur	Paini		Gangabigha

June	30		25		20		28		45

July	21		30		26		40		40

Aug.	35	Because of Monsoon	27		50		42

Sept.	45		30		35		43		36

Oct.	35		28		26		39		59

Nov.	50		45		60		41		80

Dec.	40		36		30		40		68

Jan.	10		12		15		17		20

Total patients checked by Nurse – 1399

Nurse Clinic

Presenting Problems

Kanjiar	Vinobapuri	 Dadpur	Paini	Gangabigha

###### ENT		15		10		26		20	35

Skin		45		35		52		55	60

Diarrhoea	10		5		00		10	15

Malaria 	20		15		16		20	25

(Fever)

Pregnant	20		18		15		18	20

Women

Measles	05		10		05			08

Pneumonia	12		15		15		10	12

Respiratory	 15		12		15		25	20

Typhoid	05		06					10

(Fever)

Rheumatic	25		20		15		20	25

Orthopaedic22		25		20		35	45

Headache	12		5				10	12

Circulatory	05				05			08

Minor Injury 10						10	15

Digestive	10		05		10		15	20

Luchoria	20		15		20		30	35

Anaemia	15		10		25		20	25

The average number of Health Group Members attending each Village Meeting during the period was as follows,

Village  Name		Members attendance

Kanjiar				70

Vinobapri			30

Paini				50

Dadpur				40

Gangabigha			60

The actual number of Patients attending each doctor’s clinic during the period and a summary of presenting problems were as follows

##### Village Name

Kanjiar   		Paini

June			45			20

July			77			19

Aug.			33			23

Sept.			85			41

Oct.			39			26

Nov.			55			28

Dec.			74			24

Jan.			24			18

Total Patients checked 631

Doctor’s  Clinic

Presenting Problems

Kanjiar   		Paini

###### ENT				45			15

Skin				75			20

Diarrhoea			25

Malaria 			35			15

(Fever)

Pregnant			20			05

Women

Measles			15			05

Pneumonia			20			09

Respiratory	 		40			20

Typhoid			10			00

(Fever)

Rheumatic			35			30

Orthopaedic		52			40

T.B				08			00

Injuries			10			00

Digestive			15			15

Circulatory			10			10

Others			17			15

The Actual Role and responsibilities of each Village health worker needs to be more Clearly defined. This work is going on. However here is a list of the designated Health Workers in each Village,

Kanjiar			Mrs. Asha Devi

Vinobapuri		Mrs. Sona Devi

Dadpur			Mrs. Hemanti Devi

Paini			Mrs. Patia Devi

Gangabigha		Mrs. Rekha Devi

We would like to provide a Basic First aid Kit for each Village worker and Each Village School.

Other work the team were involved in was the distribution of blankets in the cold weather, working in close cooperation with village school teachers,

We would like to involve the school teachers in the HELP programme to a Much Greater Degree. This work has already begun but again possible project changes are relevant here.

The team faced some disruption to the programme from Strikes and Political disturbances, but for the most part were able to work unimpeded.