Project Title

Vocational Training Center for 60 Poor Women’s Of Pakistan

Project Objective:

Empowerment of women through Vocational training center.

Project Area:

Slum areas of Hyderabad (Kali Mori and Sikanderabad)

District: Hyderabad Sindh

Project Summary:

The Slum areas of Hyderabad (Kali Mori and Sikanderabad) are neglected and backward people are living in a miserable conditions. They lack basic facilities of life as facilities of school, health center and road.

Mostly people are day earner they work hard whole day on low wages but they fail to full fill the needs of their family duo to these reasons women of these areas are working as a servants of the other houses their work start the morning time and end in evening means women also work whole day as males. Because of these reasons women can not give sufficient time to their homes and children’s, so there children’s have no proper diet and concept of school all time they play in the streets.

AHD organization wants to help them through the vocational centers, where the women can learn the new ways and techniques of sewing through the skilled teachers. In this way they became skilled and earn handsome amount of money and they will have no need to works in the others houses and can earn for heir family and themselves

Whole day at their homes and can give full attention to their children’s.

Registered Under:

Registered Under Societies Registration Act 1860 Registration No. 4091.

Proposed Budget:

| S. No. | Descriptions | Per month | Total amount per year |
| --- | --- | --- | --- |
| 1 | 2 Teachers | 600x2 =1,200 | 1,200 |
| 2 | Sewing Machine for 60 poor families | 75 x 60 | 4,500 |
| 3 | Rent of sewing Centers in two city slum areas of Hyderabad | 100*12*2 =2,000 | 2,000 |
| 4 | Required other material of sewing for two centers | 50*12*2 =1,200 | 1,200 |
|  | Total amount in US $ |  | 8,900 |

Project Activities:

- During 1st quarter in first phase women will learn stitching of baby cloths in first phase and in 2nd phase they will learn making of bed sheets and pillows of different kinds and making curtains.

- In 2nd quarter they learn show pieces in first phase and in 2nd phase they learn about the fashion designs.

- In third and last quarter they  will learn about the embroidery

Additional Skills Trainings modules:

- Women Training for Empowerment.

- Business development skills

- Collective saving and community participation through their won CBO/Self Help Group

Project Objectives:

- Empower women that they can address their financial and social issues

- To improve their creativity and skills

- To formed a CBO for self help and long term impact on women life.

Expected out puts:

Status of women will rise and there will be positive social change for them.

These women will be self –supportive and self -reliant, they will have earning power and skills for development.

Social life of women and children will reach higher level.

All income generation activities would be eco-friendly and sustainable.

Children of these women would enjoy better education, health and overall development leading to better citizens.

Targeted Beneficiaries:

Women of Kali Mori and Sikanderabad who are very poor and illiterate and working in the other houses are exploited in different ways.

Name of organization:

Association for Humanitarian Development (AHD)

Contact details:

Association for Humanitarian Development (AHD)

House # 142/C, Block-D, Unit No. 07 Latifabad

P. O. Box # 1094, Latifabad 71800, Hyderabad

Sindh, Pakistan

Ph: +92-22-3860880,

Fax: +92-22-8330582

E-mail: info@ahdpak.org, ahdpak@yahoo.com,

Website: www.ahdpak.org