Sahyog Work Plan and Budget

Project Title: Social Mobilization and Empowerment of Women SHGs for Improved Livelihood

Project Location: 25 villages of Lasadiya Tehsil of Udaipur district in Rajasthan.

Target Groups: Approximately 1,700 members. 80% of the members are small, marginalized tribal farming families.

A) Objective 1: To build the capacity of self help groups (SHGs) and create a system of documentation that will allow for the dissemination of experiences and lessons concerning this project.

Activities:

1) Project Level Monthly Meeting

- Meetings are planned for the 8th of every month.

- At each meeting, one member of each SHG will share work experiences.

- Increased planning efforts will focus on improving meeting attendance.

- 12 organized meetings will occur with bus fare reimbursement for participants.

2) SHG Group Trainings

- Plan to organize 5 trainings for 250 members of 50 newly formed SHGs.

- Training sessions will cover the following topics:

  - account keeping

  - planning

  - implementation

  - monitoring activities

  - leadership

  - convergence with line departments and Panchayats

- Trainings will enable SHG members to enhance vision and management skill.

3) Training for Panchayati Raj & NAREGA

- One proposed training on Panchayati Raj system and the National Rural Employment Program.

- Training will allow SHGs to actively participate in Panchayat meetings and mobilize financial support under NAREGA.

- 50 SHG members will participate in the 2-day workshop.

4) Experience Sharing

- Proposing 2 events focused on “peer sharing” for 50 selected SHG members.

- Will attempt to more effectively plan and implement meeting preparation as well as obtain financial contribution from participants.

5) Process Documentation

- Although process documentation has improved over the last 4 years, analysis and documentation remains weak.

- Will continue to collect data through monitoring with assistance from documentation specialists.

- Budget includes financial provision for consultant fees.

- Plan to complete 5 case studies whereby monthly progress reports are completed by a specified program monitor.

6) Health Educational and Treatment Camp

- Plan to organize 2 health checkup camps in project area.

- Camps will provide health education and examinations.

- Focus will be on women in interior villages.

- Doctors and specialists will be arranged.

7) Staff Training

- Increased focus on existing team over the last 4 years has improved staff activities, however entrepreneurship remains weak.

- Plan to increase entrepreneurship development with assistance from experienced staff.

- Plan to hold 2 orientation team trainings.

Anticipated Outcomes:

-60 SHG will regularly participate in project level monthly meetings and share work experiences.

-Periodic data collection of all 100 SHGs.

-500 people will benefit from the Health Education and Treatment Camp.

-Roughly 80 SHGs will maintain accounts and fills as a system.

-5 case studies will be completed and shared over a one-year period.

B) Objective 2: To facilitate natural resource development and management for sustainable livelihood.

Activities:

1) Renovation of Old Wells

- Wells are the only source of drinking and irrigation water in tribal and semi-arid areas.

- Have previously renovated 51 wells and 18 wells have been identified that need renovation work.

- Budget restraints will only allow for the renovation of 10 wells @Rs.15000 per well in the next one-year period.

2) Soil Water Conservation

- Soil erosion negatively affects farm production.

- Objective is to conserve soil and water in arable lands for increased production of crops.

- Work will be conducted in a group approach in contiguous areas on a watershed basis.

- Only 50% financial support will be provided and 50% will be borne by the beneficiaries.

- A proposed 1,000 cubic meters (covering approximately 30 hectares) will benefit 30 families.

3) Pastureland Development

- 3 units of pastureland in the Khodipipali, Patliya and Bharev villages have been developed over the past 4 years. All units are maintained by villagers.

- The Pataliya unit is weak and needs improvement of management.

- Proposal to develop 1-2 units of 20 hectares for fodder availability and conservation of soil and water.

- Cost is Rs.7000 per hectare and a total expenditure of Rs.140,000.

- Local community will contribute Rs.40,0000 and project support will equal Rs.100,000.

4) Promotion of Organic Farming

- Collaboration with the agricultural department over 2008-09 has resulted in concrete achievement.

- 20 farmers in the Bharev, Ghodaghati and Chikaldi villages have received financial support for improved seed demonstration and food processing.

- Seek to continue efforts towards convergence and relationship strengthening.

- Plan to mobilize support for 10 crop demonstrations for 10 families and 3 extended vermiculture units for 3 families.

- Villagers and agricultural department will incur all costs.

Anticipated Outcomes:

  - Effective use of water for irrigation on 10 wells that will lead to increased crop production.

  - Soil and water will be conserved in 30 hectares of arable land for increased farm production.

  - 20 hectares of pastureland will be developed and managed for increased fodder production for animals.

  - 10 families will benefit through increased production stemming from crop demonstrations.

  - 3 families will benefit from vermiculture units that will establish manure production.

C) Objective 3: To facilitate development of micro-enterprises in an effort to enhance economic empowerment.

Activities:

1) Horticulture Promotion

- Over the past 4 years, village farmers demonstrated horticulture activities as a supplementary income generation activity. These units are becoming learning points for others who wish to adopt the processes.

- Plan to continue providing quality sapling and training for horticulture activities.

- Increase efforts to mobilize financial support from horticulture department (asking for support of 500 sampling for a plantation).

- Propose to further upgrade the existing horticulture unit with proper monitoring and explore market facilities (as units will start fruiting).

- Plan to assist the agriculture department and villagers select the beneficiaries for a new plantation of 500 sampling.

2) Livestock and Dairy Promotion

- Previous experience in livestock and dairy promotion has been satisfactory.

- Seek to continue efforts for better livestock management and increased milk production for income generation.

- Propose to organize an animal treatment camp with veterinary support.

- Plan to facilitate the purchase of good breed animals (approx. 50) by an estimated 50 BPL families under Swarnjayanti Gram Swrojagar Yajana of government and banks.

Anticipated Outcomes:

-Increased income from fruit and milk production.

Budget: Sahyog Sansthan, Udaipur

| Activities | Units | USD$ Unit Cost | Project Contribution |
| --- | --- | --- | --- |
| A) Building Capacity |  |  |  |
| 1.Project Level Monthly Meetings | 12 | $34.00 | $409 |
| 2.SHG trainings (50 ppl per. 250 total) | 5 | $205 | $1,023 |
| 3.Panchayati Raj & NAREGA training | 1 | $205 | $205 |
| 4.Experience Sharing for 50 ppl | 2 | $205 | $368 |
| 5.Process Documentation: case studies | 5 | $205 | $1,024 |
| 6.Health Education & Check-up Camps | 2 | $123 | $204 |
| 7.Staff Training Sessions | 2 | $102 | $204 |
| Sub-Total | 30 |  | $3,437 |
| B) Bio-physical |  |  |  |
| 1.Renovation of Old Wells | 10 | $307 | $1,536 |
| 2.Soil Water Conservation (Hectares) | 30 | $123 | $1,843 |
| 3.Pastureland Development (Hectares) | 20 | $143 | $2,048 |
| 4.Promotion of Organic Farming |  |  |  |
| a) Crop Demonstrations | 10 | $20 | $200 |
| b) Vermicompost Trainings | 3 | $205 | $615 |
| Sub-Total | 73 |  | $6,242 |
| C) Micro-Enterprise Promotion |  |  |  |
| 1.Horticulture Promotion | 500 | $2 | $1,000 |
| 2.Livestock & Dairy Promotion |  |  |  |
| a) Animal Treatment Camp | 2 | $102 | $164 |
| Sub-Total | 552 |  | $1,164 |
| Sahyog Total |  |  | $10,843 |
| GlobalGiving Administration @15% |  |  | $1,626 |
| IDEX Program Evaluation @10% |  |  | $1,084 |
| Project Total |  |  | $13,553 |