My Community / Media Impact

Communicative Plan of Intervention -- Red Sida Cusco – Group for sexual and reproductive rights

January – December 2010

| Main audience | Adolescents and young people aged 12 to 19 from the Districts of Santa Ana (5,912), Santiago (10,920), and Santo Tomás (4,445) from the Department of Cusco (50% of the adolescent population from zones involved) | 10,639 adolescents |
| --- | --- | --- |
| Secondary Audience | Heads of families, (60% of heads of families of adolescents and young people) Teachers from Educational Institutions (20 teachers from each zone of intervention) | 7,648 heads of families and 50 teachers |
| Objective | “To promote and strenghten the appropiation processes of adequate information cooncering sexual reproductive health, with a focus on gender and cross-cultural communication, the main audience, reducing risky sexual behavior to prevent teen pregnancy, STI, HIV, and AIDS“. |
| Results | Indicators | Means of verification |
| Adolescents heightened their perception on their own vulnerability to pregnancy, STI, HIV, and AIDS. | 50 % of adolescents listened to the radionovela program (49.3% en 2009) 20% of adolescents participated in project activities: educational sessions, informational fairs and interventions of mobile phone providers (20.5% en 2009) 50% of adolescents who had sex without the use of a condom were aware that they could catch STI, HIV, and AIDS or could provoke an unplanned pregnancy (50% in 2009) | 2009 Base Line Survey 2010 Results of the evaluation’s impact Report on the application of Focus Groups with adolescents and young people aged 12 to 19 Participation Registry of community mobilization activities |
| Adolescents increased communication on sexuality with their parents. | 50 % of adolescents listened to the radionovela program (49.3% in 2009) 20% of adolescents participated in project activities: educational sessions, informational fairs and interventions of mobile phone providers (20.5% in 2009) 60% to 73% of adolescents mentioned having conversations on sexuality with their parents (50% fathers/ 63% mothers in 2009) | 2009 Base Line Survey 2010 Results of the evaluation’s impact Report on the application of Focus Groups with adolescents and young people aged 12 to 19 Participation Registry of community mobilization activities |
| Adolescents knew and exercised their sexual and reproductive rights: to various services, information about sexuality and living free from sexual violence. | 50 % of adolescents listened to the radionovela program (49.3% in 2009) 20% of adolescents participated in project activities: educational sessions, informational fairs and interventions of mobile phone providers (20.5% in 2009) 32% of adolescents knew that they had rights to various services, information on sexuality and living free from sexual violence (16% in 2009). 35% of adolescents knew of health facilities where they could receive information on sexuality and condoms free of charge (29% in 2009) 60 % of adolescents were willing to go to a health center to ask for condoms (52% in 2009) 30% of adolescents consulted health services to ask for information on sexual and reproductive health (25% in 2009) | 2009 Base Line Survey 2010 Results of the evaluation’s impact Report on the application of Focus Groups with adolescents and young people aged 12 to 19 Registry of primary health centers with different services in three districts Participation Registry of community mobilization activities |
| Adolescents changed their attitude concerning the use of condoms, because they knew that its use was more pleasant. It was easily accessible and protected them from unplanned pregnancies, STI, HIV, and AIDS. | 50 % listened to the radionovela program (49.3% in 2009) 20% of adolescents participated in project activities: educational sessions, informational fairs and interventions of mobile phone providers (20.5% in 2009) 60% of adolescents knew about the efectiveness of condoms to prevent unplanned pregnancies, STI, HIV, and AIDS (51% in 2009) 34% of adolescents knew how to use condoms properly. (17% in 2009) | 2009 Base Line Survey 2010 Results on the evaluation’s impact Report on the application of Focus Groups with adolescents and young people aged 12 to 19 Participation Registry in the Radionovela program Participation Registry of community mobilization activities |
| Heads of familities who listened to the radionovela program valued communication with their children abpit sexuality as a practice that contributes to the prevention of STI, HIV, and AIDS | # of heads of familities who listened to the radionovela, were ready to comunicate on the subject of sexuality with their children and adolescents. # of heads of familities who agreed that their children and adolescents should have sexual education at their schools. | Reports on Focus Groups with parents who listened to the program (identified based on the survey applied to adolescents). |
| Teaching Tutors incorporated the radio novela as a work instrument with adolescents | 40 teachers from the three zones involved utilized the radionovela as working instrument for at least 3 tutoring sessions | Reports on tutoring sessions submitted by teachers (using an easy format). |

| Activities | Indicators | Means of verification | Months | Staff |
| --- | --- | --- | --- | --- |
|  |  |  | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec |  |
| Design of Radio Novela |
| Formative Res. | Research cabinet | Document | X | X |  |  |  |  |  |  |  |  |  |  | Technical Project Team |
| Adjustments to the Plan | Plan approved | Document |  | X | X |  |  |  |  |  |  |  |  |  | Shirley Palomino Maritza Castro, and Rosario Salazar |
| Revision and adjustment to the 2009 values grid for 2010 | Grid agreed | Document |  | X |  |  |  |  |  |  |  |  |  |  | Shirley Palomino Maritza Castro, and Rosario Salazar |
| Meeting to work on the radio novela plot, Values Grid, and collection of stories and characters | 1 radio novela plot | Document |  | X |  |  |  |  |  |  |  |  |  |  | Shirley Palomino, Maritza Castro, Rosario Salazar, Omar Ortiz, Oscar Contreras, René Contreras, Blanca Churats |
| Creative Sessions with adolescents to: collect stories and characters for the continuation of the radionovela | Report on the Sessions | Document |  | X |  |  |  |  |  |  |  |  |  |  | Blanca Churats, Shirley Palomino, Maritza Castro and Rosario Salazar |
| Workshop on production of radio novela plot: storyline, characters map and plan blocks, 12 chapters Visit from the Consultant | weave 1 dramatic plot line, 1 map, 1 plan, chapts. Visit | Record/Report and documents products |  | X | X |  |  |  |  |  |  |  |  |  | Technical Project Team -Red Sida Cusco Javier Ampuero |
| Design of the radio magazine | Radio magazine | Document |  | X | X |  |  |  |  |  |  |  |  |  | Technical Project Team Javier Ampuero |
| Contracts with radio broadcasters or program team: a) Radio Quillabamba in Santa Ana; b) Radio Santo Tomás in Santo Tomás; c) Radio to be defined in Santiago | Contracts | Document |  |  | X | X |  |  |  |  |  |  |  |  | Technical Team |
| Coordination with Municipalities (agreements) | Agreement | Document |  |  | X | X |  |  |  |  |  |  |  |  | Technical Team |
| Signature of contract with scriptwriter, producer and actors | Signed contract | Document |  |  | X |  |  |  |  |  |  |  |  |  | Technical Team |
| Production and broadcast of radionovela and magazine |
| Writing of 2 pilot chapters | 2 chapters written revised | Archives |  |  | X |  |  |  |  |  |  |  |  |  | Blanca Churats and Omar Ortiz |
| Casting/ Preproduction | Complete Casting of actors | Listing |  |  | X |  |  |  |  |  |  |  |  |  | Blanca Churats and Omar Ortiz |
| Recording/editing of 2 chapters for validation of radionovela | 2 chapters | 2 chapters recorded to be validated |  |  | X | X |  |  |  |  |  |  |  |  | Blanca Churats and Omar Ortiz |
| Validation of 2 pilots with focus groups | Focus Groups | Report for validation |  |  |  | X |  |  |  |  |  |  |  |  | Omar Ortiz |
| Writing and revision of 12 chapters. Collecting conclusions of validation with audience. | 12 chapters written and revised | Archives |  |  |  |  | X | X |  |  |  |  |  |  | Blanca Churats and Omar Ortiz |
| Recording/editing /postproduction of radionovela | 12 chapters | Audios |  |  |  |  |  | X | X |  |  |  |  |  | Blanca Churats and Omar Ortiz |
| Design of Radio magazine structure Santiago, casting of production and presentation of radio program Santiago | 1 structure, 1 team | Document and participation registry |  |  | x |  |  |  |  |  |  |  |  |  | Blanca Churats and Omar Ortiz |
| Broadcast of 16 programs from Phase I on 3 broadcasts | 48 programs | Audios |  |  |  | X | X | X | X |  |  |  |  |  | Technical Project Team |
| Broadcast of 12 programs on 3 broadcasts | 36 programs | Audios |  |  |  |  |  |  |  | X | X | X |  |  | Technical Project Team |
| Development of methodological guides for the chapters of the radio novela | 12 Methodological guides | Document |  |  |  |  |  | X | X |  |  |  |  |  | Omar Ortiz |
| Community Activities |
| Skill development training sessions with teaching tutors (from 11 schools, 3 zones) on use of radionovela | 11 sessions (1 x school), with 50 teachers | Report |  |  | x | x |  |  |  |  |  |  |  |  | Omar Ortiz, Blanca |
| Accompaniment for tutoring sessions of trained teachers | 22 sessions | Report |  |  |  |  | x | x | x | x | x | x | x | x | Omar, Puririsum (Lili), Mujer Sana (Yizza) and PRODIFAM (Alejandrina) |
| Educational sessions on sexual and reproductive health rights, use of condoms, intergenerational comunication with youth groups (2 Santiago, 1 Santo Tomás, 1 Quillabamba). | 12 meetings | Report |  |  |  | X | X | X | X | x | x | x |  |  | Omar Ortiz, Juan Rendón, Lili, Walter, Charo, Aleja |
| personal skill development training in health on the use of the radionovela (promotión of health working healthy schools) | 1 skill development training, 38 profesionals | Report |  |  | x |  |  |  |  |  |  |  |  |  | Lida Cuaresma, Omar, Shirley, Blanca, Aleja, Yizza |
| Educational sessions and promotion of the radionovela by mobile phone providers:street interventions, video forums, interventions in public transport. | 7 interventions | Report |  |  |  | x | x | x | x | x | x | x |  |  | Omar and promotores móviles |
| Informative Fairs in spaces for socialization of adolescents and youths (1 Universidad Andina, 1 San Antonio Abad, 2 Puririsum, 1 World AIDS Day) | 5 Fairs | Report |  |  |  | Pu |  | UAC |  |  | Pu UNSAAC |  |  | 1 | Technical Project Team |
| Propaganda radionovela / radiorevista |
| radionovela / radio magazine Logo | 1 Logo | Document |  |  |  |  | X |  |  |  |  |  |  |  | Technical Project Team |
| radio spot and promotion of radio novela phase 1 | 1 radio spot | Audio |  |  | x |  |  |  |  |  |  |  |  |  | Blanca Churats and Omar Ortiz |
| radio spot and promotion of radio novela phase 2 | 1 spot en promotion | Audio |  |  |  |  |  |  | x | x |  |  |  |  | Blanca Churats and Omar Ortiz |
| Dis/prod materials propaganda posters, polo shirts. | # materials produced | Samples |  |  |  |  | X |  |  |  |  |  |  |  | Technical Project Team |
| Distribution materials of propaganda | # materials distributed | List of distribution |  |  |  |  |  | X | X | X |  |  |  |  | Technical Project Team |
| Preparation and official launch of materials for 2010 radionovela: (promotional trailer, press release, help, report on 2009 results, testimonials, banner, etc | # Materials produced | Samples |  |  | x |  |  |  |  |  |  |  |  |  | Technical Project Team |
| official launch of second day of radionovela (including promotion of results of first day), with participation of listeners, health authorities, education, municipality. | 1 press conference | Report |  |  |  | x |  |  |  |  |  |  |  |  | Lida, Puririsum, Kallpa |
| Sustainability / Community Building |
| Local Management contributions (2 x 1) | 100% of contribution amount for the project | Letter |  |  |  |  |  |  |  |  |  |  |  | X | Technical Project Team |
| Training/participation of adolescents to act in 2010 radionovela | 10 mobile phone providers # Adolescents of Puririsum | Registry participation |  |  | x | x |  |  |  |  |  |  |  |  | Technical Project Team |
| Training/participation of adolescents for production and presentation of radio magazine in Santiago | 10 mobile phone providers and # Adolescents of Puririsum | Participation Registry |  |  | x |  |  |  |  |  |  |  |  |  | Technical Project Team |
| Management of local alliances for the utilization of radio novela as tool for broadcasting in prevention of STI, HIV, and AIDS and for education sessions (tutoring) with adolescents | Agreements 11 Educational Institutions | Documents |  |  | X | X | X | X |  |  |  |  |  |  | Technical Project Team |
| Professional training session with reporters, volunteers on communication and HIV: creation of non discriminatory messages. | 1 session | Report |  |  |  |  |  |  |  | x |  |  |  |  | Media Impact and Technical Project Team |
| Systematization/Mentoring |
| Plan of intervention, Budget | 1 plan 1 budget | documents | x | x |  |  |  |  |  |  |  |  |  |  | Technical Project Team |
| Monthly report/ final | 2 reports | documents |  |  |  |  |  | x |  |  |  |  |  | x | Technical Project Team |
| Qualitative Monthly reports | 9 stories, anecdotes or photo galleries | archives |  |  | x | x | x | x | x |  | x | x | x | x | Technical Project Team |
| Mentorship Visits: a) planning and radionovela; b) monitoring, focus and interviews | 2 visits | Reports |  | a |  |  |  |  |  | b |  |  |  |  | Media Impact |
| Evaluation and Monitoring |
| Development of instruments for registry and monitoring of the whole Project’s process | # instruments | Formats |  |  |  | X |  |  |  |  |  |  |  |  | Technical Project Team |
| Permanent Monitoring of the entire Project’s process | 10 monitoring | Reports |  | X | X | X | X | X | X | X | X | X | X |  | Technical Project Team |
| Permanent Monitoring of broadcasting programs (84 shows) | 9 monitoring (3 x zone) | Reports |  |  |  | X |  |  | X |  |  | X |  |  | Omar Ortiz |
| surveys from final Evaluation: design, application and catch | 476 surveys | Report |  |  |  |  |  |  |  |  |  |  | x |  | Omar Ortiz |
| Evaluation of the process |  |  |  |  |  |  |  |  |  |  |  |  |  | X | Technical Project Team |