| Title | Scholarship for the Infantile christian Student of underprivileged sweeper colony - SISU |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Location | Country : Bangladesh Region : Chaklapara village of Lohagara Upazila of Narail district , adjacent to the Antiakhia Bapist church . |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Duration of the action | 12 months |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Amount requested | US $ 8000 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Goal | To ensure education facility of underprivileged christian student to bring them into mainstream of society. Because the target group are deprived and hard core poor community |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Objectives | - To provide the target group with monthly stipend . - To provide the targeted children with notorious food - To provide the target group with educational accessories. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Target group(s)[1] | The target groups are 25 underprivileged christian students of neglected sweeper colony / slum. The family of targeted group are living under hard core poverty line, most of the family earns less than 1 dollar in a day ; 70% of the income is spent for purchase of food . The targeted group is enrolled with a local community school but they are deprived from cloth, nutrious food, educational accessories and conveyance because of such reason drop out rate is more than 60 % at primary level. The dropped out are going to work station and other inhuman works to lead their life. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Estimated results |  The education facility of all the 25 students will be ensured.  The indispensable nutrition of growing children will be available.  The initiative will encourage the entire guardian and others to continue education. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activities | Activity 1: Monthly stipend A monthly allowance will be given to the targeted 25 student , incase of distibuting this amount the plan is here asunder : 19 student of class one will be provided with $ 8 per month per head , 2 student of class four and 4 student of class two will be provided with $ 8 per month per head . The student are advice to spent those amount for tution fee, conveyance ,umbrella , medicine , recreation and other educational purpose . The amount also ensure their food security , their parents will not creat any pressure on them to go to work / make earnings . So, the stipend will work as the shield of the targeted group . Activity 2: Providing dress The entire 25 student will be provided with the dress for two times during the project period. All the family of targeted group is living under extreme poverty line so they have no ability to buy dress for their children. Therefore, providing the dress will meet their basic need, which contributes to continue education smoothly. This activity will be taken place 1st to 2nd and 7th to 8th month of the project period. Activity 3: Educational accessories The entire 25 student will be provided with educational accessories like bag, pencil, notebook etc. All the family of targeted group is living under extreme poverty line so they have no ability to buy accessories for their children. Therefore, providing the accessories will contribute to continue education smoothly. This activity will be take place 1st to 2nd month of the project period. Activity 4: Nutritious food for children All the family of target group earns less than $ 1 in day , about 75 % of their earning is spend for buy food . The target group is taking only 1800 Kcal. in a day against 2122 Kcal., so they are suffering from malnutrition how they will continue education . To remove this problem we like to provide 1 snacks and lunch in every day at their home . The food package will include ingrtedient meat,fish , rice , vegetables and others . |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activity chart (Gantt chart) | Activity | 1 | 2 |  | 3 | 4 | 5 | 6 | 7 |  | 8 | 9 | 10 | 11 | 12 |  |  |
|  | Monthly stipend | * | * |  | * | * | * | * | * |  | * | * | * | * | * |  |  |
|  | Providing dress | * | * |  |  |  |  |  | * |  | * |  |  |  |  |  |  |
|  | Providingeducational accessories | * | * |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Nutritious food | * | * |  | * | * | * | * | * |  | * | * | * | * | * |  |  |
| Methodology | BIRD will follow an innovative and harmonized strategy in implementing the project activities. Strategies and methodologies that will be followed for proper implementation the project are described in this section.  The project will be implemented under the close monitoring and supervision of the Executive Director of BIRD and the Pastor of Antiokhiya Baptist church.  The Scholarship will be given to the students those who are enrolled in different school if the existing schooling is not fit for them BIRD will operate special one.  To ensure the appropriate use of the stipend money monitoring will be continued.  In case of providing educational accessories the phenomena of Baptist church will come in consideration, the logo of WDRC will be printed.  In case of education, the Christian religious value will be pursue / followed. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Monitoring , Evaluation and Reporting | To implement the Project activities successfully, it is of course necessary to monitor and supervise the project very closely. Project will be monitored and supervised as per monitoring and supervision system of BIRD. The Executive Director will very closely monitor and supervise the activities.  BIRD will prepare and submit the following reports data and other documents 1. Monthly activity report by field office to head office 2. Annual report to Donor. During the project period, to proper implementation of the project, the above-mentioned progress reports will be produced.  After the completion of the project, an evaluation report will be prepared and the findings will be disseminated and included into the final report. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Budget | Budget Head |  |  | Unit Cost |  |  |  |  |  | Total Cost |  |  |  |  |  |  |  |
|  | Monthly stipend |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 25 student of class – I to IV |  |  | 25 student x $ 8 x 12 month |  |  |  |  |  | $ 2400 |  |  |  |  |  |  |  |
|  | Sub total stipend |  |  |  |  |  |  |  |  | $ 2400 |  |  |  |  |  |  |  |
|  | Dress |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Dress for 25 student |  |  | 25 set x $ 30 x 2 times |  |  |  |  |  | $ 1500 |  |  |  |  |  |  |  |
|  | Sub total dress |  |  |  |  |  |  |  |  | $ 1500 |  |  |  |  |  |  |  |
|  | Educational accessories |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Book for 25 student |  |  | 25 set x $ 30 |  |  |  |  |  | $ 750 |  |  |  |  |  |  |  |
|  | Bag for 25 student |  |  | 25 pcs. x $ 10 |  |  |  |  |  | $ 250 |  |  |  |  |  |  |  |
|  | Pencil , Note book for 18 student s |  |  | 25 set x $ 10 |  |  |  |  |  | $ 250 |  |  |  |  |  |  |  |
|  | Sub total educational accessories |  |  |  |  |  |  |  |  | $ 1250 |  |  |  |  |  |  |  |
|  | Nutritious food for 25 student |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 25 student x 12 months x 1 times snacks / day + 1 lunch /day |  |  | 12 months x $ 237.5 |  |  |  |  |  | $ 2850 |  |  |  |  |  |  |  |
|  | Sub nutritious food |  |  | - |  |  |  |  |  | $ 2850 |  |  |  |  |  |  |  |
|  | Total |  |  | - |  |  |  |  |  | $ 8000 |  |  |  |  |  |  |  |