## MANSA CHAPTER

## NETWORK OF ZAMBIAN PEOPLE LIVING WITH HIV/AIDS

## CARE FOR HIV EXPOSED INFANTS IN MANSA DISTRICT

## SCALE UP PROJECT PROPOSAL

## Submitted to: GlobalGiving2011 April Open Challenge

## Contact Person: Kennedy Chungu Palangwa

## District Coordinator

## Cell: +260977646126

## Email:nzpmansa@gmail.com or nzpmansa@yahoo.com

## Executive Summary:

| Name of Organization | Mansa Chapter Network of Zambian People Living with HIV/AIDS |
| --- | --- |
| Title of the Project | Enhanced Infant Diagnosis Care and Support Project (EIDCSP) |
| Contact Person | Kennedy Chungu Palangwa |
| Position Physical address Postal address | District Coordinator District Administration Block P.O. Box 710324 Mansa, Luapula |
| Project Location | Mansa District |
| Project Operation area | Chembe, Buntungwa, Central, Senama and Mansa General hospital |
| Project Duration | 12 months |
| Project total cost | US$ 133,508 ZMK 624,120,600 |
| Proposed Funder | GlobalGiving 2011 April Challenge |
| Partners | District Health Office Luapula foundation Group Focused Consultation |

Introduction:

Mansa Chapter Network of Zambian People Living with HIV/AIDS (Mansa NZP+) in a non-profit making organization which was formed in November 2003 Registration number ORS/102/46/300; currently the organization office is located at the District Administration Block behind the District Commissioners Office.

The Mansa NZP+ was formed to help improve the quality of life of people living with HIV by pursuing three issues and these are;

Communication, Support and Representation of People living with HIV in issues affecting them

VISION

We envisage an improved quality of life for people living with HIV and a well informed HIV and AIDS competent community, free of stigmatization and discrimination of people living with HIV/AIDS.

MISSION STATEMENT

To promote support to people living with HIV/AIDS, represents their interests and facilitates the flow of vital information.

MAIN OBJECTIVE

To promote the dignity, health and socio-economic situation for PLHIV, through presentation support and advocacy on issues affecting them

STRATEGIC OBJECTIVE

- Support: Promote and support the creation of support groups, which provide a safe and conducive social spaces to PLHIV enabling positive living

- Information education communication(IEC) / access to service: To optimize the quality and access to information and services  which are relevant to PLHIV

- Advocacy: To advocate for, there by contributing

-GIPA/MIPA: To encourage people living with HIV/AIDS to active participation and involvement in decision making process at local and international levels

-Livelihood to encourage people living with HIV/AIDS to respond to developmental opportunities, e.g. income generating and micro- enterprises

Project Purpose:

The Care for exposed infant in Mansa District will work to promote early HIV infant diagnosis, linkages to treatment, Care and support to exposed children and their families.

1. Increase knowledge and awareness at community and national level on linkages between HIV and MNCH.

2. Create strong civil society platforms that mobilize and shape national policies that support integrated HIV / MNCH / SRH services.

3. Implement national advocacy campaigns that address policy gaps, bring about new policies and action on commitments.

4. Improve referral systems and knowledge thereof that enable HIV positive pregnant women to access MNCH and SRH Services.

Program Outcome/Beneficiaries:  What are the major outcomes of this program?  Who will benefit?  How does this program contribute to meeting the donor’s goals or priority issues?

The project outcomes will include the following;

Outcomes

- Increased number of access to  HIV / MNCH / SRH  services and antiretroviral therapy

- Increased number of health care providers to provide  PMTCT HIV / MNCH / SRH services to mothers-baby pairs

- Increased number of children adhering to ART treatment

- Reduced long waiting hours by clients

- Increased knowledge levels for parents to care for there children

- Increased number of parents/guardians with knowledge about children’s care

Impact

- Prolonged lives of children living with HIV/AIDS

- Reduced mortality among children below the age of five years

- Reduced stigma levels in communities

- Improved quality of life for children and their families

- Improved adherence for adults and Children

Project primary beneficiaries are;

3,000 infants

3,000 mothers

Project Secondary beneficiaries;

Volunteers 50

Project Management Staff 10

6,000 community members in the project sites

Organization’s Competitive Advantage:  Why your organization, and why not some other organization?  What do you have to offer?  How will that benefit the donor?

The government of Zambia has developed and adopted a National HIV/AIDS/STIs/TB that provides a framework for addressing HIV/AIDS response. Accordingly, people living with HIV/AIDS PLHIV came together to form Network of Zambian People Living with HIV/AIDS in + which provides important contribution to the national discourse on HIV/AIDS/STIs/TB by actively being involved at community level , district and national levels in shaping the response to the HIV/AIDS epidemic. It accomplishes this by participating in the design, development and implementation of HIV/AIDS policies and programmes.

Mansa NZP+ since 2007 has been implementing Prevention of mother to child transmission programs in ten (10) rural health centers; by end of 2010 we had trained 50volunteers in pediatric support with support from UNICEF –Zambia and Firelight Foundation (California). Who work both at health facilities and in communities to provide education, Care and ongoing support to exposed children and their families.

The Statement of the Problem should describe:

Zambia is among the countries hardest-hit by the HIV/AIDS epidemic in Africa. It is estimated that 1.2 million of the total Zambian population of 10 million was infected with HIV by 2005. Although declining HIV trends have been observed in young people since 1998, HIV/AIDS in Zambia is still a major threat to the lives of adults of reproductive age and their children.While the national HIV prevalence has reduced by two percent from 16.3% to 14.3%, to the contrary Luapula Province HIV prevalence has increased (Zambia Demographic Health Survey (DHS) of 2002 to 2007) Luapula has recorded a two (2) percent increase in the HIV/AIDS prevalence rate. The report also shows that Mansa District leads the prevalence rate with 11.6 percent, seconded by the fishing districts of Nchelenge, and Samfya at 9.8 percent and 9.7 percent respectively.

Kawambwa, Mwense, and Milenge districts have the same prevalence rate of 8.2 percent.

Specific challenges and obstacles the project is expetcted to overcome.

  - Shortages of health care workers (HCWs) have been a bottleneck in the provision of HIV/AIDS services in Luapula province and Mansa in Particular. The World Health Organization/Ministry of Health establishment recommends a staff population ratio of 1:5000, 1:700, and 1:8000 for doctors, nurses and pharmacists, respectively. The existing human resource capacity in Zambia is far below the recommended cadre-to-population ratios, with existing levels of 1:17 589, 1: 8064 and 1:473 450 for doctors, nurses and pharmacists, respectively.  With the rapid expansion of access to antiretroviral therapy (ART), the increasing patient load will put a strain on the existing fragile human resource base. Universal access to ART treatment is inextricably linked to availability of and access to HIV counseling and testing (CT) services. However, the human resource shortage in Zambia, coupled with a national HIV prevalence rate of 14.3% has placing a heavy burden on the few health care workers available at health facilities to provide these services.  (Source: Task-shifting HIV counseling and testing services in Zambia: the role of lay Counselors 2007)

  - Issues of access also occur right at the clinics and hospitals; Due to limited number of trained medical personnel, many ART clinics and hospitals have significant queues and waiting times for tests and consultation. In particular, CD4 count and Dried Blood Sample results tests take much longer than what is acceptable making it difficult for initiation for treatment.  (Data from the 2008 Report on Access to medical Services by Network of Zambian People Living with HIV/AIDS)

  - Low access to treatment (ART, opportunistic infection); reviewed that many PLHIV miss clinical appointments due to investments in early infant diagnosis need to go beyond support for laboratory systems to community follow up. Mansa NZP+ has observed from that many of our members fail to make it the health centers

  - Limited resources to support staff and Volunteers

The Chapter also has problems to maintain the increasing number of volunteers which started with 10 members to 50. Currently we have received funding to support the staff and volunteers who still have the commitment to report and contribute their services in all the five ART facilities were we operate from.

In November 2007, Mansa NZP+ chapter with, financial support from UNICEF Zambia began training and placing community PMTCT volunteers as lay counselors in order to compliment  the efforts of the Health Care Workers  HCWs in providing HIV counseling and help reduce their burden, using the national HIV CT curricula.

This national training package includes a one-week classroom component followed by a four-week supervised practicum component. The intensive training is able to address individual learning needs related to education or experience level.

The one-week classroom component of the training includes instruction as well as role-plays and case studies to ensure that trainees understand the concepts and methods of HIV counseling and testing. In the four-week practicum, each trainee practices counseling and testing under the supervision of an experienced CT provider. This ensures that each trainee is able to practice and refine his or her counseling skills.

Lay counselors are selected from Support groups of people living with HIV/AIDS based on their ability to read and write in English, residing within the facility catchment area, and experience with the health facility for at least one year. These criteria were used for both urban and rural settings, but preference was given to those with some level of background training in HIV/AIDS.

A study carried out by ZPCT gives the firsthand experiences and lessons learned; According to health facility managers interviewed, lay counselors have contributed significantly to reducing the workload of HCWs, even having a “tremendous” or “overwhelming” impact.

“They have given us a relief, coverage of CT services has gone up and we have been able to reach our targets.”

All facility managers interviewed mentioned that the presence of lay counselors has resulted in more clients’ gaining access to CT services, while simultaneously decreasing the workload of health care workers. Lay counselors were always or usually available to provide CT services. up-take of CT services increased by about 27.3% and 101.3% in Luapula and Copper belt provinces, respectively, after the introduction of lay counselors.

Project Purpose: To improve the quality of care provided to HIV-exposed infants and their families through baby-mother tracking

Goal and Objective(s):

Project Goal: To contribute to the reduction of child mortality in Mansa District

Project Objectives:

- At the end of the 12 months project increase (PMTCT)/SRH/MNCH) children’s access to infant diagnosis by 5% from the baseline

- Increase knowledge in 5 communities about (PMTCT)/SRH/MNCH) pediatric health care for infants and children by the end of the 12 months project

Increase  (PMTCT)/SRH/MNCH pediatric health care skills for 50 health care workers by the end of the 12 months project

| Enhanced Infant Diagnosis Care and Support 2011 Implementation Plan |
| --- |
| Specific Objectives | Timeframe per Quarter | Responsibility |
|  | M | A | M | J | J | A | S | O | N | D | J | F |  |
| 1 | At the end of the 12 months project increase children’s access to infant diagnosis by 5% from the baseline |
| 2 | Increase knowledge in 5 communities about pediatric health care for infants and children by the end of the 12 months project |
| 3 | Increase pediatric health care skills for 50 health care workers by the end of the 12 months project |
|  | Objective 1. Activities |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Conduct a two day project kick off session |  |  |  |  |  |  |  |  |  |  |  |  | Capacity development Officer |
|  | Conduct baby mother tracking |  |  |  |  |  |  |  |  |  |  |  |  | Site Coordinators/ Counselors |
|  | Pay bimonthly missing lunch |  |  |  |  |  |  |  |  |  |  |  |  | Finance and Administration Officer |
|  | Objective 2. Activities |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Conduct 5 x one day Community sensitization |  |  |  |  |  |  |  |  |  |  |  |  | IEC Officer |
|  | Conduct health talks, drama performances, during antenatal clinics |  |  |  |  |  |  |  |  |  |  |  |  | Site Coordinators/ Counselors |
|  | Provide counseling & testing during antenatal clinics |  |  |  |  |  |  |  |  |  |  |  |  | Site Coordinators/ Counselors |
|  | Objective 3. Activities |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Printing and distribution of M & E tools |  |  |  |  |  |  |  |  |  |  |  |  | Monitoring and Evaluation Officer |
|  | Conduct 5 x 1 day orientation on monitoring tool |  |  |  |  |  |  |  |  |  |  |  |  | District coordinator |
|  | Collection of monthly reports |  |  |  |  |  |  |  |  |  |  |  |  | Monitoring and Evaluation Officer |
|  | Compiling and submitting of Quarterly reports |  |  |  |  |  |  |  |  |  |  |  |  | District Coordinator |

Work plan and Proposed Activities

Monitoring and Evaluation:

|  | Key activities | Target | Indicator | Frequency | Data source |
| --- | --- | --- | --- | --- | --- |
| 1 | Conduct a two day project kick off session | 1 | # of sessions conducted | Once | Attendance list |
| 2 | Conduct baby mother tracking | 6000 | # of baby mother pairs reached | Monthly | Registers |
| 3 | Pay bimonthly missing lunch | 6 months | # of counselors paid | Bimonthly | Pay sheets |
| 4 | Conduct 5 x one day Community sensitization | 1 | # of sessions conducted | Once | Attendance lists |
| 5 | Conduct health talks during antenatal clinics | 520 | # of Health talks held # of drama performances | Weekly | Registers Drama field reports |
| 6 | Provide counseling & testing during antenatal clinics | 6000 | # of counseling sessions held | Monthly | Registers |
| 7 | Printing and distribution of M & E tools | 2500 | # of M&E tools printed | Once | Distribution lists |
| 8 | Conduct 5 x 1 day orientation on monitoring tool | 1 | # of sessions conducted | Once | Attendance lists |
| 9 | Collection of monthly reports | 2500 | # of reports collected | Monthly | Reports |
| 10 | Compiling and submitting of Quarterly reports | 20 | # of reports compiled | Quarterly | Reports |

Program Management:

Mansa NZP+ has strived to network with collaborating partners in implementing its activities, with this project Mansa NZP+ will work in collaboration with five (5) rural health Centers and the surrounding communities, Zambia Prevention Care and treatment Project (ZPCT II), Luapula Foundation, Luapula Families in Distress. In managing this project, Mansa NZP+ will play the role as the lead organization and will be responsible for the overall coordination of the strategic design and implementation, monitoring and evaluation of the project.

The District Coordinator is designated to be the principal contact person through whom all information should flow. The coordinator will ensure that all activities are on course, within budget and carried out strategically.

Below is the table showing positions and responsibilities of program officers that will work to implement the program as they are already engaged in implementing other Mansa NZP+ activities:

|  | Position | Responsibilities |
| --- | --- | --- |
| 1 | District Coordinator | Contact person for the project Provide oversight on the project implementation Approve activities Writing reports |
| 2 | Capacity Development Officer | Organizing trainings Offer ongoing technical support to the project Writing reports and submit to the coordinator |
| 3 | Information and Education Communication Officer | Developing BCC messages Source and distribute IEC materials Offer technical support Writing reports |
| 4 | Livelihood Officer | Offer technical support Assist with trainings and to roll out activities |
| 5 | Finance Officer | Advise on issues of finance Develop financial reports Prepare payments Receiving project funds |
| 6 | M & E Officer | Offer technical support to the project Monitor and review project activities |
| 7 | Programs assistant officer | Assist in organizing trainings Perform assignments from other program officers Filing all project documents |

| Care for HIV Exposed Infants - Budget |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Programme Costs |  |  |  |  |  |  |  |
| Activity 1: Conduct a five (5) day Training for fifty (50) Counselors |  |  |  | US$1= ZMK4,700 |  |
| ITEM | QUANTITY | No OF DAYS | UNIT | UNIT PRICE | TOTAL | TOTAL |  |
|  |  |  |  | (ZMK) | (ZMK) | US$ |  |
| Venue Hire | 1 | 5 | days | 600,000 | 3,000,000 | 638 |  |
| Note pads | 50 |  | each | 25,000 | 1,250,000 | 266 |  |
| Bolstic | 4 |  | each | 30,000 | 120,000 | 26 |  |
| A4 Bond paper | 5 |  | each | 50,000 | 250,000 | 53 |  |
| Flip charts | 5 |  | each | 50,000 | 250,000 | 53 |  |
| Markers | 2 |  | set | 100,000 | 200,000 | 43 |  |
| Pens | 2 |  | box | 40,000 | 80,000 | 17 |  |
| Participant's accommodation | 50 | 6 | days | 250,000 | 75,000,000 | 15,957 |  |
| Participant's lunch | 53 | 5 | days | 65,000 | 17,225,000 | 3,665 |  |
| Participant's tea breaks | 53 | 10 | days | 50,000 | 26,500,000 | 5,638 |  |
| Participant's transport refunds | 50 | 2 | each | 50,000 | 5,000,000 | 1,064 |  |
| Participant's subsistence allowances | 50 | 2 | each | 150,000 | 15,000,000 | 3,191 |  |
| Facilitator's Direct service allowances | 3 | 5 | days | 300,000 | 4,500,000 | 957 |  |
| Total |  |  |  |  | 148,375,000 | 31,909 |  |
| Activity 2: Conducting Baby/Mother tracking |  |  |  |  |  |  |
| ITEM | QUANTITY | No OF DAYS | UNIT | UNIT PRICE | TOTAL | TOTAL |  |
|  |  |  |  | (ZMK) | (ZMK) | US$ |  |
| Lunch for counselors | 50 | 12 | months | 250,000 | 150,000,000 | 31,915 |  |
| Total |  |  |  |  | 150,000,000 | 31,915 |  |
| Monitoring and Evaluation |  |  |  |  |  |  |  |
| ITEM | QUANTITY | No OF DAYS | UNIT | UNIT PRICE | TOTAL | TOTAL |  |
|  |  |  |  | (ZMK) | (ZMK) | US$ |  |
| Data collection | 1 | 12 |  | 100,000 | 1,200,000 | 255 |  |
| Driver allowances | 1 | 12 |  | 100,000 | 1,200,000 | 255 |  |
| Fuel | 16 | 65 | liters | 8,590 | 8,933,600 | 1,901 |  |
| DSA | 16 | 32 |  | 300,000 | 153,600,000 | 32,681 |  |
| Total |  |  |  |  | 164,933,600 | 35,470 |  |
| Community Sensitization Through Drama Performances |  |  |  |  |  |  |
| ITEM | QUANTITY | No OF DAYS | UNIT | UNIT PRICE | TOTAL | TOTAL |  |
|  |  |  |  | (ZMK) | (ZMK) | US$ |  |
| Drama Performances | 10 | 3 | days | 800000 | 24,000,000 | 5,106 |  |
| Driver Allowances | 10 | 3 | days | 150000 | 4,500,000 | 957 |  |
| Staff DSA | 20 | 3 | days | 300000 | 18,000,000 | 3,830 |  |
| Total |  |  |  |  | 46,500,000 | 9,894 |  |
| Procurement of Equipment |  |  |  |  |  |  |  |
| ITEM | QUANTITY | No OF DAYS | UNIT | UNIT PRICE | TOTAL | TOTAL |  |
|  |  |  |  | (ZMK) | (ZMK) | US$ |  |
| Desk Top Computers | 1 | 1 | each | 9500000 | 9,500,000 | 2,021 |  |
| Printer | 1 | 1 | each | 7000000 | 7,000,000 | 1,489 |  |
| Printer Cartridge | 1 | 1 | each | 850000 | 850,000 | 181 |  |
| Total |  |  |  |  | 17,350,000 | 3,691 |  |
| Administration Costs |  |  |  |  |  |  |  |
| ITEM | QUANTITY | No OF DAYS | UNIT | UNIT PRICE | TOTAL | TOTAL |  |
|  |  |  |  | (ZMK) | (ZMK) | US$ |  |
| NZP+ Staff monthly allowances | 8 | 12 | monthly | 700,000 | 67,200,000 | 14,298 |  |
| Bank charges | 1 | 8 | months | 100,000 | 800,000 | 170 |  |
| Internet Bills | 1 | 12 | months | 800,000 | 9,600,000 | 2,043 |  |
| A4 Bond paper | 50 |  | each | 50,000 | 2,500,000 | 532 |  |
| Pens | 10 |  | set | 40,000 | 400,000 | 85 |  |
| Fuel | 12 | 150 | liter | 8,590 | 15,462,000 | 3,290 |  |
| Box files | 20 |  | each | 50,000 | 1,000,000 | 213 |  |
| Total |  |  |  |  | 96,962,000 | 20,630 |  |
| Grand Total |  |  |  |  | 624,120,600 | 133,508 |  |