ROZARIA MEMORIAL TRUST

DATE:                                                               22 November 2010

PROJECT TITLE:                                       ART Literacy & Care for HIV Positive

Children in Murewa, Zimbabwe

AMOUNT REQUESTED:                                  $10000

PROPOSED GRANT PERIOD:                         January 2011 - December 2011

CONTACT DETAILS:                                      PO Box 114, Murewa

Tel: +263278 22835

Cell: +2632775 336291

Email: rozaria@africaonline.co.zw

info@rozariatrust.org

Website: http://www.rozaria-trust.org

REGISTRATION STATUS:                            Registered Trust, No: 1050/2007

GEOGRAPHICAL COVERAGE:                   Murewa District, Zimbabwe

EXECUTIVE SUMMARY

Rozaria Memorial Trust has been carrying out a project entitled,  “ART Literacy & Care for HIV Positive Children in Murewa, Zimbabwe”. The project strengthened the work of Community Caregivers both at household and community level. The work of Community Care Givers has been centred on providing psycho-social support to both the infected and affected people.

Rozaria Memorial Trust has been working with volunteer Community Care Givers from 16 Support Groups of People Living with HIV and AIDS. The HIV and AIDS care and support programme is reaching out to about 5000 people in Ward 8 and 17 in Murewa District.

To accomplish project goals, Rozaria Memorial Trust scaled up networking among People Living with HIV through Support Groups and engagement of other relevant stakeholders in the circle of care, and support. These include village heads, educational institutions and affected households. RMT model acknowledges the paradigm shift in the Home Based Care programming with the increasing availability of Anti-Retroviral Therapy which has seen prolonging of life amongst PLHIV and a gradual reduction in bed ridden people. The range of services which have been provided includes psychosocial support, educational support and community capacity in various spheres of positive living especially on Anti-Retroviral Therapy Literacy. Also to meet the nutritional needs of PLHIV, Rozaria Memorial Trust is building developmental assistance nutritional project to strengthen care and support at household level.

The project supported and facilitated partnerships with local, national and international stakeholders. These partnerships have been important in stimulating community driven responses which recognises that local initiatives are part of a broader global initiatives. This has led to a wider referral network to serve the needs of People Living with HIV. Another element is the referral aspect of the work, in which RMT refers specific cases or situations to other organisations. This is recognition of the limitations of the organisation and the appreciation of the existing services, and organisations in providing holistic care and support for people living with HIV.

To reach a wider network of partners and other people, RMT has been using the online communication systems. The organisation has a running website http://www.rozaria-trust.org,

and also actively uses the facebook and twitter in sharing, and disseminating information. A monthly Community Voices has been established in the past year and it has been shared through the online channels of communication.

This project builds on an on-going partnership with AVERT, AJWS and SAFAIDS.

BUILDING ON LESSONS LEARNT:-

- The project now seeks to place special focus on children and young people living with HIV within its established Support Groups and beyond. Through the community outreach and awareness initiatives, RMT has come in contact with increasing number of positive children ranging from infants to 17 years. Most of these children are in schools and the majority of them are being taken care of by a grandparent or a relative.

Rozaria Memorial Trust would like to have a focused approach on these children and young people to enable the provision of adequate care and support both at household, school and community level. Also they are very few organisations with integrated programmes for this category in Murewa District. The Ministry of Health’s approach is more on treatment, but these children do face many barriers that include adherence, stigma and discrimination.

- RMT also plans to build the good practise on Children Anti Retroviral Therapy Literacy into the care and support programme in schools. RMT will work with 5 primary schools and 2 secondary schools which fall under its project catchment area.

- The other shift of the project activities is the integration of a developmental assistance nutritional project targeting production of maize (corn) which is the staple food in Zimbabwe. This will strengthen food security level thereby bringing about comprehensive care and support for PLHIV which increase adherence and consequently prolonging life of the infected people.

PROJECT DESCRIPTION

Rozaria Memorial Trust project is going to focus more on children and young people living with HIV. HIV epidemic has affected many families; with this challenge it means parents and caregivers need to be capacitated to develop the right skills needed to care for the child especially in the work of Anti-Retroviral Therapy.

Psychosocial support counselling sessions are going to be done targeting both the guardians and the affected children at household, and community level. This helps a long way in improving the care that is given to the children and promote a healthy development and a full, active life for the children. Currently, Rozaria Memorial Trust is working directly with more than 60 HIV positive and more are to be identified in the life of the project; a total target number at the end of the project is 100 HIV positive children from Ward 8 and 17 in Murewa.

To provide a comprehensive care and support for the HIV positive children, Rozaria Memorial Trust will continue to work closely with the educational institutions where the children spent most of their time at. The project is targeting 5 primary schools and two secondary schools that fall under the catchment area of Rozaria Memorial Trust operations. This is going to be done through poetry and quiz forums amongst children and capacity building workshops for teachers on Paedriatic care and support. This is meant to provide a supportive environment through educational awareness on HIV to reduce stigma and discrimination; and facilitates for adherence to medication during school time.

Recognising the shift in the needs of people living with HIV in the community because of Anti-Retroviral Therapy, care and support for adults is to be centred on psycho-social support and nutritional education mainly through the community caregivers. Trained community care givers will be utilised to provide direct physical and psycho-social support activities that capacitate households to respond positively to the requirements and expectations and needs of PLHIV in the family.

The project is also going to consolidate the developmental assistance project in nutrition which is already underway for people living with HIV and AIDS reaching out directly to 260 people. This is meant for self reliance which improves the nutrition at household level and consequently adherence to medication.

PROJECT OBJECTIVES

- Improve accessibility and meaningful involvement to education for Children living with HIV in schools through care and support initiatives.

- Increase access to Anti Retroviral Therapy literacy and paediatric care around children and their circle of care.

- Enhance positive living in PLHIV through psychosocial and nutritional support

KEY PROJECT ACTIVITIES

- Carrying out in-school activities on Paedriatic care giving through capacity building of teachers, and quiz and poetry forums amongst students.

- Community meetings on counselling services for children and care givers.

- Community care and support to PLHIV through psycho-social services and nutritional support.

WORK PLAN

| Objectives | Activities | Input | Time Line |
| --- | --- | --- | --- |
| 1. Improve accessibility and meaningful involvement to education for Children living with HIV in schools through care and support initiatives. | 2 x 1 day Capacity Building of teachers on Paedriatic ART |  | March and July 2011 |
|  | 1 Quiz and 1 Poetry Forum on HIV | -Transport for participants -Food -Prices -Public Address System | June and September 2011 |
|  | School fees assistance for 50 HIV positive children | -school fees subsidies | January to September 2011 |
| 2. Increase access to Anti- Retroviral Therapy literacy and paediatric care around children and their circle of care. | 5 Community meetings for counselling services of children and care givers | -Transport -Food -Facilitators Fee | January –October 2011 |
|  | 2 Educational outreaches for HIV positive children | -Transport -Food -Booking fees | April and August 2011 |
| 3.Enhance positive living in PLHIV through psychosocial and nutritional support | Community Support Visits by Community Based Volunteers | -Field Allowances | January-November 2011 |
|  | Food production and management meetings | -Transport -Food | March and May |
|  | Procurement of food production inputs for PLHIV | -fertilisers | December 2010-January 2011 |

MONITORING AND EVALUATION

Monitoring and Evaluation of the project is going to be based upon the Logical Framework Analysis. The LFA is made of the following:-

- Set objectives and activities

- Project Indicators

- Methods and tools of collecting information on the indicators

- Assumption

Logical Framework Analysis

| Narrative Summary | Verifiable Indicators | Means of Verification | Assumption |
| --- | --- | --- | --- |
| Objectives 1. Improve accessibility and meaningful involvement to education for Children living with HIV in schools through care and support initiatives. | -Number of teachers capacitated on Paediatric care and support -Number of students reached by anti-stigma and anti-discrimination messages | -Participants registers -Office reports -School reports | -Schools support and programme ownership -Stable political and economic environment |
| 2. Increase access to Anti Retroviral Therapy literacy and paediatric care around children and their circle of care. | -Number of care givers and children participating in community meetings. -reduction in cases of stigma and discrimination | -meeting reports -participants registers | -Community support and participation -stable political environment -availability of adequate financial resources |
| 3.Enhance positive living in PLHIV through psychosocial and nutritional support | -Number of PLHIV and households reached -Increase in HIV disclosure amongst PLHIV -Reduction in incidence of malnutrition in PLHIV | -field reports -meeting reports | -Community support and programme ownership |
| Activities 1. Carrying out in-school activities on Paedriatic care giving through capacity building of teachers, and quiz and poetry forums amongst students. | -Number of capacity building workshops conducted -Number of students directly participating in the quiz and poetry forums | -participants registers -Office reports | -stable schools calendar -100% support from schools |
| 2. Community meetings on counselling services for children and care givers. | -Number of meetings held -Number of children and care givers reached | -meeting reports -participants registers | -Community support and participation -stable political and economic environment |
| 3.Support to PLHIV through psycho-social services and nutritional support | -Number of people receiving nutritional support |  | -positive commitment of support group members -normal rainfall pattern |

PROPOSED BUDGET

| Budget Item | Unit Cost |  | Quantity |  | Total Cost |  |
| --- | --- | --- | --- | --- | --- | --- |
| In-School Activities on Paedriatic care and support |  |  |  |  |  |  |
| Teachers capacity building on Paedriatic ART | 1500/session |  | 2 |  | 3000 |  |
| Transport assistance Assistance to HIV positive kids | 15/child |  | 200 |  | 3000 |  |
| Subtotal |  |  |  |  | 6000 |  |
| Supporting of children through psycho-social services and skills building |  |  |  |  |  |  |
| Meetings on counselling services for children and primary care givers |  | 200/session | 5 |  | 1000 |  |
| Educational Outreaches for HIV positive children |  | 500/outreach | 2 |  | 1000 |  |
| Subtotal |  |  |  | 2000 |  |  |
| Care and Support for People Living with HIV |  |  |  |  |  |  |
| Community visits by Community Based Volunteers |  |  |  |  |  | 1000 |
| Running Costs |  |  |  |  |  |  |
| Rentals and staff |  |  |  |  | 1000 |  |
| Total 10,000 |  |  |  |  |  |  |

END//