| -Activates List the 7 main activities of the project, break down into sub-groups | Action or deliverable | Main person /Organization | Anticipated start Date | Date to be completed |
| --- | --- | --- | --- | --- |
| 1. Commissioning an Estate Surveyor to secure accommodation /site for the project. Recruitment of project Manager. | Secured accommodation project manager in place | FOTD/BDU Chief B.A.J Orduh | From date money is made available | 3 Months |
| 2. Interior Decoration, supply of work desk, and fixing of burglarproofs | Supply and deliver of office furniture | Coordinated by Chief B.A.J Orduh | 4th month of project | 30 days |
| 3. Application and installation of Telephone and Fax Lines | Nigeria Telecommunication | Consultant Concurrent with Supply of Furniture | Minimum – 60 days | 60 days |
| 4. Procurement of operational equipment. And components | Installation of Internet Connectivity | To be supervised by ISP/ Chief Orduh | 7th month of project | 4 weeks |
| 5. Recruitment and interview of Support Staff | Staff recruited (Disabled) | Implantation by Trustees | 8 Month | 30 days |
| 6. Putting in place other contingencies. | To be sure that nothing is left to change | Chief Orduh | 9 Month | 90 days to measure the success of the project |
| 7. Commissioning. Pre opening press conference. To sensitize the Nigerian people | The Executive Director. /Nigerian population about the need and the merit Trustees and Board member of the project and its Funders | 10-12th months members |  | Project Completion |

Project Implementation