Civil Society Organization’s Network for Sustainable Agriculture and Environment in East Africa (CISONET)

BUSINESS PLAN FOR

Enhancing the Capacity of Rural Poor Women Farmers in production and Marketing of Charcoal Briquettes in Uganda

Country; Uganda

Location; Mpigi District

Contact Person:

Mr. Bukenya Isah

Executive Director

Civil Society Organization’s Network for Sustainable Agriculture & Environment in East Africa (CISONET)

Plot 27, Nakasero Road

P O Box 29578 Kampala, Uganda

Tel. 256 234550, 256-772-585605, 256-782-605939

Fax: +256-41-230748

E-mail:  info@cisonet.org

Funds requested:                      Ug shs 72,000,000 = $30,000

Project duration:                        1 year From June 2012 to July 2013

March 2012

1.0 Background History

Civil Society Organizations’ Network for sustainable agriculture and Environment in East Africa (CISONET) is a registered non-government organization which was formed to eradicate poverty, hunger and climate change catastrophes through social and economic empowerment of the Community Based Civil Society organizations fisheries groups and cooperatives by way of empowering them to strengthening their capacity in Sustainable Agriculture and Environment in East African Region.

The organization was established on 5th January 2007 by Ugandans of diverse professional backgrounds in agriculture, environment and social workers among others. This came after the realization of continuous poor methods of farming and poor agricultural practices that has resulted into hunger, poverty, malnutrition and climate change catastrophes faced by the global world, Therefore in order to find solutions to these challenges, the founders of CISONET deemed it necessary to have a coordinating Body for Community Based Civil Society organizations with an ultimate aim of addressing these challenges so as to improve on the Socio-economic wellbeing of the local communities through sustainable agriculture and proper management of natural resources.

The CISONET Vision is;

To become a sustainable model of excellence that contributes to the development of efficient and effective Community Based Civil Society organizations (CBCSOs), fisheries groups and cooperative farmers that create a community free of hunger and poverty.

The CISONET Mission;

To unite, empower and strengthen the capacity of the community based Civil Society organizations (CBCSOs), fisheries groups and Cooperative farmers, through linking them with appropriate support from global partnerships and advocate for formulation of favorable policies to promote effective and efficient sustainable development in Agriculture and Environment.

## 2.0 Introduction to the Business Plan

CISONET Project Business Plan is intended to present a mechanism for which rural poor women farmers can improve their livelihoods and household incomes through production and marketing of charcoal briquettes reliable. This project seeks to empower 1000 poor women smallholder farmers with skills in producing & utilizing the most effective fuel source from agricultural waste materials ‘Charcoal Briquettes’. This technology has been proven to be a substitute for wood fuel and a good source of income for women. It was introduced because of Climate change effects as a result of deforestation which accounts for 20%. CISONET will act as the mediator in building the capacity of the rural women and linking them to the markets.

Expected short and long-term Results

Short term results

- The knowledge & skills acquired will be used for manufacturing of the briquettes

- There will be increased household incomes from 1USD to $3 per week through selling of the briquettes

- Sharing of knowledge and experiences among the group members

- Empowered women will be able to influence formation of other women groups.

Long term results

- There will be reduced rate of deforestation as a result of mitigation of climate change effects

- There will be empowered women groups for meaningful and active participation in all other opportunities

- Empowered women groups will be able to easily access other resources like group loans & grants

- Empowered women groups will be able to participate in other activities which will led to their sustainability these may include; village savings (VSLA), Poultry keeping, & Art and crafts

3.0 Activity Work plan from June 2012 to July 2012

| Activities/output | PERIOD; January to December 2012 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Holding project awareness and planning meetings for community beneficiaries & stakeholder | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May l | Jun |
| Conducting training workshops in charcoal Briquettes production and marketing for women |  |  |  |  |  |  |  |  |  |  |  |  |
| Procurement of equipments for 30 women groups |  |  |  |  |  |  |  |  |  |  |  |  |
| Conduct monitoring and evaluation of the project |  |  |  |  |  |  |  |  |  |  |  |  |

CISONET Budget for Enhancing the Capacity of Rural Poor Women in Charcoal Briquette Production and Marketing

| No | Activity | Unit Cost | Amount |
| --- | --- | --- | --- |
| 1. | Holding project awareness and planning meetings for community beneficiaries & stakeholder | Fuel for Mobilisation and awareness about the project 50,000 x 30 Facilitators perdiem 100,000x 3 x 15 days | 1,500,000 4,500,000 |
|  | Sub-total |  | 6,000,000 |
| 2. | Conducting training workshops in charcoal Briquettes production and marketing for women | Refreshments 5,000x30peoplex 30groups Transport refund 10,000x 30 p’plex 30groups Facilitators perdiem 100,000x 3 x 30groups Fuel for travel & vehicle 100,000x 30groups Stationery assorted | 4,500,000 9,000,000 9,000,000 3,000,000 1,000,000 |
|  | Subtotal |  | 26,000,000 |
| 3. | Procurement of equipments for 30 women groups | Kiln 500,000x30 groups Extruders 500,000x30 groups Drums 100,000 x30 Polythene material 50,000 x 30 Gloves 5,000 x 30people x 30 groups Stools 50,000 x30 groups | 15,000,000 15,000,000 3,000,000 1,500,000 4,500,000 1,500,000 |
|  | Subtotal |  | 40,000,000 |
| 4. | Conduct monitoring and evaluation of the project |  | CISONET Contribution |
|  | Sub-total |  | 6,000,000 |
|  | Grand total | In Uganda Shillings | 72,000,000 |
|  | Grand total | In USD | 30,000 |

Comparative advantage

|  | Charcoal Briquettes | Charcoal /wood fuel | Hydro-electric power |
| --- | --- | --- | --- |
| Strengths | ●Affordable ●Easily accessible ●Clean fuel ●Easy & cheap to produce ● Easy to market | Already available Market | It is easily accessible It is clean |
| Weaknesses | ●Collection of agricultural waste ● Equipments are a bit expensive for rural poor women | ●It produces soot ● it is expensive | It is expensive |
| Opportunities | ● The raw materials are free & locally available ● already available market | N/A |  |
| Threats | Lack of equipments for charcoal Briquette production | Its continuous usage leads to climate change effects | It is very dangerous |

Financial plan

Capital expenditures Budget

| Particulars | Quantity | Unit cost | Amount | Time lag |
| --- | --- | --- | --- | --- |
| Holding project awareness and planning meetings for community beneficiaries & stakeholder | 30 | 200,000 | 6,000,000 | 1year |
| Conducting training workshops in charcoal Briquettes production and marketing | 30 | 866,667 | 26,000,000 | 1 year |
| Procurement of equipments for 30 women groups | 30 | 1,333,333 | 40,000,000 | 1 year |
| Conduct monitoring and evaluation of the project |  |  |  |  |
| Total |  |  | 72,000,000 | 1 year |

Financial plan

Capital expenditures budget

Business information:

Our business requires a loan of 72,000,000 for start up capital. We would like to use this money to train women in charcoal briquette production and marketing and also procurement of equipments to be used so that the women groups can produce charcoal briquettes them selves and sale them to increase their house hold incomes.

| Monthly charcoal production per group per month | Total group income projections per month | Total group annual income projections |
| --- | --- | --- |
| 400kgs of Charcoal briquettes per month x 1,500= @ = 600,000= $250 | 600,000 income per group per month x 30groups = 18,000,000 $7,500 | 18,000,000 x 12 months = UG Shs 216,000,000 $90,000 |
| Monthly income per person 600,000÷ 30people = 20,000> $8 per month |  | Total annual income projections Per person 216,000,000÷ 900 people = 240,000 > $100 |