Learnings in the second phase of chullah construction show encouraging results. A report on chullahs till end 25 Jan 2015:

|  |  |  |  |
| --- | --- | --- | --- |
| **Points** | **Khansyu Area** | **Karayal Area** | **Total** |
| No. of total constructed chullahs till Jan 15 | **81** | **104** | **185** |
| No. of not in use till Jan 15 | 1 | 0 | 01 |
| No. of chullahs broken till Jan 15 | 4 | 1 | 05 |
|  No. of villages covered | 11 | 10 | 21 |
| No. of challah planned for construction in Feb 15 | 15 (VinodKumar) | 30 (NareshBahuguna andGirishBahuguna) | 45 |