Second Quarter 2007 Progress Report By Albina Ruiz - Executive Director of Ciudad Saludable Two new micro-enterprises are created during the second quarter 2007, and the first one adds seven new employees, up from 12 to 19 rural recyclers. This means that there are three micro-enterprises with a combined 45 urban recyclers. These thee micro-enterprises operate under the business names of: SEMRES-Pucallpa SAC, MIRES-Pucallpa SAC and UTL-Pucallpa SAC, which provide solid waste collection services to 66 shantytowns, covering 85 % of the total shantytowns located in Pucallpa. In terms of families served, this represents a total of 8,390 families or 45,000 inhabitants approximately.

Training Plan for school teachers:

Ciudad Saludable presented the Modular Training Plan “Handling and Management of Solid Waste in Schools" to 70 directors of 45 institutions. 

150 teachers participated in the first module “Regulations and Environmental Health" in school premises where staff from the health ministry and non-government organizations developed workshops related to environmental health in the school system

Recycling of solid waste at the school level:

This program was presented to 80 directors of 45 schools which have been executing the "clean, safe, and healthy school" program promoted by the Department of Education.

Ciudad Saludable established 14 School Environmental Committees made of 88 members from the educational sector. During the first training session, an annual action plan was prepared that covered trainings, evaluation sessions, and community activities, etc.

1,832 students were trained through seven theoretical/practical workshops in areas such as "the three Rs--Reduce, Reuse, and Recycle", segregation at source of generation level, five sessions that involved games, and two plays (theatre) teaching students about segregation of waste on the school premises.

At the community level, 8,000 triptychs with important information about segregation of solid waste at the household level were distributed among the 66 shantytowns with the participation of the 45 rural recyclers that make up the three micro-enterprises.

Volunteers:

Students from the university "Alas Peruanas" who are volunteers of Ciudad Saludable received training received in two areas: integrated solid waste management at the household level and segregation of solid waste.

Other events:

Throughout the month of June, the roundtable “perspectives and opportunities of solid waste management in Pucallpa” took place with the participation of 60 university students and municipal officials.

Also, the first environmental fair celebrating the “World Day of the Environment” took place in Pucallpa downtown with the participation of the general public, students, teachers, among others. Ciudad Saludable presented projects that were implemented in other regions of Peru. The event closed with a street parade where 25 private and public institutions participated. Approximately, 5,000 people attended this event.

First Quarter 2007 Progress Report By Albina Ruiz - Executive Director of Ciudad Salduable The first micro enterprise is up and running! . It is called “Servicios Múltiples de Residuos Sólidos de Pucallpa SEMRES-PUCALLPA SAC.” or Multiple Services of Solid Residues for Pucallpa SAC and is made of twelve trained and well-equipped rural recyclers. This micro-enterprise provides solid waste collection services for six shantytowns in the South of Pucallpa making a direct impact on more than 2,700 families or approximately 14,643 inhabitants.

Training plan for school teachers:
There were working sessions that brought 31 strategic partners to develop the training plan for school teachers. The strategic partners represented different groups such as municipal officers, regional health ministry representatives, regional environmental department officers, and regional educational department representatives, among others. All of these partners contributed to the development of the training plan made of three modules.

At the community level, Ciudad Saludable reached 270 members from 13 grassroots organizations in Pucallpa to prepare education materials. These materials displayed information about recycling practices of solid waste at the household level.

