[image: image1.png]x globalgiving






PROJECT Report

Project Title (50) Ensure food security for 300 families in Bangladesh

The IDEX-SATU Partnership:

International Development Exchange (IDEX) is a San Francisco-based social change organization whose mission is to promote economic empowerment and social change in Africa, Asia and Latin America. In Bangladesh, one of IDEX’s local partners is the Social Advancement through Unity (SATU). SATU is a grassroots organization that empowers individuals and communities so that they can become successful agents of change and development on their own behalf.  SATU promotes the socio-economic status of distressed and powerless women through institution building, education, economic development activities, and food security initiatives. SATU's programs reach over 24,000 women in 283 villages across 5 districts of Bangladesh.

Summary of Project Progress to Date

The activities are taking place as per plan. SATU continues its savings and credit program with 1,040 women in the Kalihati area. It provided micro-credit to 100 women to increase their income, trained 300 women in diversified crop and vegetable cultivation utilizing ecologically sound and sustainable agricultural practices and met the health needs of 90 vulnerable infants and pregnant women.

The area and issues

IDEX submitted a proposal to Global Giving on behalf of SATU to develop long-term sustainable methods for improving the status of women from the acutely poor, small, and marginalized farm households of Kalahati Upazila
 in Tangail, Bangladesh. Kalihati lacks any kind of communication infrastructure or public facilities. The area’s health complex is far from the interior villages, understaffed and ill-equipped. People do not receive adequate medical treatment, and the area is beset by high child mortality and morbidity rates. The literacy rate (for those 7 years and over) in the project area is 35.2% for men and 19.3% for women.  

SATU found that the low standard of living in these communities was characterized by large disparities of income, indebtedness, poor housing facilities, a lack of health care or education. 75% of the women did not have enough income to meet the prescribed food intake and 78% of the farmers had limited knowledge about food processing and storage. Children from these families were underweight, often due to the mothers’ poor health resulting from the lack of pre-and post-natal care. 

Activities carried out

Group formation

SATU formed 46 women’s groups in 20 villages, with a total of 1,040 members. The members were selected from extremely poor, small, and marginal households. SATU made regular visit to the groups and members to discuss the changes that were taking place. They found that in many instance the groups were convening their own meetings, discussing and taking action on issues affecting the members, and participating actively in the credit program. Some group leaders were taking an active part in the local government activities.  
Training on capacity-building

Training and awareness building are key components of SATU’s projects. The training programs were organized to build on the skills of women and farmers and served 300 women. SATU provided training on vegetable cultivation, crop diversification, land use, integrated pest management
, food preservation, and fish cultivation. After receiving training, the participants reflected on what they had learned at the group meetings.

Income generating activities

90 women were provided credit to carry out income generation activities and help them take steps out of poverty. The activities included food processing and vegetable garden, small trade, and poultry rearing. The credit amount ranged from $50 to $100. The credit was available through grants made this year and from the revolving fund (principal and interest repaid from earlier loans). The repayment rate is around 98%. 

Women in small trade small trade, bakery, and grocery are making profits of 50% from their small business. Tangail is a commercial town with high traffic flow, women can sell their wares quickly and on a regular basis.

Mother and child health

To date SATU’s has monitored the health status of 150 pregnant women and 150 infants. A trained nurse conducts regular health counseling and treats minor ailments. The nurse and group leaders ensure that the women and infant maintain healthy diets and adhere to their immunization schedules. The crux of this program is to educate women about food quality and balanced diet preparation.  

In an informal survey, SATU found that, “Awareness about health has increased among the group members and there is less blind observance to religious beliefs and superstitious practices. The door step medical facilities and health check-up of pregnant women is helping to ensure safe motherhood and in reducing incidence of child mortality.”

The group members put into practice what they learn in the meetings. For example pregnant women are more conscious about their diet and try to include meat, milk, and vegetables. They also make sure that they get sufficient rest after completing their daily household work. 

The women are careful in preparing meals. They wash the vegetables thoroughly before cutting and cooking. They do not cook vegetables for a long time so as to not lose the protein content. After cooking they preserve the food in a safe place and cover it to protect it from flies & other insects.   

� Tiers of administration. The country is divided into districts, upazilas and unions.


2 Integrated pest management (IPM) is a farming method that is environmentally responsible and economically viable.  IPM  focuses on minimizing pesticide use, enhancing environmental consciousness and promoting sustainable agricultural systems.





