Learning to Read in South Africa

(Empowering Older People through Literacy In South Africa)

# Background

Muthande Society for the Aged (MUSA) implemented a pilot literacy project which ended in 2001 with the help of HelpAge International. It was the first project of its kind in South Africa, using a unique approach: training older people as facilitators who then assisted older learners to develop literacy (both English and Zulu) and numeracy skills. This project will expand and develop the lessons learnt from the pilot, helping create awareness of older people’s literacy needs and how such skills can change their lives.

# The Problem

Despite South Africa’s relatively high GDP compared to its neighbours, it is still a very poor country, ranked as 107 by UNDP in their 2002 Human Development Index.  Poverty and inequality remains a fact of life for the majority of people, with almost every social and economic indicator highlighting truly vast differences between racial groups.  Based on the 1996 census, it is estimated that 52% of people in RSA are living below the poverty line, and while estimates may vary at least 25% of the population, or well over 10 million people, can be categorised as ‘ultra’ poor (means that they are living on less than one US$ a day).  Poverty assessments consistently find much higher rates of poverty among black people (68%) than white people (8%).  In terms of poverty, the black population of South Africa ranks alongside Mozambique (70%) - one of the world’s poorest countries.

There have been attempts to address issues related to literacy, but despite these, low levels of basic literacy remains a serious problem in South Africa.  Alarmingly, there are currently 2 million people who are illiterate in Kwa–Zulu Natal and 12 million nationally.  The business sector is a major provider of adult basic education, but such programmes tend to be designed to enhance the workforce based on the needs of the company and not the individual. Many such programmes target the younger groups and in some cases consider educating older people, as a waste of their resources.

# Situation of older people

Sadly, poverty is a fact of life for the majority of South Africans.  After a lifetime of poverty, people enter old age with very few resources and the opportunities that exist for other adults to participate in poverty reduction programmes are denied older people simply on the basis of age.  Breakdown in traditional family structures reduces the support given to older people and exacerbates the poverty in which older people live.

There are virtually no opportunities for older people to participate in education programmes and or decision making processes.  Older people, in particular, are seldom given the opportunity to learn. It is through literacy programmes such as these, that older people can develop the skills required to read important documents which may include medicine labels, write their names, learn of their rights, to speak up for themselves and challenge the issues affecting them.

Project Aim

The aim of the project is to improve the quality of life of older people through the provision of appropriate literacy skills.  Facilitators will teach functional literacy and numeracy skills to groups of older learners in four townships around Durban. The project also will also work with Adult Basic Education institutions and other organisations to promote the importance of supporting older people’s literacy.

Project Description

In partnership with MUSA, this project seeks to improve the quality of life of older people, through enhancing their literacy skills. Older people will have the opportunity to attend literacy classes, and those with little or no literacy skills will be targeted. Classes will be run by older people, most of whom are former teachers or educators.  . This project will also raise awareness of the needs of older people and demonstrate that they can and do want to learn. Moreover, with increased literacy skills, older people will be able to contribute fully in family life and within their own communities – becoming involved in community affairs or assisting grandchildren with their homework.

Sustainability

A modest fee will be charged to those attending classes and receiving learning materials, ensuring that some income is generated to help support the project. Older people will continue to use the skills they learn after completing the training.  In a much broader context, such learning will positively impact on the lives of older people by increasing confidence, independence and respect.

# Projected Outcomes

- Increased literacy skills of 100 older people through attending literacy classes

- 4 older people trained as facilitators to support older learners

- Awareness of the needs of older people and how to address them will be highlighted

How older people will benefit

“Come and experience for yourself that life is not the same once you can read and write. You’ll never know the joy of being able to board a bus on your own simply because you are able to read the destination on the front window by yourself. I am very happy because when I now attend meetings, I am able to understand the minutes of meetings and can also contribute. You’re never too old to learn. For me it was like stepping out of the darkness into the light.” - Mrs Mchunu, an 82-year-old, of the pilot literacy project in South Africa.

The programme will benefit older people in many ways.  It will give them skills that will assist them in their daily lives and will help build their confidence.  Examples from previous experience give an indication of how the programme is likely to change the lives of older learners:

- Older people will be able to count their pension money and also count the change after making purchases, this will help them avoid being cheated.

- Many older people in the townships are caring for orphans or are living in households with grandchildren.  Their literacy skills will help them to help the children in their care with homework.  It has also been found that as older people learn to read, the benefit from increased respect from the children in the house.

- The skills acquired will help the older people in their daily lives in church and community meetings, when doing shopping, at health clinics, when sewing and cooking and also in doing crafts.

- Older people will be more able to access their rights.  Some of the older people who have been involved in the programme now write letters to their councillors and community leaders voicing their concerns.  They have also contacted the Health Authorities and hospital personnel expressing their concern about treatment that they receive.

Project Budget

| Activity | Cost ($) |
| --- | --- |
| Project Staff (contribution to salaries of a supervisor, finance officer and driver) | 2,270 |
| 4 Facilitators | 4,178 |
| Literacy classes (venue and materials) | 1,020 |
| In-house training of facilitators | 135 |
| Awareness Raising | 195 |
| Running Costs | 1,095 |
| Monitoring and Evaluation | 195 |
| Admin at 10% for Global Giving | 908 |
| Total Project Cost | 9,995 |

Muthande Society for the Aged (MUSA)

Muthande Society for the Aged (MUSA) was formed by a group of community health nurses, social workers, health educators and community leaders in consultation with older people in 1982.  In the course of their work, they realized that the older people face many challenges. MUSA operates in South Africa’s Durban Metropolitan, South Central and Inner West Councils and serves three townships Lamontville, Chesterville and Clermont.  MUSA works with over 2,000 older people. Muthande, which means ‘Love the aged’, obtained a fundraising number in 1982 and was registered as a Black Welfare Organisation. Muthande’s mission statement is to improve the quality of life for older people and keep them at home where they prefer to be for as long as possible and only consider institutionalisation when it is no longer possible to do so.

# Organisational Structure

An Executive Committee of 12 members elected during the Annual General Meeting (AGM) runs MUSA. The Committee in turn elects subcommittees to attend to special tasks and also co-opts other persons where special knowledge and experience is needed. During the AGM, the committee reports on the year’s activities and new committee members are elected.  The auditors’ report is read and an auditor is appointed for the coming year.

# Programmes and activities

In order to meet the social, physical, economic and emotional needs of older people, MUSA runs the following services:

# Service Centres

These provide a support structure and prevent social isolation of older people.  They are run in the three townships.  Members meet Monday to Friday and engage in different activities. When necessary, experts are invited to give talks on issues affecting older people’s lives. This creates an opportunity for social interaction with people from outside, making them feel recognised. Older people also receive new skills, which they use in their homes, making them feel worthwhile. They also benefit from trips to various places of interest to improve their quality of life. MUSA provides well-balanced meals at the centres and at pension pay points to who live far from the service centres, satellite and luncheon clubs have been initiated.

# Home Based Health Care

This programme was established in 1987 in order to provide older people with support in the community.  Because some older people are physically frail, they are often considered a burden and are neglected and abused by family members leading to dependency and indignity.  The organisation has 15 caregivers deployed in the three townships.  The duties of these caregivers include home visits, bathing the older people, hygiene, collecting medication and taking the frail to the hospital.  They also cook and link them with religious ministers, pension officers and health authorities.

# Capacity Building

Capacity building was started in 1992 and forms an integral part of the home based health care project, which was initiated to empower family members. These family members were lay careers of the bed ridden, housebound and blind older people.  The programme has gained importance because of the HIV/AIDS epidemic which has meant that older people, especially women, have become carers of their sick children and grandchildren.  However, most of them do not know how to protect themselves from contracting HIV/AIDS.

# Transportation to Clinics

The organisation started this service in 1986 to ensure that the blind, be/house bound older people get their medication.  Through consultation with government clinics in the three townships, it was arranged that geriatric clinics be held on certain days of the week so that older people could get easy access.  MUSA also provides tea and sandwiches as people wait for treatment.

# Literacy Programme

The programme was born out of the need of older people who felt that democracy goes with being able to read, write and sign documents. In 1996, MUSA and HelpAge International together with University of Natal’s Department of Adult and Communication Education collaborated in the training of facilitators, design of materials and in-service training programmes.  Through the programme, older people have been able to develop new skills, which they have used in self-help projects and to contribute to their own and other people’s well being.  This has, in turn, made them independent and restored their pride and confidence.  The project has 4 learning centres, 1 coordinators and 7 literacy facilitators.

# Involvement of Older People

The members of the organisation are involved in all the activities as much as possible.  Older people are involved in the Executive Committee, volunteering, sports and cultural activities, visiting the sick, managing the ‘flea’ market and counselling among others.

For more information, please contact:

Mrs Thembekile Doris Hlubi, P O Box 10070, Marine Parade, Durban 4056, Tel: 031 332 6853/6756/3721, Email:  msfta@saol.com

Natal Adult Education Support Agency, 2000