Campaign for a Latin American free of Violence against Women

ARGENTINA - ECUADOR

2013-2018

VISION

That the Latin-American society will be a place where gender violence towards women will not be tolerated and positive masculinity will be promoted and inclusive. A society where restored relationships are established with the active involvement of Latin-American women and men.

This vision is sustained by God’s purpose when he created women and men on his own image, with the same dignity, the same rights.

STRATEGY

Create a network of Christian organizations, denominations, churches, and education centres to prevent violence against women, protect victims, strengthen links with service providers and the church as well as identify provision gaps, and seek appropriate prosecution

We will start with a pilot project in two countries, Argentina and Ecuador, and we will expand it as funding is available.

There are five main pillars on this campaign:

- Baseline research around VAW impact in the church, services and legislation.

- Campaign to end VAW and Promote Positive Masculinities orientated to the church in first instance and then from the church to the general public.

- Strengthen links between current service and the church and provide training for future provision of services for victims y perpetrators.

- Advocacy at government level to include Femicide as a unique crime category and better government provision of services for victims.

- Online training and centralize hub for churches with resources, written material, videos etc.

LOG-FRAME

|  | Indicators |  |  |
| --- | --- | --- | --- |
| GOAL Important progress towards the eradication of VAW in Latin America |  |  |  |
| Purpose To built capacity of women and men to identify and respond positively towards VAW as well as support victims in their restoration through specialized services. | Number of women and men with increase awareness to identify and respond to VAW Number of women referred to specialized services. |  |  |
| Outcome 1 Baseline research conducted including : Levels of violence classified by type, current legislation, access to justice, service provision (statuary and non-statutory) for victims and perpetrators and perceptions/actions of the church around VAW by geographic area. | Report with findings about Levels of violence classified by type, provision and gaps in provision by Geographic area detailing type and scope. |  |  |
| Activities | Milestone 1 | Milestone 2 | Milestone 3 |
| Identify/outline places to conduct research | 2 weeks | 3 weeks | 4 weeks |
| Agree on definitions, methods and design research tools | 3 weeks | 4 weeks | 5 weeks |
| Data Collection | 7 weeks | 8 weeks | 9 weeks |
| Sorting information | 3 weeks | 4 weeks | 5 weeks |
| Written Report/Presentation of findings | 2 weeks | 3 weeks | 4 weeks |
| Total | 17 weeks | 22 weeks | 27 weeks |
|  | Indicators |  |  |
| Outcome 2 Campaign implemented to increase awareness in men and women about VAW and to promote positive masculinities. Directed to: Men and Women (initially focus on the church) When designing the campaign messages key targets groups will be consider according to the results of the baseline study | Number of people, organizations and churches reached by the campaign. At least 10 documented cases of organizations, people or churches with deep changes in their belief system and behavior. |  |  |
| Activities | Milestone 1 | Milestone 2 | Milestone 3 |
| Formation of the team who will be in charge of designing the campaign ( it will be 4 people ( 2 form Argentina Comunidad y Cambio /Kairos Foundation and 2 from Ecuador , 1 from P&E and 1 Mujeres Solidarias) | 2 weeks | 3 weeks | 4 weeks |
| Design of the Campaign | 6 weeks | 7 weeks | 8 weeks |
| Collection of feedback to Campaign . The campaign will be submitted to feedback from other Christian organizations with experience in gender and a minority of non-Christian groups working in the women’s sector Ej, Irene (Kairos foundation), Gemrip Bs As, P&H Peru, Micah Network. Pablo Besson Bs As, LA RED Bs.As., Universidad de Córdoba) | 4 weeks | 5 weeks | 6 weeks |
| Final Document of the Campaign | 3 weeks | 5 weeks | 6 weeks |
| Total | 15 weeks | 20 weeks | 24 weeks |
| Implementation | 2 years |  |  |
| Periodic evaluation in three instances: At the end of the design 1 year after implementation At the end of the second year. |  |  |  |
| Outcome 3 Enhanced support to victims and perpetrators from the Church and strengthen links between churches and specialized services. |  |  |  |
| Outcome 4 Improved gender equality as a result of changes in government policies regarding penalization of Femicide and allocation of resources. |  |  |  |
| Outcome 5 Updated and centralized hub of resources up and running, that facilitates access to all those interested in information, documentation, training etc to end VAW. |  |  |  |
| Outcome 6 |  |  |  |
| Monitoring and evaluation systems in place with clear timeframes and indicators established. |  |  |  |

Comments:

Areas for the pilot project have been defined as Cordoba Region in Argentina (Population 3.310.000 approx) and the city of Guayaquil in Ecuador (Population of 2.600.000 approx)