**Support to 12 informal schools with local volunteers’ project in Ruaraka, Nairobi.**

**LOGICAL FRAMEWORK**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | **Intervention logic** | **Objectively measurable**  **and verifiable indicators** | **Sources of verifications** | **Important assumptions** |
| **Development objective/goal** | Improve educational standards in the informal schools in Ruaraka. | Attendance at informal schools / Success rate of informal schools’ students | Schools’ registers / Public records  Ad-hoc survey / interviews with local people. |  |
| **Project objective/purpose** | To increase ratio of teacher to student from 1:60 to 1:25 in informal schools. | School records  Teachers records | School registers  Teachers profile document | Cooperation between the school management and PV-Kenya |
| **Results/outputs** | 1. 12 informal schools benefit from volunteer teachers for one year.  ---------------------------------------  2. 100 volunteer teachers and mentors teach and mentor pupils in the informal schools for one year  ----------------------------  3. 12 school reading and mentorship clubs established in each of the informal schools | Three way partnership agreement between PV, Volunteer and school  -----------------------------------  50% of pupils in each of the informal schools is mentored through this project  -----------------------------------  Reading clubs of 100 pupils in each school established- | Project personnel will visit all schools and monitor project progress  Monthly progress reports from volunteer teachers.  End of school term reports  Annual school reports  End term examination results | Healthy partnership agreement between schools management and PV-Kenya  Quality service from volunteer teachers |
| **Activities** |  | **Project costs:** | **Necessary capital goods, materials and local financing** | |
| Provide local informal schools with skilled volunteer teachers  ----------------------------  provide 1-to-1 mentorship for a most in need child in public and informal schools  ----------------------------  Establish school reading and mentorship clubs in each of the 12 informal schools. | Volunteer teachers allowances $ 60 for one month for 60 volunteers    Total cost = **$ 3,600.00**  -----------------------------------  Volunteer mentors allowances  $ 25 for one month for 40 mentors    Total cost = **$ 1,000.00**  ------------------------------------  Establish school clubs  $50 for 12 informal schools for one term.  Total cost for 3 terms.  **$ 600 X 3 =$ 1,800.00**  -----------------------------------  Administrative cost for the project **$ 100**  **Total cost for the project**  **$ 7,500.00** | Curriculum books from PV-Library.  Local financing:   * Monitoring and Evaluation of the project * Teachers Teaching Guide and Curriculum books to be provided by informal schools   . | |