PROGRESS REPORT

REBUILD KALIGATHUK SCHOOL FOR INDONESIAN STUDENTS

	Period : April 2007


After rebuilding of the ruined schools caused by the quake got into the closing stage, the procurement of the aid goods, the place preparation and the goods delivery were directly done in April 2007. 

For the reason of security, trellises were set to doors and windows before we sent the computers and several scientific books for library. As seen in the following pictures, workers were doing their work for security of two schools got the aid from Global Giving. 
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	The wooden door was equipped with the ironed trellises so that it would be much more secure. It is a part of appreciate other’s help. 
	The glasses windows were equipped with ironed trellises as well. Expectedly, if the donators come for a visit, the goods are still there in good condition. 


First stage of distribution to two schools of program beneficiary consisted of:

1) 6 (six) units of four-pentium-computer set for two schools (Each 3 (three) units computers)

2) 2 (two) units of printers and refilled ink for two schools (Each 1 (one) units)

3) 6 (six) units of computer desk for two schools (Each 3 (three) units)

4) 6 (six) units of chair (Each 3 (three) units)

Several of the mentioned aid goods can be seen in the following pictures: 
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	FTPI-Global Giving Aid before time of delivery to Kaligathuk and Mirisewu School.
	Students were cheerfully welcoming FTPI-Global Giving Aid.


Gratitude to FTPI-Global Giving and donators were expressed many times by the teachers. It was much more delighting as the students and the teachers enthusiastically tried to use the computers as seen in the following pictures of Kaligathuk and Mirisewu School. 
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	The students of Kaligathuk School were studying the computer assisted by the teachers.  
	Rika and Ade from Kaligathuk School were operating the computer by themselves. 


Activity in May and June 2007:

1) Monitoring students activity at schools

2) Delivery of the package of scientific books AKU INGIN TAHU MENGAPA which consists of 24 (twenty-four) books. Books content and their luxuriously design were expected to arise the reading interest of the students and to give the broader knowledge beside the lesson books. 

3) Delivery of the library bookcases that were attractive and specially designed for student accessibility reason so that the students would be more convenient to be in their library and to take care of it. 

4) Curriculum preparation of the student journalism training. 

5) Mentioning several names of students of the first and second class and names of Global Giving donator in the story books to motivate the students to read more frequently. 

In addition, if possible, we suggest the program to be applicable to other schools since the program REBUILD KALIGATHUK SCHOOL FOR INDONESIAN STUDENTS were quite beneficial to victim children of Yogya quake and there are still a lot of schools that need it.    

This is the brief progress report as our communication media. Thank you. 

Yogyakarta, May 1, 2007

Muslikhin Kusma

Fellow Ashoka

FTPI-Yogyakarta

Indonesia  

