The Empowerment of Children Dropped Out of School  in West Sulawesi

Considering the number of children who was forced to be able to not continue the school,  so as the empowerment program for them was very urgent was carried out. This program aimed at empowering children dropped out of school through the training and the increase in living skills (Life Skill) Like; printing media, sewed, made the cake, studied driving car, made bricks, business skills, family welfare and atc. Moreover also PUSPEM will give help of capital of efforts with the rolling system. In this progam, PUSPEM carried out the identification of the program in 2 regencies/the city that is; the Polewali Mandar Regency (Polman) and the Mamuju City, Province Sulawesi West.

Through this identification was gotten by 180 children dropped out of school.

The problems:

- Generally children that dropped out of school in the Polman regency, and Mamuju City because of the inability of parents.

- In general around children who dropped out of school this became the farmer to help parents.

- The shortage of the interest from these children to continue the school

4.   The influence of the environment that very strong

Output:

1.  Was built him 180 children dropped out of school.

2.  The concept increase of children dropped out of school with living skills and the

development of the small business and medium-sized businesses

3.  Children could again go to school

4.  Moved on him the aid fund of effort

5.  The increase in the achievement of the organisation and the management.

The profits:

- The development of autonomy 180 children dropped out of school in expanding efforts that will be undertaken by him

- The decline in the percentage of the number of children was neglected because of

dropping out of school

- The decline the number of unemployments that was absorbed by manpower or

that made efforts personally.

- The criminal action reduction that was carried out by children dropped out of

school because unemployed

5.   The increase in the income and welfare of the child on the whole

The activities:

- Preparations/the socialisation of the program

- Workshop of strategy the implementation of the program

- Children's check-up.

- Giving of help of nutrition for children

- Giving of the scholarship for 30 children who will continue his education

- Trainings of living skills

  - The training of efforts sewed

  - The training printing media

  - The training made the cake

  - The training driving car

  - The training made bricks

F.   The training of the marketing product

G.  The training of the management of efforts/bookkeeping

H.  The training of English

I.   The training computer

7.    Training services

8.    Monitoring and the evaluation of the program

9.    Reporting

- The first report

- The progress report

- The final report

Budget:

1. Preparations/the socialisation of the program

a. Transfort, 8 persons x 250.000 x 3 days = Rp.6.000.000

b. The stipend, 8 persons x 250.000 = Rp.2.000.000

c. The brochure, 10.000 sheets x 1500 =Rp.15.000.000

2. Workshop of strategy the implementation program

- Rent place, = Rp.1.000.000

- Transport participants, 100 pesrons x 50.000 = Rp.50.000

- Ate participants, 100 x 10.000 =Rp.1,000,000

- Stipend of speaker, 3 persons x 1.000.000 =Rp.3,000,000

- Banner =Rp. 250,000

3. The medical check-up for children

- Rent checkpoint, =Rp.1,000,000

- The Procurement medicines =10,000,000

- The Stipend of children of the health inspector, 2 x 1,000,000 =Rp.2,000,000

4. Giving of help of nutrition for children, 180 children x 250.000 =Rp.45,000,000

5. Giving 30 scholarships for children who will continue his education

30 children x 2,000,000 = Rp.60,000,000

6.  The trainings

a.  The training of efforts sewed

- Rent place for training, =Rp.1,000,000

- Rent sewing machine, 5 machine x 100,000 =Rp.500,000

- The Purchase of the thread, the needle and cloth, =Rp.2,000,000

- Transport participants, 50 x 50,000 =Rp.2,500,000

- Ate participants, 50 x 10,000 = Rp.500,000

- The Stipend of instructor, 2 person x 1,000,000 = Rp.2,000,000

- Banner, =Rp.250,000

b. The training of printing media

- Rent place for training, =Rp.1,000,000

- Rent equipment of printing media, =Rp.2,500,000

- The Purchase of the material printing media, =Rp.2,000,000

- Transport participants, 50 x 50,000 =Rp.2,500,000

- Ate participants, 50 x 10,000 =Rp.500,000

- The Stipend of instructor, 2 persons x 1,000,000 =Rp.2,000,000

- Banner, =Rp.250,000

c. The training made cakes

- Rent place for training, =Rp.1,000,000

- The Purchase of equipment of cook, =Rp.2,500,000

- The Purchase materials made cakes, =Rp.2,000,000

- Transport participants, 50 x 50,000 =Rp.2,500,000

- Ate participants, 50 x 10,000 =Rp.500,000

- The Stipend of instructor, 2 persons x 1,000,000 =Rp.2,000,000

- Banner, =Rp.250,000

d. The training of driving car

- Rent car, 5 car x 500,000 x 7 days =Rp.17,500,000

- Transport participants, 50 x 50,000 =Rp.2,500,000

- Ate participants, 50 x 10,000 =Rp.500,000

- The stipend of instructor, 5 persons x 1,000,000 =Rp.5,000,000

e. The training made bricks.

- Rent place for training, =Rp.1,000,000

- The Purchase of the material made bricks, =Rp.3,000,000

- The Purchase of the equipment made the bricks, =Rp.3,500,000

- Transport participants, 50 x 50,000 =Rp.2,500,000

- Ate participants, 50 x 10,000 =Rp.500,000

- The stipend of instructor, 2 x 1,000,000 =Rp.2,000,000

- Banner, =Rp.250,000

f. The training of the marketing product

- Rent place for training, =Rp.1,000,000

- Transport participants, 50 x 50,000 =Rp.2,500,000

- Ate participants, 50 x 10,000 =Rp.500,000

- The Stipend of instructor, 3 x 1,000,000 =Rp.3,000,000

- Banner, =Rp.250,000

g. The training of the management of efforts/bookkeeping.

- Rent place for training, =Rp.1,000,000

- Transport participants, 50 x 50,000 =Rp.2,500,000

- Ate participants, 50 x 10,000 =Rp.500,000

- The stipend of instructor, 2 x 1,500,000 = Rp.3,000,000

- Banner, =Rp.250,000

h. The training of the english  language

- Rent place for training during 6 months x 1,000,000 = Rp.6,000,000

- The Purchase of english language books, =Rp.5,000,000

- The stipend of teacher, 1,500,000 x 6 months =Rp.9,000,000

- Transport for children, 50 x 50,000 x 6 =Rp.15,000,000

- Banner, =Rp.250,000

i. The training of the computer

- Rent place for training during 6 bulan x 1,000,000 =Rp.6,000,000

- The Purchase 5 computers x 6,000,000 =Rp.30,000,000

- The Purchase 2 printers x 750,000 =Rp.1,500,000

- The Purchase of computer books, =Rp.2,500,000

- The stipend of instructor, 2 x 1,500,000 x 6 months =Rp.18,000,000

- Transport for children, 50 x 50,000 x 6 months = Rp.15,000,000

- Banner, =Rp.250,000

7. Training services, 2 instructor x 1,000,000 x 6 months = Rp.12,000,000

8. Giving of help of capital of efforts with rolling system.

=Rp.100,000,000

9. Monitoring the program

- Local transportation, 8 persons x 500,000 =Rp.4,000,000

- The Salaries, 8 persons x 1,000,000 =Rp.8,000,000

10. The evaluation of the program

- Local transportation, 4 persons x 500,000 =Rp. 2,000,000

- The salaries, 4 x 1,000,000 =Rp.4,000,000

11. Annual Reporting

- The first report, 1 x 500,000 =Rp.500,000

- The progress report, 5 x 500,000 =Rp.2,500,000

- The final report, 1x 1,000,000 =Rp.1,000,000

12. The management of the program, =Rp.5,000,000

Grand Total: =IDR Rp. 479,500,000

=USD $ 53,500