Volunteer With Us to Support 12 informal Schools project in Ruaraka, Nairobi.

LOGICAL FRAMEWORK

|  | Intervention logic | Objectively measurable and verifiable indicators | Sources of verifications | Important assumptions |
| --- | --- | --- | --- | --- |
| Development objective/goal | Improve educational standards in the informal schools in Ruaraka. | Attendance at informal schools / Success rate of informal schools’ students | Schools’ registers / Public records Ad-hoc survey / interviews with local people. |  |
| Project objective/purpose | To increase ratio of teacher to student from 1:60 to 1:25 in informal schools. | School records Teachers records | School registers Teachers profile document | Cooperation between the school management and PV-Kenya |
| Results/outputs | 1. 12 informal schools benefit from volunteer teachers for one year. --------------------------------------- 2. 100 volunteer teachers and mentors teach and mentor pupils in the informal schools for one year ---------------------------- 3. 12 school reading and mentorship clubs established in each of the informal schools | Three way partnership agreement between PV, Volunteer and school ----------------------------------- 50% of pupils in each of the informal schools is mentored through this project ----------------------------------- Reading clubs of 100 pupils in each school established- | Project personnel will visit all schools and monitor project progress Monthly progress reports from volunteer teachers. End of school term reports Annual school reports End term examination results | Healthy partnership agreement between schools management and PV-Kenya Quality service from volunteer teachers |
| Activities |  | Project costs: | Necessary capital goods, materials and local financing |  |
|  | Provide local informal schools with skilled volunteer teachers ---------------------------- provide 1-to-1 mentorship for a most in need child in public and informal schools ---------------------------- Purchase of school reading and mentorship materials clubs in each of the 12 informal schools. | Volunteer teachers allowances $ 60 for 6 months for 5 volunteers Total cost = $ 1,800.00 ----------------------------------- Volunteer mentors allowances $ 30 for 6 months for 5 mentors Total cost = $ 900.00 ------------------------------------ . $ 3,000.00 ----------------------------------- Administrative cost for the project $ 100 Total cost for the project $ 5,800.00 | Curriculum books from PV-Library. Local financing: - Monitoring and Evaluation of the project - Teachers Teaching Guide and Curriculum books to be provided by informal schools . |  |