Hydraulic Ram Pump Water System Project (Drinking)

Technical Study

| Project Partner | : Green Empowerment (GE) |
| --- | --- |
| Location | : Sitio Tinumpagan, Brgy. Kauswagan, Manjuyod, Negros Oriental, Philippines |
| Date of Survey | : March 29, 2007 |
| Target Number of Beneficiaries | : 35 – 45 households or 210 or 270 populace |
| Surveyor/s | : Placido Gonzales and Felix Inocencio of Alternative Indigenous Development Foundation, Inc. (AIDFI) |

Result/s:

Q  -  90 liters per minute

h   -   65 meters

H  -     3 meters

Distances:

Source – Catchment        :  60 meters

Catchment -  Ram Pump :   30 meters

Ram Pump – Reservoir   :   540 meters

Reservoir – Tapstand/s   :   300 – 400 meters

Structure:

Impounding Tank  - (0.6 m X 1.0 m X 2.00 m)

Catchment Tank  -   (1.0 m X 1.0 mj X 1.0 m)

Reservoir             -    (2,000 liters capacity)

Estimated Delivery Output:

One (1) unit – 1 ½ “ Hydraulic Ram Pump

q   = 2HQ/3h

Q  = 90 liters per minute

q   =  2 (3) (90)      540

------------  =  ------     = 2.76 liters per minute

3 (65)           195

q =  2.76 liters per minute X 1440 minutes/ day

q =  3,974.40 liters  per day  (with  10 % friction losses factor)

q =  3,5767 liters/day

Note:  q = delivery output (in liters/min.)

Q = water required by ram (in liters per minute)

h =  delivery height (in meters)

H =  available head from source to ram (in meters)

- PROJECT DESCRIPTION

This hydraulic ram pump drinking water system starts with the construction of 0.6 X 1.0 X 2.0 meters stone –ferrocement impounding tack just below the source spring/s.  A 2 ½ “ X 60 meters ISO HDPE SDR – 17 hose will be directly connected to the impounding tack and serve as diverstion line going to a 1.0 X 1.0 X 1.0  meters ferrocement cathment tank.

A 1 1/2 “ X 12 meters schedule 40 flanged and supported G.I drive pipe will be attached to the catchment tank on one end and to a 1 ½ hydraulic ram pump with stainless steel waste valve, stopper and check valve place on the other end.

The  delivery line from the ram pump will be composed of ¾ “ X 540 meters ISO HDPE distribution line composed of ¾ “ X 500 meters ISO HDPE SDR-17  hose will be coupled between the intermediate tank and 2,000 liters ferrocement reservoir that will be constructed at Sitio Tinumpagan.  There will be 3 taps stands that will be constructed and be established on the strategic area wherein households are located, serving as communal faucet/s.

- WORK PLAN

Alternative Indigenous Development Foundation, Inc. (AIDFI)

- Purchase, preparation and fabrication of materials

- Hauling of materials to an on project site

- Lay-out and connection of all pipes  and hoses

- Construction of all cement structures

- Installation and tuning of ram pump

LGU of Manjuyod/ Brgy. Development Council and Community

- Provide funds for the project

- Embedding of all pipings

- Provide two or three permanent resident technicians for ram pump repair and maintenance which will be trained during the actual installation

- Facilitate all budgetary requirements necessary for the project implementation

- Facilitate any legalities that may arise during the project implementation

- Provide accommodations to Alternative Indigenous Development Foundation, Inc. (AIDFI) Technical Staff.

- WORK SCHEDULE

| Purchase and preparation of materials | Fifteen days (12 days) |
| --- | --- |
| Hauling, construction and installation | Twenty five (18) days |
| Curing period of cement works | Twenty (21) days |
| Total | Fifty one (51) days |

IV.  LIST OF MATERIALS

- Impounding Tank (0.6 X 1.0 X 2.0m)

  - 15 bags Portland cement                      @  180.25             Php  2,703.75

  - 2  cu.  m.  mixing sand                                450.00                        900.00

  - 1  cu. m. gravel                                            550.00                        550.00

  - 3 rolls wire mesh (# 12 2 “ X 6’ X 20’)       1,001.00                    3,003.00

  - 5 sheets ordinary plywood (1/4 “ X 4’ X8’)   285.00                    1,425.00

  - 3 kgs. G.I. Tie Wire # 18                                50.00                       150.00

  - 1 pc. Doweled Nipple 3” X 12”                     230.00                       230.00

  - 1 pc. G.I. Cap 3”                                           163.55                       163.55

--------------------

Php 9,125.30

10 % contingency                               912.53

-------------------

Sub-Total                               Php 10,037.83

============

- Diversion Line

  - 1 roll  ISO HDPE 2 ½ X 60 m SDR-17     @ 9,348.30        Php 9,348.30

  - 2 pcs. Fabricated Doweled Hose Clamp          300.00                  600.00

------------------

Php 9,948.30

10 % contingency                               994.83

------------------

Sub-Total 			     Php 10,943.13

===========

- Catchment Tank (1.0 X 1.0 X 1.0m)

  - 5 bags portland cement                            @ 180.25          Php     901.25

  - 0.5 cu.m. mixing sand                                    450.00                     225.00

  - 10 bags gravel                                                 20.00                     200.00

  - 2 rolls wire mesh # 12 2” X 6’ X 20’)            1,001.00                2,002.00

  - 2 sheets ordinary plywood  (1/4” X 4’ X 8’)      285.00                   570.00

  - 1 kg. G.I. tie wire # 18                                        50.00                     50.00

  - 6 pcs. Coco lumber (2”X 2” X 8’)                        40.00                   240.00

  - ½ kg. c.w. nail  4”                                               40.00                     20.00

  - ½ kg. c.w. nail 3”                                                40.00                     20.00

  - ¼ kg. c.w. nail 1”                                                45.00                     11.25

----------------

Php 4,239.50

10 % contingency                              423.95

-------------------

Sub-Total                              Php 4,663.45

===========

- Drive Pipe (30 meters)

  - 5 lengths G.I. G.I. Pipe 1 ½ “ X 20’  S 40        @ 976.00     Php 4,880.00

  - 14 pcs. MS flanges 3/8” X 1 ½ “ X 4”                   188.80            2,643.20

  - 42 pcs. SS bolt and nut with washer                       20.60               865.20

  - 7 pcs.  rubber gasket  1/8” X 1 ½ “ X 4”                   25.00               175.00

------------------

Php 8,563.40

10 % contingency                      856.34

------------------

Sub-Total 		        Php 9,419.75

===========

- 1 unit – 1 ½ Hydraulic Ram Pump with     @ 11,000.00   Php 11,000.00

stainless  waste valve, check valve

and stopper  plate (1 set)

--------------------

Sub-Total 		       Php 11,000.00

===========

- 1 unit – 1 1/2 “ HRP Foundation Frame

  - 4 pcs. Threaded CR shafting ½ “ X 12”        @ 45.00          Php      180.00

  - 8 pcs. Stainless nut ½ “                                     12.00                        96.00

  - 1 length Deformed Bar 10 mm X 6 m               140.00                     140.00

  - 2 bags portland cement                                     180.25                    360.50

  - 8 bags gravel                                                       20.00                    160.00

  - 6 bags mixing sand                                              15.00                     90.00

-------------------

Php   1,026.50

10 % contingency                       102.65

--------------------

Sub-Total 		       Php   1,129.15

============

- Delivery Line (540 meters)

  - 2 rolls ISO HDPE Hose 1 ¼ “ X 60 m SDR-11 @ 5,800.10  Php 11.600.20

  - 2 rolls ISO Hose 1” X 100 m SDR – 11                 4,979.50           9,959.00

  - 2 rolls ISO HDPE Hose ¾ “ X 150 m SDR – 11    3,579.05           7,158.10

  - 2 pcs. ISO brass rep. 1 ¼”                                       538.20           1,076.40

  - 2 pcs. ISO brass rep. 1”                                           335.40              670.80

  - 2 pcs. ISO brass rep. ¾”                                          303.20              606.40

  - 1 pc. G.I. reducer 1 ¼” X 1”                                       22.00                22.00

  - 1 pc. G.I coupling 1 ¼”                                             347.00              347.00

  - 1 pc. G.I. coupling 1”                                                277.33              277.33

  - 1 pc. G.I. reducer ¾”                                                208.80              208.80

  - G.I. reducer 1” X ¾”                                                   15.00                15.00

  - G.I. nipple 1 ¼” X 3”                                                   14.50                14.50

---------------

Php  31,955.53

10 % contingency                                3,195.55

--------------------

Sub-Total                                  Php  35,151.08

---------------------

- 2,000 liters Ferrcement Reservoir

  - 7 bags portland cement                     @ 180.25                      Php  1,261.75

  - 0.5 cu.m. mixing sand                             450.00                                285.00

  - 2 rolls wire mesh # 12 2” X 6’X 20’       1,001.00                             2,002.00

  - 3 sheets ordinary plywood                       285.00                               855.00

  - Lumber 2”X2’X8’                                      120.00                               960.00

  - 1 kg. c.w. nail 1 ½ “                                    60.00                                 60.00

  - 1 kg. c.w. nail 3”                                         60.00                                 60.00

  - 1 kg. G.I. tie-wire # 18                                50.00                                 50.00

------------------

Php 5,473.75

10% contingency                          547.37

------------------

Sub-Total 		          Php 6,021.12

------------------

- Distribution Line

  - 4 rolls ISO HDPE Hose ¾ “ SDR-11      @ 3,579.05            Php 14,316.20

  - 2 pcs. ISO Plastic reducer ¾ “                       102.65                         205.30

  - 2 pcs. Plastic coupling 3/4 “                            208.80                        417.60

  - 2 rolls Teflon tape ½”                                        20.00                          40.00

------------------

Php 14,979.10

10% contingency   		       1,497.91

--------------------

Sub-Total                       Php 16,477.01

--------------------

- 3 Units Tapstand/Fittings

  - 2 pcs. G.I. elbow ¾” C 450                  @ 25.00	                    Php      50.00

  - 2 pcs. G.I. ¾” C 900                                 27.00 				54.00

  - 3 pcs. G.I. doweled nipple ¾” X 6”          35.00		                    105.00

  - 1 pc. G.I. doweled nipple 1 ½” X 12”       55.00			           55.00

  - 1 pc. G.I. cap 1 ½”                                   65.00				65.00

  - 3 pc. Gate valve ¾”                                135.00                                405.00

  - 3 pcs. Brass faucet                                  75.00                                225.00

  - 6 bags portland cement 		         180.25    		       1,081.50

  - 10 bags mixing sand 			15.00 			          150.00

  - 15 bags gravel 				20.00			          300.00

------------------

Php 2,490.00

10% contingency                          249.05

-----------------

Sub-Total 		         Php  2,739.55

-------------------

K.  Tool Kit (1 set) 								Php 2,500.00

-----------------

Sub-Total		          Php 2,500.00

------------------

Summary:

| A. Impounding Tank | Php 10,037.83 |
| --- | --- |
| B. Diversion Line | 10,943.13 |
| C. Catchment Tank | 4,663.45 |
| D. Drive Pipe | 9,419.75 |
| E. 1 ½ “ Hydraulci Ram Pump | 11,000.00 |
| F. 1 ½ “ HRP Foundation Frame | 1,129.15 |
| G. Delivery Line | 35,151.08 |
| H. Ferrocement Reservoir | 6,021.12 |
| I. Distribution Line | 16,477.01 |
| J. Tap Stands/Fittings | 2,739.55 |
| K. Tool Kit | 2,500.00 |
| Total Material Cost | Php 110,352.07 |
| Add: Hauling Labor Social Preparation | 8,000.00 78,000.00 15,000.00 |
| Total Project Cost | Php 211,352.07 or $ 4,403.00 |