| ACTION/ ACTIVITY | INDICATORS | TARGET | PROJECT BUDGET FOR 5YEARS |  |  |  |  | Total | SOURCE OF FUNDING |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2016/2017 (000) | 2017/2018 (000) | 2018/2019 (000) | 2019/2020 (000) | 2020/2021 (000) | (000) |  |
| Prosecution of perpetrators | No. of cases handled | 200 Cases | 6,000, | 6,000, | 6,000, | 6,000, | 6,000, | 40,000, | District support and non-state actors like JFCU |
| Conducting radio programmes and Community Barazas | Number of radio talk shows conducted. Number of radios partnered with. no. of Community barazas Conducted | 72 Radio talk shows | 14,400 | 14,400 | 14,400 | 14,400 | 14,400 | 72,000, | District support and JFCU |
| Conducting school outreaches in the District to openly talk about child Marriage and its consequences | Number of school visited | (240 out reaches) | 17,200 | 17,200 | 17,200 | 17,200 | 17,200 | 86,000, | District support and non-state actors like JFCU |
| Capacity Building for TOTs at S/C and school level. | Number of trainings and trainees | 5 Trainings | 16,700, | 16,700, | 16,700, | 16,700, | 16,700, | 83,500, | Non-state actors like JFCU |
| Conduct community dialogues on child marriage issue. this will be done on market days, prayers days and Community Barazas | Number of dialogues carried out | 4dialogues, 1 each sub county per month (240 meetings) | 14,680, | 14,680 | 14,680 | 14,680 | 14,680 | 73,400, | District support and Non-state actors like JFCU |
| Make child marriage a Discussion point on every district and sub county levels meetings and Monday Police parades | Number of discussion meetings | 4 meetings (quarterly) | 5,200, | 5,200 | 5,200 | 5,200 | 5,200 | 26,000, | District support and Non-state actors like JFCU |
| Follow up on child Marriage cases | number of cases reported, number reports on cases handled | on going | 10,200, | 10,200 | 10,200 | 10,200 | 10,200 | 51,000, | JFCU and Butaleja District |
| Review Meetings about the progress of the project | Number of meetings conducted | 20 meetings. (4 pa) | 5,525, | 5,525, | 5,525, | 5,525, | 5,525 | 27,625, | District support and JFCU |
| GRAND TOTAL |  |  | 91,905, 000 | 91,905, 000 | 91,905, 000 | 91,905, 000 | 91,905, 000 | 451,525, 000 |  |