## Sheet1
| Global Giving |  |  |  | Last update:
| Status of Villages Undergoing Hydraulic Ram Pump Installation- Negros, Phillipines |  |  |  | 2003-12-18
| Location | POPULATION (households / people) | CURRENT PHASE (Technical study; Seeking Funds; Construction; Finished) | BUDGET | local CONTRIBUTION (Local Gov, AIDFI, Community) | CONTRIBUTIONS FROM GLOBAL GIVING, GREEN EMPOWERMENT, & other foundations.
| 13 technical studies |  | Funded - 9 of 12 studies completed | 2780 | 0 | 2780
1 | Amin/Isabela | 80 households / 480 people | Construction Feb'08 | 5114.35 | 1468.15 | 3646.2
2 | Bayhao | 300 households / 1,800 people | Construction Dec '07 | 6312 | 6312 | 0
3 | Canlandog | 100 households / 600 people | Planning | 6607.2 | 6607.2 | 0
4 | Purok Lacson | 300 households /1,800 pple | Planning | 7536.2 | 7536.2 | 0
5 | Purok Lopues | 130 households / 780 people | Planning | 19013.9 | 19013.9 | 0
6 | Nangka & Minaluha | 120 households / 720 people | Seeking Financing | 12134.39 | 7525.5 | $4,609 sought
7 | Manghumay | 90 households / 540 people | Seeking Financing | 6546.18 | 3088 | $3,458 sought
8 | Candabong | 70 households/ 420 people | Technical Study in progress | 9345.898 | 4682.8 | $4,663 sought
9 | Buenavista | 100 households / 600 people | Technical Study in progress | 11281.04 | 5304.85 | $5,976 sought
10 | Buglas | 30 households / 180 people | Seeking Financing | 6895.298 | 3660 | $3,235 sought
11 | Sikatuna | 100 households / 600 people | Seeking Financing | 11634.08 | 5731.7 | $5,902 sought
12 | Balicotoc | 80 households / 480 people | Technical Study in progress | 8046.926 | 3841.45 | $4,205 sought
13 | Paytan & Mabini | 150 households /900 people | Technical Study in progress | 11710.6 | 7475.6 | $4,235 sought
| Total cluster plan target | 1650 households /9900 people |  | 124958.062 | 82247.35 | 42710.712
| Commitment to-date |  |  | 88673.55 | 82247.35 | 6426.2
| Total Needed |  |  | 36284.512 |  | 36284.512