PROJECT AT A GLANCE

| Name of the Project | A Proposal for –Training, Workshop, Rehearsal & performance of show Including capacity building of open stage for Folk & Tribal Performing Art at Tribal Area of Birbhum, West Bengal, India. |
| --- | --- |
| Performing Art | i)Baul, ii)Raibes(Marshal Dance), iii) Santali Dance iv)Kabigaan v) Dhak&DholBadddya vi) Leto vii) Bahurupi |
| Project Area | Village:Debanandapur,GP: AlbandhaSarpalehana Gram Panchayet, Block: Bolpur Sriniketan, Dist.-Birbhum , West Bengal, INDIA |
| Executing & Implementing Agency | “AIM” ART ILLUMINATES MANKIND |
| Legal status of the implementing organization | i) Reg. No. S/IL/16764 of 2003-04 W.B Act. XXVI of 1961 ii) FCRA Registration No. 147120903 iii) IEC(Importer-Exporter Code) 0209005190 iv) EPCH Registration No. 31006/2011-12 v) Fair Trade Forum-India Member ID : WBK-O-130111 |
| Contribution of AIM | - 2 Acres of Land - Existing of open Stage. iv) III Phase Electricity connection v) Water (Sub-Marseille Pump) |
| Total Project Cost | US $ 10,443.00 |
| Project Period | 06 months |

PROFILE OF THE ORGANISATION

Our Mission:

The mission of the organization is to study and research, focusing on the folk culture, tribal art and craft that are on the brink of extinction in order to protect the rights and to safeguard the interests of those associated poor people, suffering from deprivation and exploitation by bringing them into limelight through various required social interventions.

Our Objectives:

1)  	    To research, study, investigate different folk & tribal art & craft of India.

2)	To focus on the art and craft of associated people and   to ensure comprehensive development.

3)	To make common people more   aware of the social, economic & cultural life of the artisans.

4)	To revive and restore ancient culture, art and craft.

5)	To support and promote cultural activities through the universally appreciated medium of folk & tribal art & craft, music, theatre, film, painting and literature.

6)	To organize national and international level   seminars and festivals to popularize Indian folk & tribal art & craft in India and abroad.

7)	To motivate children and impart them formal and alternative education like music and dance and to train mentally retarded children and adults through the medium of art and craft.

8)	To run health care programmers in villages and educate people to lead a hygienic way of life based on rationalism and reason.

9)	To provide skill training, counseling and other support to women artisans and other poor women who have no social support system to rely on. We aim at enhancing self reliance and autonomy of women by upgrading their productivity and intensifying their income generating activities.

10)	To take steps to protect the environment from further degradation.

Background of the Organization- The Genesis:

Every community based organization is germinated to address to a specific social need. Like others, the genesis of “AIM” Art Illuminates Mankind is no exception. A group of like-minded social activists, with their vision to a sustainable social development, joined hands together for meaningful social interventions to protect the rights and to safeguard the interests of the poor and underprivileged sections of the society.  In order to fulfill that vision, the organization viz. “AIM” Art Illuminates Mankind was established in 2003 with its mission to focus, study and research on the folk culture, tribal art and craft along with the associated people to bring those people into limelight through various required social interventions . Since then the group continued to work to make common people aware about these art and culture, socio economic and cultural life of those people through various documentation, exhibitions, fairs, festivals etc.

PROJECT PROPOSAL

Project Title

A Proposal for –Training, Workshop, Rehearsal & performance of show  Including capacity building of open stage for Folk & Tribal Performing Art at Tribal Area of Birbhum, West Bengal, India.

Executive Summery:

India is marked by its rich traditional heritage of Tribal/Folk Arts and Culture. Since the days of remote past, the diversified art & cultural forms generated by the tribal and rural people of India have continued to evince their creative magnificence. Apart from their outstanding brilliance from the perspective of aesthetics , the tribal/folk art and culture forms have played an instrumental role in reinforcing national integrity, crystallizing social solidarity, fortifying communal harmony, intensifying value-system and promoting the elements of humanism among the people of the country. However with the passage of time and advent of globalization, we have witnessed the emergence of a synthetic homogeneous macro-culture. Under the influence of such a voracious all-pervasive macro-culture the diversified heterogeneous tribal/folk culture of our country are suffering from attrition and erosion. Thus the stupendous socio-cultural exclusivity of the multifarious communities at the different nooks and corners of our country are getting endangered.

UNESCO’s Declaration on Cultural Diversity mentions that culture, cultural knowledge, and intangible heritage all have a role to play in alleviating poverty and creating livelihood opportunities. In this project we are covering five folk forms namely Baul, Raibense(Marshal Dance), iii) Santali Dance iv) Kabigaan v) Dhak&DholBadddya

This folk performers lamented lack of opportunities to practice and perform. They did not even think of their art form as a possible means of livelihood. Many had stopped nurturing their art forms. As most of these people lack formal education they earned mostly through daily labor and agriculture. There was thus a vicious cycle of poverty and loss of traditional skills and wisdom. The leading folk artists across all the folk art forms are continuously sensitized on the prospects of safeguarding their traditional heritage as a means of livelihood. Their active participation and support all through the project will be a key factor in achieving the key targets of this project i.e. rejuvenation of the art forms and improved well being of the folk artists. Training and capacity building plan will be formulated with participation of the Folk Gurus as well as leading singers, musicians, theatre workers and various stakeholders in promotion and patronage of our cultural heritage. On completion of construction of Studio theater, there will be a rigorous training will be held per month for three to six months across twenty five blocks for strengthening the basic skills of the artists under the aegis of the Gurus. There will be an innovation, exchange, interaction and skill transfer with contemporary dance, music and theatre performers will be facilitated to innovate new ways of rendering the art forms and improve their marketability

This project will be established a model for empowering communities lacking formal education but rich in intangible cultural heritage. It shall successfully used livelihood perspective for safeguarding cultural heritage. The project will showcase how performing art traditions can be explicitly treated as resources in the context of achieving sustainable community development. Replication of this model for other performing and visual art forms across India holds the promise of answering the critical need of augmenting income generation options for rural and tribal people of the country. Unfortunately culture is often considered as separate from the process of economic development. There is thus need for dissemination of the success stories and best practices established by this project among various stakeholders in rural non farm sector development and academic organizations doing research on development theory. We have a vast untapped scope for developing cultural industries based on traditional intangible cultural heritage. Our folk forms can become powerful tools for economic development, poverty reduction and assurance of cultural diversity if cultural industries are mainstreamed into national development plans.

Under such circumstances, we are submitting project proposal  for –Training, Workshop, Rehearsal & performance of show  Including capacity building of open stage for Folk & Tribal Performing Art at Tribal Area of Birbhum, West Bengal, India.           The proposal will be governed by the following logic–driven objectives:-

Objectives of the project

- To create appropriately equipped training, rehearsal and performance spaces for artistes.

- To explore and analyze the status of various forms of tribal and folk art & culture of Birbhum District

- To study the intensity of acceptance and popularity of the folk songs and folklores within the area of operation as well as the adjoining areas

- To study the existing opportunities facilitating the preservation, promotion and dissemination of tribal and folk art & culture

- Preservation Promotion and Dissemination of all forms of Tribal and folk art &culture;

- To predict logical and strategic mechanism for enhancing the skill of the practitioners of traditional art & culture;

- To suggest tenable strategies for enshrining, promoting and propagating tribal and folk art

&culture.

Project Area

Moram, Debanandapur, Bolpur, Birbhum, West Bengal, INDIA

ROAD MAP

By AIR- The nearest Airport is Calcutta Approx 225 km.

By Rail- The nearest railhead is Bolpur, 15 km away. Trains connecting Bolpur with Howrah/Sealdah are HWH-Bolpur Shantiniketan Express, Ma Tara Exp, Shahid Exp, Kanchenjunga Exp, Saraighat Exp.

By Road- Good Motor able Roads connect MORAM ,Debanadapur  with Calcutta 238 km via Delhi Road

About the Art Forms

Birbhum is known not only for its red soil and the shallow serpentine rivers ridden with sand islands, but also for the notable poets. Many poets belonging to the age of VaishnavaPadabali and ShaktaPadabali of Bengali poetry were born here, as for example, Jaydeb, the celebrated author of Geetagovinda, and Chandidas (Rami).

Bauls

The bauls of Birbhum, their philosophy and their songs form a notable representation of the folk culture of the district. Baulism is a religiously liberal philosophy and lifestyle which might have some links to Sahajiya movement of 16th century (derived from Sahajyan, a form of Vajrayana Buddhism, influenced also by Vaishnavism and Sufism). Chandidas and many other poets were part of the Sahajiya movement. The bauls earn their living by singing and collecting alms. They accommodate people from any caste and creed. Poet Rabindranath Tagore was inspired by their philosophy and patronized them actively. Birbhum has also been home to famous kabiyals, kirtaniyas and other folk culture groups.

Baul and Fakiri music is a rich, vibrant and living folk heritage of Bengal. These wandering minstrels sing about love and devotion. Their philosophy emerged in a society stifled with superstitions, caste divisions, religious intolerance and malpractices, Bauls and Fakirs sang about humanism and brotherhood, celebration of life and nature. Baul philosophy propagates the thought that God resides amongst us and we humans should search our soul for finding God within.

Santali dance

The Santali dance and music is tuned with the nature of occasion whether it is social or ceremonial. The three most quintessential instruments in Santali music are two kinds of drums one Tumdak and the other Tamak, and Tiriao or flute. The Tumdak is a double headed drum having the shape of a frustum, the drum skins at left and right are made of animal skins. The one at the left has bigger circumference than the right. The Tamak has a hemispherical shape, with a wider circumference and played by two drum sticks. Tiriao or basically a bansuri is a bamboo made musical instrument with five holes.

The most well known dance form of the Santals is a group of women with interlocked hands forming a semicircle, encircling a relatively smaller group of male percussionists at the centre. The dance steps and movements are in accordance with the beats which is relatively simple. The dance forms, countenance, and beats differ from region to region. The Santali Dance have a wide variety and types and is tuned with ceremony and social celebrations. The Dasai dance is performed only by males of the community on festive occasions. Langre, Guluri, and Humtiis danced all round the year, whereas Baha and Sohorai are only for festive seasons. In social ceremonies like marriage Dong is danced. Along with these popular dances some other rare forms like Rinjha and Jhika also exist and performed only in few regions.

The Santal songs also have similar variety like there dance, the Santali word for song is "Sereng". Generally singing is accompanied with dancing but there are some songs which do not include dancing. There is also a kind of song sung during the sowing of paddy. The "Gam Sereng" is another type of song which is sung in hot summer evening.

Dhaki

Dhakisare  traditional drummers who play the dhak (drum) during religious Festival of Hind us. Birbhum district is  notorious for this instrument palyers.The nuances of playing the instrument are handed down from generation to generation, but the old rhythms are undergoing changes. The rhythm is no longer as slow as in earlier generations. Nowadays, dhakis opt for faster tunes. Before, different beats were used for specific aspects of Durga Puja, as for example chokhhudaan (eye presentation), pathabali (goat sacrifice), bisarjan (immersion ceremony), sandhyaarati (evening offerings), sandhipuja (worshiping at the conjunction of two phases), and so on.Dhakis who cannot learn within the family typically take training under a guru in order to become a good dhaki, as is the case for most musical instruments. Some take six months to become mature players, while others do not even learn after three or four years. Many young dhakis nowadays are moving towards modern rhythms.

The occasions when the dhak was played are changing. Apart from pujas or religious festivities, dhakis are also called to play in markets before Durga Puja when people crowd in large numbers. Sometimes, they are called for store inaugurations.

Raibenshe

Folk dance is a dance of primitive or rural communities originated from their culture reflecting their way of life very closely. In Bangladesh, folk dances have flourished since ancient times. Folk dance is a very popular pastime form and integral part of many religious, cultural and social gatherings.

Folk dances differ from classical dances in many ways. The tempo, rhythm and gestures of classical dances are complicated and require long and arduous practice. But folk dances are simple and spontaneous. Since there are no complex or ritual gestures and movements, they can be learnt more easily. Folk dances are passed down from one generation to another, and, although the artistes have a great deal of liberty in performance, the basic form remains the same.

.Raibenshe is such a traditional folk dance which is not yet brought under regular learning and practice.Raibenshe dance is mostly performed in the western regions of Birbhum, Bardhaman, and Murshidabad. These dances are only performed by the men who belong to the Bauris, Domes and other depressed castes of the Hindu community. Raibenshe dance is a martial dance form of Bengal remarkable for their expression of their military energy and depiction of martial arts. These dances serve as a reminder of the military prowess of the Bengalis.

The Raibenshe dance was a martial dance of the Raibenshe community, which was a Hindu community under the Gangaridaijanapad (ancient state). The Gangaridai stretched a long way on the coastline of the Bay of Bengal between the westernmost (Bagirothi River) and easternmost River Padma mouths of the Ganges. The inhabitants of Gangaridai were highly skilled in fighting and even in boating. Because of the powerful and tactful arm force of Gongaridi, the force of Alekjendar could not dare to move forward when he attacked India in 326 BC. The Raibenshe martial dance is a traditional art of a community of GangaridaiJanapad.

The performers of Raibenshe dance wear brass anklets known as ‘nupurs’ on their right ankle during their performance. The Raibenshe dance is considered as one of the manliest and energetic folk dance of Bengal. It is often accompanied with wild yells of men, and punctuated with gestures that suggest drawing of bows from the quiver, throwing of spears and brandishing of knives.

At times the dancers proceed in a squat position towards the middle of the ring alternatively joining in and out while bending knees. This dance position imitates the hunters riding on the back of a horse. At other times the dancers form pairs where one of the partner stands on the shoulder of the other partner moving hands and arms. The upper partner performs the head movements and lower partner performs the foot movements. This performance requires high acrobatic skill, and practice.

Kabigaan

Kavigan is normally sung by two groups. Each group is led by a kaviyal or sarkar. The accompanying singers called dohars often repeat what the leader said. A kaviganprogramme starts with bandana (evocation) or gurudevergeet (song of the sect patron). The bandana can be directed to or be in praise of Saraswati, Ganesh, people, and the audience, as deemed fit by a particular kaviyal. This is followed by Radha–Krishna related song, some call it agamani. Then songs on four subjects are sung: Sakhisambad, biraha, lahar and kheur. Finally, the competitive part starts.Inkavigan, also referred to as kabirlarai, two person who are lyricist plus composer at the same time answer each other in form of songs. A number of kaviyals attained popularity and fame. In Birbhum district alone there were about three hundred kaviyals from the 18th–20th century. Amongst the earliest were GonjlaGuin, born in the 18th century and his contemporaries: Lalu–Nandalal, Raghu and Ramji.

Leto

Leto is a form of folk drama,

Bahurupee

The word Bahurupee had derived from Bahurup which signifies multiforms. Bahurupee are capable of assuming or disguishing various types of appearances. This particular form of art did not arise from any religious beliefs. It is completely secular in nature and had arisen from the hunger of the general low caste, poverty stricken backward classes of agrarian society. Bahurupees are mostly found in Birbhum.  They earn their livelihood by amusing people with different appearances. Two or three members are needed for the performances of Bahurupee.

Present Condition of Folk performers

The twenty first century, the age of globalization, is marked by the incidence of cultural crisis. It is the era in which many tribal/folk art & cultural forms are either losing originality, or passing into oblivion. Globalization has exerted adverse influence in the social, economic and cultural arenas. Especially our indigenous cultural exclusivity is getting decimated. Our traditional culture is being replaced by a homogenized and westernized culture which is fomented and fostered by rampant consumerism. This has a negative impact on the third-world countries. Its vitiating influence is destroying cultural identity.

The massive transformation that globalization has engineered in the cultural arena, is that the indigenous culture of the various parts of the entire world are gradually coming under the clutches of an all-pervasive omnipresent macro culture. As a result the exclusive micro cultures that retain our cultural identity are on the verge of extinction. Indigenous cultural forms are becoming vulnerable to subjugation by a synthetic macro culture which is toppling the socio-cultural structure of the regions having weaker economy.

Global culture is maliciously affecting the cultural identity of the backward society. Since our study was concentrated among the tribal communities of the impoverished areas, we have witnessed the fact that incisive permeation of a synthetic global culture has exerted an injurious influence upon these areas disrupting the community structure, social structure, and cultural structure. Globalization has facilitated the infiltration of consumerism andthe art of playing the dhak is now being referred to as a dying profession. While some of the dhakis may be lucky to retain old contacts, many are facing a decline and some are moving away from the traditional profession. Take the example of the more than hundred dhaki families in Ratanpur, a village in Birbhumdistrict. Ancestors of the dhakis were on the palace of Birbhum. Daily pujas were organised for the deities in the palace and the dhakis played a significant role. Times have changed. One of them was offered Rs. 800 for playing the dhak for five days. It is a pittance. Some of the younger generation even took to work as shoe shine boys, but the older generation hedonist culture. This is gradually effacing our cultural identity at the local, ethnic, and national levels. Globalization has emerged as a tempestuous deluge, engendering the diverse cultures of our backwards areas, decimating stable localities, displacing people under the pressure of market force , and developing a market-driven, brand-conscious cultural propensity among the people of the society. A globally endorsed monoculture is silently creeping into the mind of the common people thus effacing the interface between locality-defined cultures which had constituted our identities.

Through globalization the entire world is shrinking into a single place marked by the dominant presence of a single culture and single identity. Distinctions of culture and society are wiped off through a homogenous global culture.

Folk-art forms are getting removed from their religious ritualistic nature. Religion is a binding factor in the areas covered under study. Since there has emerged a chasm between religion and culture, intensity of local culture is waning away. Thus the entire indigenous culture system is crumbling and there will no longer be any socio-cultural solidarity. In this context it deserves mention that we have witnessed a threatening phenomenon. Under the severe pressure of commercialization and market economy, we have found that even in the religious rituals popular cultural forms are being used as a tool for mass entertainment. Moreover with the advent of globalization materialistic culture has outpaced mystic culture. Many community-based religious rituals, where the devotion towards the deity was offered through folklores, have ceased to exist. Thus the traditional artists are being left in the lurch. Under tremendous economic pressure they are being compelled to make an occupational shiftstill has pride in being artists. They look down upon such misadventures of the younger generation, but do not have an alternative before themselves.

Ratanpur, in theBolpurarea of Birbhum district, is a locality of dhakis, who came as refugees from East Bengal. There is not a single family without a dhaki. All used to go out to work as dhakis during the festive season, but now the demand has declined to such an extent that many are forced to give up the traditional profession and work as wage labourers. Worse still, a dhaki from the village was contacted by a well-known Durga Puja in Kolkata for Rs. 2,000. They regret, “earlier, we used to be treated like any other artist. Today, we are just another component of the Puja paraphernalia, who are supposed to perform on those days.“ Earlier, they used to be from around Mahalaya, but now go only for the five days. The importance of dhakis has diminished because of some people's preference for electronic music and bands. These days, some of the Nott’s make dhaks. A dhak made of mango wood and goat skin sells for around Rs 3,000 to Rs 3,500, leaving a profit of only Rs 50. Some have taken to other professions.

Dhakis are losing out to technology. While music shops do brisk business in selling pre-recorded CDs and cassettes for anything between Rs. 23 and 40, dhakis find it hard to earn Rs. 150 to Rs. 200 per day, poor compensation considering the cost or hire charges of the dhak, the training that the dhaki must undergo, and the effort involved.

JUSTIFICATION OF THE PROJECT

It is clearly evident that tribal/folk art and culture is of immense importance in ensuring national integrity, communal harmony, diversified socio-cultural identity of the various corners of our country and our adherence to the traditional value-system of our nation. This project is of immense importance because it has made an attempt to review the current status of Tribal/ folk Arts and Culture. It has tried to explore the utility of Studio Theater cumRehearsal&training center for the Promotion and Dissemination of Tribal/ folk performances of Birbhum.

The direct interaction with the performers and the reputed institutions involved in promoting the Tribal Arts & Culture is expected to throw light upon the significant issues, critical problems and daunting challenges relevant to the professional performances. The regular rehearsal & training will improve the skill of the performers.

BENEFICIARIES:

| Direct | 500 artist in the adjoining areas of Debanandapur, Bolpur, Bhirbhum |
| --- | --- |
| Indirect | 1) Family Members of the Artist. 2) Academicians, Scholar and Students from all over the world interested in the ancient folk Arts & tribal Culture in the area. 3) Visitors of the place. |

Social impact of the project:

As an impact, this training centre will bring the scope of increased level of income for the beneficiaries, which will be helpful to raise their level of independence and will lead them to participate in the decision making process. Stable income in the family will definitely improve the overall quality of life of all the family members. Increased awareness will motivate them towards a positive attitude in regard to their family affairs especially for childcare and will enable them to send their children to the school resulting into reduced dropout of children from the school and abolition of child labour in the community. As the project is replicated in other areas, it will have its greater impact in the community. Thus the project will directly contribute towards the total development of the society.

- PROJECT EXPENDITURE (Non-Recurring Exp)

YEAR-1

| Sl.No. | COMPONENTS OF COST |  | Amount(Rs.) | Amount(Rs) |
| --- | --- | --- | --- | --- |
| 1 |  | Land &Building |  | Owned |
| 2. |  | Infrastructure development for open stage i) Electrical Fittings- ii)Interior Decoration /Furniture/Sound& studio equipment etc | Rs 50,000.00 Rs2,00,000.00 | Rs 2,50,000.00 |
| 3. |  | Musical instruments Dhol/Nagara/Shehnai /Dhamsa/Sword/Dhaki & Drum /Ektara/Dotara/ Flute/Harmonium/Violin/etc |  | Rs 50,000.00 |
|  |  | Audit fees |  | Rs 10,000.00 |
|  |  | TOTAL |  | Rs 3,10,000.00 |

- PROJECT EXPENDITURE (Recurring Exp)

YEAR-1

|  | COMPONENTS OF COST |  | Amount(Rs) |
| --- | --- | --- | --- |
| 1. | Training cost 1)Salaries of Gurus-2*6*Rs20000/- 2)Supervisor cum Manager-1*6*Rs6000/- 3)Accountant-1*6*Rs5000/- | Rs 2,40,000.00 Rs 36,000.00 Rs 30,000.00 | Rs3,06,000.00 |
| 2. | Other Operational Cost - Electricity& Generator-Rs2000*6 - Travelling expenditure to Gurus/trainers - Snacks to trainees (@Rs100/- | Rs 12,000.00 Rs 30,000.00 Rs 50,000.00 | Rs92,000.00 |
| 3. | Organized performance of show( troupe of 15 Artists) in metropolitan cities of India, once in Kolkata, Delhi & Mumbai (i)Hire charges of Hall(@Rs25000/- (ii)TA&DA(@Rs2500/-head) (iii)Arrangement cost & Publicity (@Rs60000/-venue | Rs 75,000.00 Rs 1,12,500.00 Rs 1,80,000.00 | Rs3,67,500.00 |
| TOTAL RECURRING EXPENDITURE |  |  | Rs 7,65,500.00 |
| TOTAL EXPENDITURE | (Non-Recurring A + Recurring B) |  | Rs 10,75,500.00 |
| Less-Income generated through performance of show and PIA Contribution |  |  | Rs 4,30,000.00 |
| TOTAL Financial Requirement( in Indian Rupees) |  |  | Rs 6,45,500.00 |
|  | Conversion rate from INR to US $ | 0.0161786 |  |
| TOTAL FINANCIAL REQUIREMENT (in US DOLLAR) |  |  | US$ 10,443.00.00 |