Trans-nzoia Youth Sports Association (TYSA)
SAFE SPACE FOR CHILDREN AFFECTED BY POLITICAL VIOLENCE IN KENYA

2008

 CURRENT  PROJECT STATUS REPORT 
MAY 2008
Writen by:

TYSA BOARD

contact Person

Gichuki Francis

Executive Officer

Tel.+254 725 200099

Email; tysktl@yahoo.com,info@tysak.org, gichuki@tysak.org
Web: www.tysak.org 

Keeping Children’s Hope Alive


Introduction

This project has enabled children to meet and socialise with other young people in similar circumstances at the Noigam IDP camp and also interact with trained and committed volunteers who would act as positive role models. It has provided them with both emotional and educational support thus empowering them to broaden their base of social support outside their families.  The project has given them the opportunity to develop through trying out new activities and learning some essential life skills. Through this project children are being safeguarded from abuse, discrimination and harm of any kind.
Towards achieving the project objectives:
The project is addressing the following four issues; Hopelessness, Poor School attendance, Trauma and Idleness among the children and youth at the Noigam IDP camp.

We have witnessed encouraging results so far which include:
· Improved school attendance, especially at Noigam primary school initially attendance for the IDP pupils was as low as 40 %.Currently it is at 70 %
· Increased participation in sports activities as evident by formation of more sports and recreational groups. we started with 12 but current we have 48 sports groups
· More youths seeking information which can help them continue with education, or develop their careers
· There is increased positive attitude towards life as demonstrated by the desire to resettle back to their homes

· Reduction in violence cases among  the children

Project Implementation Status
Daily Sports and Creative Arts
TYSA Sports and recreation volunteers run daily activities at the IDP camp. They also offer interface break activities in collaboration with other agencies. Up to date 90 sessions have been offered
School Link

Through its School Link program with local schools, TYSA has managed to secure scholarships for 3 girls from the IDP camp to pursue secondary and 1girl post secondary education. 30 are still in our waiting list.
Girls Empowerment 

The Girls Empowerment forum is an outcome of close working relationship with girls at the IDP camp. These girls are now more confident and ready to face the life challenges. One training session on post secondary education career choices was done in April. Other session covering different themes will be done in subsequent months.
Campaign against Child Labor

Labor Days’ ‘NO to Child Labour, Let Me Play’ Campaign is an activity that demonstrated children have the capability to speak and express themselves.  This was done through sports, music, poetry, dance and facing painting. This campaign will be sustained for the next two months in order to highlight and reduce cases of child labour
Child and Youth Protection
TYSA was influential in the formation of the Inter agencies Child and Youth Protection Team at the Noigam IDP Camp .The mandate of the team is to coordinate all protection issues relating to children and youth at Noigam IDP camp. TYSA together with International Rescue Committee spearhead the coordination.

Project Sponsorship Status
	Project Activities
	Sponsor
	Sponsorship Package
	Areas NOT Sponsored

	Counseling Services
	Handicap International
	4 Counselors 
	Counseling books, assorted reading materials, 

	School home work support
	Safaricom Kenya Limited
	Texbooks,Teachers’ guide books, story books, pens,
	Exercise books

	Creative Arts e.g. drawing, painting etc
	Safaricom Kenya Limited
	Crayons,manilla papers,plastcisine,water colors, printing papers
	Drums, costumes,

	Sports and Recreation
	Alive and Kicking Kenya

Globalgiving (Keeping Hope Alive)

	Balls

Balls
	Mobile goal post, old tyres, darts, uniforms, volleyball nets, Balls, amplifier



	life Skills Development
	No sponsor
	-
	Video equipments, Generator, Instructors’ transport and stipends

	School link program
	Wiyeta Girls School
TYSA
	School Fees for 3 girls
Partial fee for 1 college girl
	30 girls school  / college fees

	*Transport Expense
	Mamacash
	Transport for  2 sports  instructors 
Ksh.32,000
	Transports for 18 volunteers

Ksh.288,000 (US$ 4500)

	*Volunteer Stipends
	No Sponsor
	-
	Stipends Ksh.320,000 (US$ 5000)

	*Administration costs
	TYSA
	Printing and typing
Ksh.60,000
	Photocopying, office costs,
Ksh.100,000 (US$ 1570)


Appeal

We are Appeal for urgent sponsorship especially to support logistical and administrative activities which are Key to the project implementation. 
