

	Background information


	Many parts of Kenya particularlly North Rift region were engulfed in unrelenting political violence arising from the disputed results of the December 2007 General elections. Ensuing  protests led to loss of lives, property worth millions of shillings and displacement of over 20,000 people in Trans-nzoia East district specifically Geta Farm. These were hosted at the Noigam Kachibora IDP camp, where TYSA has been working for the last four months offering psycho-social support, sports & recreation, safe space for children, education scholarships for girls, child labour advocacy, peace building and youth empowerment.


	Aim of the project

	To provide an opportunity for the East African youths to share knowledge and experiences and contribute towards dialogue, peace building, reconciliation and affirm solidarity with the internally displaced persons.
 

	Activities


	1. Training workshops on peace and conflict resolution
2. Sports 4 peace tournaments
3. Festival extravaganza e.g. sports, games, drama, music, athletics etc.
4. Community work e.g. rebuilding a burnt house, or donations



	Participants
	Youths from Uganda, Tanzania, Rwanda, Denmark and Kenya. We expect 200 active participants as well as 10,000 community members to be reached by the end of the project.

	Time Frame/Venue
	It will run for 4 weeks Starting 1st to 31st August 2008 at Noigam IDP camp and Geta farm.

	What contribution can I make to this great Project?
	By providing any or part of these: 
1. Training Workshops (7 days for 50 Participants)
· Stationeries

· Meals for participants

· Transport

2. Sports 4 Peace Tournaments

· 60 assorted balls

· 8 sets of uniforms

· 10 Volleyball nets
3. Festival Extravaganza

· 1000 printed T-shirts
· 2000 peace message pamphlets/brochures

· Public address system

· Transport for invited groups

· Refreshments

4. Community Work

· 40 bags of cement

· 100 iron sheets

· 1000 Tree seedlings

· Assorted household items or any other gifts
5. Logistical Support

· Accommodation for 20 participants from East Africa and Denmark (Kshs, 120,000 equivalent to USD 2,000)
· Meals for 20 participants from East Africa and Denmark (Kshs, 100,000 equivalent to USD 1,670)

· Transport for 20 guest participants (Kshs. 80,000 equivalent to USD 1,400)

· Transport for 8 local invited groups (Kshs. 32,000 equivalent to USD 540)
· Typing, Printing and photocopying (Kshs. 12,000 equivalent to USD 200)


	Contacts
	For more information on the project and your support, please contact:
Trans-nzoia Youth Sports Association (TYSA)
E-Mail: info@tysak.org  tysaktl@yahoo.com (www.tysak.org)
Phone : +254 725 200 099

Contact Person : Gichuki Francis
Designation: Executive Officer



