About Reach India

Reach India(RI), headquartered in Kolkata has been working in poverty endemic states of India with a mission to enable women, adolescent girls and youth to build futures of health, hope and dignity for themselves and their families by bringing knowledge, life skills and linkages. Reach India carries its mission by imparting life changing health and livelihoods education to women and girls from poor families through its partnership with Self Help Promoting Institutions (SHPI’s) including government in the areas of health, livelihoods and family finance. Reach India has helped in promoting demonstrable and replicable models across different geographic areas focusing on young girls in the age group of 10-19 years and women’s self help groups (SHG’s). Reach India has established itself as a professionally managed organization with its work in 14 states including  Assam, Bihar, Jharkhand, Chhattisgarh, Orissa, Meghalaya & West Bengal. Reach has its expertise in designing, developing behavior change communication and educational modules based on adult learning principles. Reach works directly or through its partners in the areas of its geographical focus, thus building the capacities of frontline workers and cascading education to the community members with a direct outreach to 13,01, 316 women and 212,218 girls on thematic areas like public health, vocational skills, livelihoods, banking for the poor and organizational development.

In Murshidabad, West Bengal, Jamtara and Deoghar, Jharkhand Reach India is working with poor and marginalized women and their families for improving their capabilities and access to resources for their enhanced health and income status. Reach focuses on formation, nurturing and strengthening of women SHGs in Raghunathganj 1 & 2 blocks of Jangipur, Murshidabad, West Bengal. The project is supported by NABARD, West Bengal. Till date Reach has formed 426 SHGs linked with savings facility at Scheduled Commercial Banks out of which 88 groups have access to credit facility, with each group accessing 1 lakh rupees as credit facility. Reach has created a cadre of 16 community resource person, two block supervisors and one service centre manager who currently forms the team and look after the day to day running of the projects ranging from group meeting, training, opening of bank facilities to credit linkage, grading etc.

Most of the women are from minority Muslim community engaged in bidi rolling and as agriculture labour. Reach is identifying opportunities to provide them skills training to set up micro enterprises, take up cultivation of vegetables on leased land, or strengthen their livestock farming. Reach is also imparting life-skills education, promoting health awareness and building capacities of the group members and their daughters so that they are able to access the products and services to improve their sanitation and health status.

As a new approach, Reach India increasingly engages communities through intensive social mobilisation process and it also engages with officials, people’s representatives, and other social and business groups to strengthen delivery and accountability of the services. (www.reach-india.net)

Map

Project Area and the Map :

Murshidabad is one of the 19 districts of West Bengal. Murshidabad is located on the southern bank of the Bhagirathi, a tributary of the Ganges River. The place is of great historical importance. The district is named after the historical town of Murshidabad, which was named after Murshid Quli Khan, all of Bengal was once governed from this town. According to the 2011 census Murshidabad district has a population of 7,102,430, roughly equal to the nation of Bulgaria or the US state of Washington. This gives it a ranking of 9th in India (out of a total of 640 districts). The district has a population density of 1,334 inhabitants per square kilometer as against the state average of West Bengal being 903 and the national average of 382 persons per sq. km. respectively.

The proposed project area Raghunathganj located at 24°28′N 88°04′E is an administrative block and part of Jangipur subdivision with an area of 94.65 kilometers. Reach is working in all the six (6) village councils [locally known as gram panchayats] in Raghunathganj 1 Block namely Dafarpur, Jamuar, Jarur, Kanupur, Mirzapur and Raninagar. However the project will focus intensely on Dafarpur and Jamuar Gram Panchayats.

The majority of people of the district, around 64%, are Muslim by faith whereas Raghunathganj has 75.61% Muslim population.  Most of the people depend on agriculture based livelihoods. Murshidabad being famous for its silk threads have some traditional silk farms and weaving units, but they are losing out fast against the modern industries. Bidi [local cigarette] industry is also there. Many of the India's major bidi [local cigarette] companies are from this district and women and children are mostly involved in this trade in bidi rolling.

Instead of having a very glorious past, Murshidabad district has lost its past glory and currently many parts of Murshidabad, largely rural areas suffer from chronic poverty because of overdependence on agriculture with majority having small and unviable plots of agricultural lands or working as agricultural labors or migrant labors.

Problem statement:

Raghunathganj-1 block of Murshidabad district has socially and economically disadvantaged population, mostly from minority Muslim community. Most girls are married off at a young age between 14 to 16, and much before they attain the legal age of marriage (18 years), bear and give birth to first child, and suffer from lifelong cycle of poor health, low literacy, poverty, diseases and drudgery. Because of the prevalent purdah (veil) system women’s social movements are restricted and younger women post marriage, remain confined within their households. The health intervention proposes to equip women with relevant knowledge, skills and linkages so that they access without hindrance the products and services that they need, through different service providers including the flagship National Health Mission programme of government of India. The intervention will focus on enabling them to assert their needs and entitlements, exercise free and informed choices about age of marriage, use of contraceptives, family size, etc. for the improved health and well being of themselves and their families.

Male members mostly work as agriculture labour and in recent times, a large majority trained in masonry locally, migrate to big cities. In the absence of the adult male members in many families, responsibility of looking after their families comes on the women. Women contribute to their family income apart from managing the household chores and responsibilities. A large number of women in this belt are engaged in hazardous bidi (local cigarette) rolling along with their children who are preferred by the traders for bidi rolling, because of their nimble fingers. Statistics reveals 9 out of 10 women are engaged in bidi binding job in Murshidabad. The main problem and intervention is not with the bidi binding, but its associated effects to their health, environment and society as smoking tobacco is a known pollutant and a source of carcinogenic diseases. It is evidenced that the bidi binding as a livelihood activity not providing a huge yield in compare to their effort. As discusses with few of the young women from our SHG groups, we get to know about the fact that for a 1,000 pieces of bidi they are getting a mere 100 rupees and after giving so much effort they are able to earn 1,500 to 2,000 rupees per month only. But the bitter fact is that to earn that amount most of the time they use to engage small children and adolescent girls from their families and in the long run these people get affected with lung related diseases such as TB and for pregnant women their children born with asthma and other lung related diseases.

A suitable alternative and proven viable source of income, of enabling these women to earn through sewing and tailoring will go a long way in reducing their dependence on bidi rolling. Reach has experience of providing training on sewing, tailoring and also on different trades, and later allowing them to get self-employed through establishing these trades that are suitable for women with restricted outside movement. Such other trades that have been promoted successfully are beauty parlour business, grocery shops etc. However sewing and tailoring is a viable livelihood option which can create large scale self employment and has wide spread acceptance within the focus groups which have restricted social movements, as it can be pursued comfortable from their home.

After receiving initial tailoring training, a trained person can purchase a machine and start her own tailoring shop. Tailors who start up their own businesses perform all the duties of a regular tailor but they also run their businesses, which includes creating marketing campaigns, finding new clients, hiring additional workers and dealing with budgetary concerns. With an initial investment of mere 10,000 rupees ($167), trained women can earn from Rs. 3000 to Rs. 6000 per month ($ 50 to $100) as an incremental income, which compares well with their income from bidi rolling and would be even higher as women gain proficiency and devote more time.

Existing  intervention:

Reach India has been working in the Raghunathganj and other blocks of Murshidabad, having promoted more than 426 self help groups of more than 6000 poor women, all of which have their own bank accounts. Self help groups are collective unit comprising 10 to 15 women of same locality and similar socioeconomic backgrounds, which enable them to enhance their individual and collective potential through group based savings, microcredit activities and other social development processes. Now 175 of these self help groups have taken bank loans for pursuing individual and group based activities for their income generation. We are also addressing health and hygiene issues affecting their lives through our initiatives.

- It is observed that mostly women get married early in the age group 14 to 16 years and become mothers even before their legal age of marriage of 18 years. Among the focus group, small family norms are not observed and women have poor reproductive and sexual health and hygiene.

- Women and children also suffer from widespread malnutrition.

- Mostly the young women and children are compulsively engaged in bidi 
(local cigarette) rolling activities and suffering from different types of health hazards.

Proposed Intervention:

At present we are proposing two pronged intervention, which will address reproductive & sexual health and hygiene issues and also simultaneously address their income poverty through the following set of proposed project activities:

| Theme 1 Reproductive sexual health, hygiene and nutrition | Activities | Sub activity | No. of activities | Outcome |
| --- | --- | --- | --- | --- |
|  | Situational analysis | Baseline study | 1 |  |
|  | Reproductive and Sexual Health, Hygiene & Nutrition and Sanitation | Awareness generation at the community level | 10 | Enhanced understanding on reproductive health, sanitation, nutrition, need better Equipped with life skill to assert their entitles & right and better access govt. services and products |
|  |  | Awareness generation amidst adolescent boys and girls in schools | 10 |  |
|  |  | Training of 50 women on RSH over 1 year, each training of 6 days duration @ 3 hours per day | 24 |  |
|  |  | Follow up training and assistance at the field locations; 4 FTA in each quarter; each FTA will provide onsite support to 4 trained women leaders. | 16 |  |
| 3. | Strengthening Community Level Institution Building Processes | Facilitation for developing action plan by the young women to address their health, reproductive sexual health, nutrition issues | 12 | Increase in demand for iron tablets, nutrition supplements, contraceptives, sanitary napkins and exclusive breast feeding, ANC monitoring |
|  |  | Facilitating linkages with Patient Welfare Committees( Rogi Kalyan Samity) under the National Health Mission (Programme) at the block level to address the community level issues identified through village plans |  |  |
|  |  | Advocacy for developing district level action plans to address their health, reproductive sexual health, nutrition issues incorporating village plans |  |  |
|  |  | Working with the village health and sanitation committee and strengthening the system of health services in the villages |  |  |
|  |  | Involving SHGs in community actions involving trained 50 young women as health resource persons |  |  |
| Theme 2 | Income Generation | Training of 50 women on tailoring, weaving for 10 days in 2 batches for 10 days | 2 | Women have incremental increase from sewing and tailoring |
|  |  | Helping 50 women to set up their home based sewing and tailoring units by purchasing sewing machines and making necessary arrangements | 2 |  |
|  |  | Refresher training for 50 women on tailoring |  |  |
|  |  | Advanced training on tailoring | 2 |  |
|  |  | Follow up , technical assistance about the machines and monitoring |  |  |
| 5. | Impact assessment | End line study | 1 |  |

- Measurable indicators in the reproductive sexual health, hygiene and nutrition

- No. of women who report regular intake of iron tablets

- No. of household who report consuming safe drinking water

- No. of household who report their resolve in using toilets

- No. of women who report recommended practice for menstrual hygiene including use of sanitary napkins

- No. of women who report delaying marriage of girls in their families, till they attain legal age

- No. of young women who report joint decision making on spacing or delaying pregnancy

- No. of mothers who report commitment to antenatal check-up

- No. of mother of new born who report the decision to exclusive breast feed their children

6.      Measurable indicators in income generation

- Women having sustained and incremental income

- No. of women who reports joint decision making in financial matters

This project is based on the first hand experience of working with poor women of the district and related feasibility analysis of related data. Subsequently the project will be scaled up in the entire district of Murshidabad and other poverty endemic districts in west Bengal and Jharkhand, India by linking up with government and corporate sector partners.

| Proposed Budget for the Period of August 2015 to July 2016 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sl. No. | Particulars | Timeframe | No of unit | Unit Price | Total amount |  | Budgetary Notes |
|  |  |  |  |  | In INR | In $ |  |
| Theme 1 | Reproductive and Sexual Health, Nutrition and Sanitation |  |  |  |  |  |  |
|  | Awareness, knowledge and skill building |  |  |  |  |  |  |
| 1a | Awareness generation at the community level |  | 10 | 5000 | 50000 | 833 |  |
| 1b | Awareness generation amidst adolescent boys and girls in schools |  | 10 | 10000 | 100000 | 1667 |  |
| 2 | Training of 50 women on RSH over 1 year, each training of 6 days duration @ 3 hours per day | Q1-July to Sept 2015; Q2: Oct to Dec 2015 | 24 | 10000 | 240000 | 4000 | Each batch will be of 15 beneficiaries, each batch will receive 3 hours training spread across 6 days covering 18 hours of effective training delivery. So 24 days will be needed to cover full training coverage for 100 bens . |
| 3 | Follow up training and assistance at the field locations; 4 FTA in each quarter; each FTA will provide onsite support to 4 trained women leaders. | Full one year; July 2015 to June 2016 | 16 | 5000 | 80000 | 1333 |  |
| 4 | Apportioned salary for training expert |  | 4 | 30000 | 120000 | 2000 |  |
| 5 | Training related travel |  | 4 | 10000 | 40000 | 667 |  |
|  | Total |  |  |  | 630000 | 10500 |  |
|  | Strengthening Community level Institution Building processes- direct staff cost of 1 community resource person for carrying out/supporting following activities (6a-6e): |  | 12 | 7000 | 84000 | 1400 |  |
| 6a | Facilitation for developing action plan by the young women to address their health, reproductive sexual health, nutrition issues |  |  |  |  |  | Involving PRI and communities |
| 6b | Facilitating linkages with Patient Welfare Committees( Rogi Kalyan Samity) under the National Health Mission (Programme) at the block level to address the community level issues identified through village plans |  |  |  |  |  | Involving block level officials, NGO representatives and health department officials |
| 6c | Advocacy for developing district level action plans to address their health, reproductive sexual health, nutrition issues incorporating village plans |  |  |  |  |  | Involving District Offficials, Civil Surgeon from the government health department |
| 6d | Working with the village health and sanitation committee and strengthening the system of health services in the villages |  |  |  |  |  | Involving PRI, communities, ASHA, ANM, Anganwadis |
| 6e | Involving SHGs in community actions involving trained 100 young women as health resource persons |  |  |  |  |  |  |
| 7 | Advocacy and liaising related travel |  | 12 | 5000 | 60000 | 1000 |  |
|  | Total |  |  |  | 144000 | 2400 |  |
|  | Supervision, Monitoring and Evaluation |  |  |  |  |  |  |
| 8 | Conducting baseline and end line study |  | 2 | 200000 | 400000 | 6667 |  |
| 9 | Project monitoring and supervisory support including review workshops, documentation support | Full one year; July 2015 to June 2016 | 12 | 6000 | 72000 | 1200 |  |
| 10 | Monitoring related travel | Full one year; July 2015 to June 2016 | 12 | 5000 | 60000 | 0 |  |
|  | Total |  |  |  | 532000 | 7867 |  |
| Theme 2 | Income Generation |  |  |  |  |  |  |
| 11 | Training of 50 women on tailoring, weaving for 10 days in 2 batches for 10 days | Q1-July to Sept 2015 | 2 | 50000 | 100000 | 1667 | Training will be non residential and of 10 days duration |
| 12 | Refresher training for 50 women on tailoring | Q2-Oct to Dec 2015 | 2 | 25000 | 50000 | 833.3333 | Training will be of 3 days duration to provide refresher and follow up support |
| 13 | Advanced training on tailoring | Q3- Jan-Mar 2016 | 2 | 50000 | 100000 | 1667 | Training will be of 7 days duration |
| 14 | Honorarium to trade specific certified trainers from recognized institutes for tailoring, stitching and embroidery |  | 50 | 1000 | 50000 | 833 |  |
| 15 | Training related travel |  | 15 | 800 | 12000 | 200 |  |
| 16 | Capital assets for training and raw materials | Q4-Apr-June 2016 | 4 | 18000 | 72000 | 1200 |  |
| 17 | Assets for the future initiative for the trainees |  | 50 | 8000 | 400000 | 6667 |  |
|  | Total |  |  |  | 784000 | 13067 |  |
|  | Admin & Overheads |  |  |  |  |  |  |
| 18 | Apportioned time cost for the project management team |  | 12 | 50000 | 600000 | 10000 |  |
| 19 | Project Coordinator |  | 12 | 15000 | 180000 | 3000 |  |
| 20 | Apportioned time cost for the accounting support |  | 12 | 15000 | 180000 | 3000 |  |
| 21 | Admin travel |  | 12 | 10000 | 120000 | 2000 |  |
| 22 | Overheads cost |  | 12 | 10000 | 120000 | 2000 |  |
|  | Total |  |  |  | 1200000 | 20000 |  |
|  | Grand Total |  |  |  | 3290000 | 54833 |  |

http://www.jiarm.com/May/paper2672.pdf