## Sheet1
MOUNTAINS OF HOPE CHILDRENS MINISTRIES WORKPLAN 2015
Project | Task | Person resp | Status | Months
HEALTH |  |  |  | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sep | Oct | Nov | Dec
| Training community on making of sanitary pads | Milly | Complete | bar: Months Aug
| Training 50 youth to make energy saving stoves | Joy | Not started | bar: Months Nov
| Provide water purifiers to 50 people | James | Complete | bar: Months July
| Train 50 women to set up back yard gardens | James | Complete | bar: Months Mar
| Train 50 mothers on best feeding | James | Complete | bar: Months Jan
SPONSORSHIP/EDUCATION | Pay school fees,scholastic materials and tuition for 11 children | James | Ongoing | bar: Months Feb; Months May
| Tuition payment for 2 University students | James | Ongoing | bar: Months Mar; Months July
| Build a home/orphanage for children | James | Ongoing
| Provide 50 children with blankets | Milly | Not started | bar: Months Dec
| Facilitate 50 children celebrate Christmas parties | James | Not started | bar: Months Dec
| Facilitate a primary school with posho to enable children have lunch at school | James | Not started | bar: Months Sep
| Facilitate 2 schools with foot and Net balls | James | Not started | bar: Months Sep
| Facilitate 50 school girls with solar led lamps | Lilian | Complete | bar: Months Feb
ADMINISTRATIVE COSTS | Payment of office rent | James | Complete
| Internet monthly subscription | James | Ongoing
| Electricity | James | Ongoing
| Water | James | Ongoing
| Night guard | James | Ongoing
| Purchase of power back up | James | Ongoing | bar: Months Sep
| Hospitality | James | Ongoing
| Stationery,tonner | James | Ongoing | bar: Months Jan; Months Apr; Months July; Months Oct
| Staff salaries | James | Ongoing