2015 Budget  Anticipated census:  100 campers ages 4 to 16      Actual: 60 campers   due to funding cuts

T-shirts $ 2.50 x 100	 $  250

Actual :  $150

Art Supplies 		 $  200

Actual      $200

Snack $0.50 per child	 $2,400	 ($0.50 x 100 kids x 6 days = $ 300 x 8 weeks = $2400)

Actual     $1440

Certificate $0.75 x 100	 $      75   Completion certificates used in end of camp ceremony

Actual     $45

Transportation 	1	$1,920	(2 tuk tuk for 30 kids $ 20 round trip x 6 days = $ 240 wk x 8 wks = $1920

Actual   $0   Cancelled due to lack of funding

Transportation 	2	$   960    ($20 round trip est. 10 kids from FSP x 6 days x 8 weeks = $960

Actual    $0   Cancelled  due to lack of funding

Party supplies & Food	$   200	( estimated 150 persons)

Actual   $ 120

Buses for water park	$   300	(estimated 3 buses)

Actual   $0   Cancelled  due to lack of funding

Entry fee  water park	$   300	( estimated at $3.00 per camper)

Actual  $0   Cancelled due to lack of funding

Misc. expenses 8 weeks	$1,000	( covers unanticipated expenses, supplies, extra transport, more kids

Actual   $ 470

Fund raising costs	$  750    ( estimated average fundraising costs on GlobalGiving site for project)

Actual  $ 345

Total Budget 2014 	$8,255

Approximate  Total  spent   $ 2770    vs  funds raised  of $ 2795