A MEAL A DAY PROJECT FOR THE ORPHANS AND WIDOWS AMONG THE IDPs

# WORK PLAN

| NAME OF PROJECT | A MEAL A DAY |
| --- | --- |
| NAME OF ORGANISATION | MARKENGEE HOME FOR ORPHANS AND WIDOWS (MAHOW) |
| EXPECTED OUTCOME | PROVIDING THIRTY DAYS OF HEALTHY MEALS FOR THE LESS PRIVILEGED |
| TOTAL FUNDS | Five Thousand Dollars ($5,000) |
| DURATION | Thirty Days (One Month) |

|  | Main Planned Activities | Implementation Period | Lead Party/Person |
| --- | --- | --- | --- |
| 1. | Organisation of Meal | Entire Duration | Mr. Damilare |
| 2. | Distribution of Meal | Entire Duration | Mr. Godfrey |
| 3. | Safety Talk | Entire Duration | Dr. O. Daniel |
| 4. | Security | Entire Duration | Mr. O. Frances |

# ESTIMATED BUDGET

| ORGANISATION | MARKENGEE HOME FOR ORPHANS AND WIDOWS |
| --- | --- |
| PROJECT | A MEAL A DAY FOR THE ORPHANS AND WIDOWS AMONG THE IDPs |
| BUDGET | FIVE THOUSAND DOLLARS |
| DURATION | ONE MONTH (30 DAYS) |

| LINE | ITEMS | UNIT COST | NO. OF UNITS | AMOUNT |  |
| --- | --- | --- | --- | --- | --- |
|  | PROJECTS ACTIVITIES |  |  | NGN | USD |
| A1 | A PACK OF MEAL | 150 | 200 | 30,000 | 150 |
|  | DURATION |  | *By 30 Days |  |  |
|  | SUBTOTAL |  |  | 900,000 | 4,500 |
|  | LOGISTICS |  |  |  |  |
| B1 | PROCUREMENT | 25,000 |  | 25,000 | 125 |
| B2 | TRANSPORTATION OF SUPPLIES AND PERSONNELS | 25,000 |  | 25,000 | 125 |
|  | SUBTOTAL |  |  | 50,000 | 250 |
|  | OVERHEAD |  |  |  |  |
| C1 | PERSONNEL | 50,000 |  | 50,000 | 250 |
|  | SUBTOTAL |  |  | 50,000 | 250 |
| TOTAL COSTS |  |  |  | 1,000,000 | 5,000 |