## Sheet1
Project | Description | Parish | Acres | Partners | Start Date | Status | Market | What is needed | Notes
Onion | Reduce importation of foreign Onions by 100,000lbs per season. This is an Agriculture student-run Farm. Flagship program with Heart Trust Academy & various neighboring agriculture schools | South Manchester | 5 acres | Heart Trust, CASE | 2013 | Active - In the process of preparing lands for November Cultivation | Local | US$30k funding to cover fertilizer, agriculture student stipends, travel, room & board | Traditional farming. First season lost 30%, 2nd season notable improvements- harvested 1000 LBS (no loss.) Tested Sweet Peppers and carrots for intercrop & rotation. Red Peas and Corn tested. Corn failed. Red Peas and carrots did well, Sweet Pepper did exceptionally well. Planting high density onions, 20k-25k pounds per acre. Spacing 4 inches apart. 50 students, volunteers and Peace Corp. to plant and harvest starting November 2015
Santa Cruz Scotch Bonnet Pepper Seed Bank | Organic Scotch Bonnet Pepper Seeds & Seedlings Run By Farmer and Student Interns | St. Elizabeth (Santa Cruz) | 3000 sqft greenhouse plus 30 acres of land |  | 2014 | Active - in the process of Harvesting seed and growing seedlings | Loal and Export | US$8k funding to cover agriculture student tipends for additional students to work the Greenhouse, travel, room & board | Greenhouse was donated to the farmers, however they were provided no trays & no irrigation. We provided organic resources: manure, trays, etc. Northeastern university volunteers launched the project by planting the initial seedlings. Requests for seeds and seedlings are pouring in from neighboring Farmers.
Scotch Bonnet Pepper | Organic Scotch Bonnet Peppers (Transition from Conventional to Organic) | St. Elizabeth (Santa Cruz-Bright River) | 200 acres | Bright River Cooperative. Farming Co-Op (26 farmers) | 2014 | Active - in the process of bringing in organic inputs to improve soil quality | Local and Export. Contaracts for 5000 lbs. peppers per week. 100+ super markets and Patty shops | US$40k funding to increase Soil Quality to bring yield to 5k pounds/week (currently getting 100 pounds/week.) travel, room & board | Planted 5 acres of Scotch Bonnet pepper seedlings after cleaning up the land. Will improve soil quality by adding biomas; soil problems are deeper than topsoil. Expanding to a total of 10 acres. Will be introducing solar-powered water pumps to combat drought.
Ginger | Provide Jamaican ginger to dōTERRA, largest manufacturer of essential oils in the world. | Westmoreland (Haddo) | 10 acres | dōTERRA & Knockalva Agriculture School | 2015 | Active - Anticipating harvest Dec/Jan | Export | US$21k Funding for labor and 20 agriculture student stipends, organic fertilizer and organic mulch. (Compost heaps are being created around the perimeter for future fertilization) travel, room & board | dōTERRA sponsored 600+ international volunteers to plant the ginger and will be buying the ginger oil when harvested and processed locally. They've invested over US$100k to date. The land requires continuous weeding and clearing. This project creates vast employment opportunities for the community.
Solar-Powered Processing Facility | Student dorm, drying facility and distillery for ginger and other agricultural products | South Manchester (New Forest) | 3000sqft building; 1/4 acre of land | dōTERRA | 2015 | Active - 35% complete | Local & Export | US$8k funding to complete Decking. US$35k to complete the entire building, travel, room & board | This project will create a location for distilation, drying and general product processing. This location will also include a farmers market and dorming quarters which can house up to 24 agriculture students and provide a location for hands-on technical training.
Botanical Garden | Organic Indigenous Garden (Nursery) Student operated | St. Catherine (Above Rocks) | 5 acres |  | 2014 | Active - in the process of building access roads & bridge | Local Farmers - Campaign to Combat Climate Change through Biodiversity - Nursery will provide indigenous suckers for intercropping on all Farm Up Jamaica Farms | US$25k funding for steel to finish the bridge that enables access, travel, room & board | This is a heritage project
Ackee | Organic Ackee orchard Diaspor-owned and Farmer & Student-operated | Westmoreland | 7 acres | Hanover Charities & Trees that Feed | 2015 | Official Launch at 6th Biennial Jamaica Diaspora Conference Day of Service. Pruned, cleared & administered organic herbicides & pesticides | Export | Initial 7 acres - US$25k funding to finish treating trees, to address the issue of Bio-diversity, travel, room & board | US$9k donated by Hanover Charities. This property is on the border of Hanover and will employ the community as well as provide ackee, making it sustainable. Ackees have fungus and require revitalizing and ongoing maintenance. Will be planting new trees & intercropping. Expansion to total 70 acres being assessed.
Ackee Manufacturing | Revitalization of an Ackee factory | Westmoreland | Factory on 5 acres land | Redi-A-Redi Brand Canners. Organic packing and processing facility | 2014 | Actively Exporting | Export. New York Supermarkets. | US$150k Funding for working capital, labor & facility improvements to accommodate organic food processing; this will officially be the 1st organic food processing company in the country. | All Redi-A-Redi, organic canned Ackee will be labeled with the new Farm Up Jamaica's Official Verified Seal
Callaloo Farm | 8k pounds of organic callaloo per week for secured export market | Clarendon (Ebony Park) | 10 acres |  | TBD | Pending |  | US$10k Funding for Labor, 20 agriculture student stipends, assistance for construction of a shade house | Independent Farmer involved requires a loan. He is leasing the land so collateral is an issue. Hoping to arrange a Crop lean vs a Land lean.
Banana | Organic Banana | St. Mary (High Gate) | Test plot 25 acres | Pending Cooperative (50 farmers). | TBD | Pending | Export: Germany | US$75k funding for Labor, agriculture student stipends, irrigation, organic pesticides/herbicides, travel, room & board | Plan to bring in partner in Dominican Republic Banana Co-Op to teach them how to grow organic bananas. Expansion to total 100 acres being assessed.
Bees | Organic honey, goal tohelp a farmer expand 100 boxes to 1000. | Westmoreland | N/A |  | TBD | pending | Local | US$60k funding for expansion, travel, room & board | Can begin once funding is made available
Expansion of Onion Production - Ebony Park Area | Reduce the importation of foreign onions by 300,000lbs per season | Clarendon (Ebony Park) | 15 acres | Pending Cooperative | Estimated for November 2015 | Pending | Local | US$75 Funding for labor, a portion of land clearance, agriculture student stipends, organic seeds & inputs, travel, room & board | Part of the cumulative effort to reduce the excessive onion imports, yearly.
Onion Plantation | 100 acres of Onion | St. Elizabeth | 100 acres | Northern Caribbean University | TBD | Pending | Local | US$600k Funding for Complete infrastructure development, land clearance, solar-powered irrigation, plowing, Seeds, Organic inputs, Labor, agriculture student stipends, farming equipment, travel, room & board | Huge Project with massive opportunity. Live-work farming experience, International & local students & volunteers, good access to water. WILL REDUCE IMPORTATION OF ONIONS BY 20% WITHIN 18 MONTHS.
Garlic Test Plot | 100% imported garlic | St. Elizabeth (Malvern) | 1 acre |  | TBD | Pending | Local | US$5k Funding for land clearance, plowing, irrigation, farming materials, organic biomass and agricultrue student stipends, travel, room & board | This innovsate project will use a warm climate garlic, most garlics are cold climate garlics