# Tech on Wheels Project Report

## Core objective

To build a platform for creating technological foundational skills in day and night school students from underprivileged background and create awareness among them about the information technology sector and  enabling them to choose a career path going forward.

## Partnership Outcomes

| Year | Student Reach (Day) | Student Reach (Night) | No of School / Batches (Day) | No of School / Batches (Night) |
| --- | --- | --- | --- | --- |
| 2018-19 (Oct – Dec) | 297 | 247 | 12 | 10 |

## Course Activities & Outcome –

## The following table indicates the courses/ topics covered under the program

| Particulars | Activities | Outcome(s) |
| --- | --- | --- |
| - Graphic Designing | - Trainer conducted the session as per plan - Students learned 3 different software’s - Corel Draw, Photoshop & Illustrator | - Students are able to make Logo’s, Pamphlets, Visiting Cards & Calendar etc. |
| - Web Designing | - Trainer conducted the session as per plan - Students learned programming languages to make web pages. - HTML & JavaScript. | - Students are able to make their own web pages with programming languages in HTML & JavaScript. |
| - Exposure Visits | - Students got the opportunity to learn advanced graphic designing & web designing. (In tied up with pride computer institute is provided the advance training in Graphic & Web Designing.) | - Students got the opportunity to work on live projects with pride computers. - Participation certificate from the Pride Computer Education to be provided. |

Activities Done

- During the year 2018-19 Masoom has planned to reach approx. 750 students from night & day schools.

- The Tech on Wheels course is being conducted in 12 MCGM run schools where 297 students from IXth grade learned web designing & graphic designing.  This course duration is 30 sessions of 2 hours each session (25 Sessions in practical training and 5 sessions for advance training & exposure visits). The students are then taken for visits to offices and studios to see actual application of their designs.

- Similarly IXth grade students from 10 Night schools (BVM Dahisar & Janata night School etc) are given training in Basic Computer Course & Graphic Designing.  (Ms- Word, Excel, PowerPoint & Internet).The course duration is 16 sessions of three hours each.

- Masoom is in the process of developing its own digital curriculum for Tech on Wheels Project. The purpose of this is to use it in times where the trainer is absent. The student will be shown the live lectures and will not miss any session. This format will also be useful to reinforce training of difficult topics.

Challenges -

| # | Challenges | Intervention at School Level (as of date) |
| --- | --- | --- |
| 1 | Electricity – could not be taken from schools. | - Use of invertor & generator to run the class. |

Way Ahead – Jan – Mar 2019

- Tech on wheel is planning to tie up with more NGO’s & organization to reach more students from underprivileged background. These children will get an opportunity to avail the benefits from the Tech on Wheels Bus.

- We have shortlisted three potential partners interested in tech on wheels project.