## Plan & Budget
Plan & Budget - GlobalGiving
Education Challenges of Adolescent Girls in School
Problem you seek to address | Objective(s) | Activities |  | expected impact |  | Measurement & Indicators | Fund utilisation timeframe
|  |  | US($) | Your beneficiaries
|  |  |  | Direct | Indirect
Poor hygiene practices and environmental issues in schools and the children are not empowered to take remedial measures | To promote best hygiene practices and to empower the school children to take lead role in overcoming the school environmental issues - 100 new schools will be targeted | Formation of the 100 School Hygiene Clubs (SHC) | 0 | 1500 | 15000 | 100 school hygiene clubs are formed in girls schools | 2017-01-01
|  | Developing One SHC manual for school children | 0 | 0 | 0 | Manual for SHC is developed for training | 2017-02-01
|  | Printing of 1,000 SHC Manual | 5000 | 1000 | 5000 | 1,000 copies of SHC manual are printed | 2017-02-01
|  | 40 Training of 500 SHC members on Hygiene Promotion, Environmental issues, Basic life skills and child rights | 7500 | 1000 | 5000 | 1,000 SHC members are trained | 2017-09-01
|  | Activities by SHC to overcome the issues of hygiene and environment. | 0 | 15000 | 70000 | at least 75 schools have improved WASH environment and hygiene messages are spread through peer groups | 2017-12-01
TOTAL |  |  | 12500
Hygiene Promotion and environmental issues are not the concern of teachers in schools. They lack the basic concepts and skills to tackle the situation | To enable the teachers as change agents for WASH in schools | 2-days trainings of teachers will be conducted for 100 teachers from 100 schools on hygiene promotion, environmental issues and children rights. | 1400 | 100 | 15000 | At least 100 teachers have improved knowledge and practices about WASH and children rights | 2017-03-01
TOTAL |  |  | 1400
Issues of growing girls (9-16 years) related to menstrual hygiene and lacking of facilities which will contribute to reduced dropout ratio and quality education. This will be done in 25 girls school | To build the capacity of growing girls on menstrual hygiene management contributing to girls health and education | Training of the growing girls on MHM, low cost sanitary pads production. 40 trainings of 2 days duration will be conducted for 1,000 growing girls (age 9-16) from 100 schools of the targeted areas. the cost will include the transportation of children, their training refreshment, MHM kits material for trainings and stationary required for trainings. | 10000 | 1000 | 5000 | 1000 girls (aging 9-16) are trained on MHM and low cost sanitary pads | 2017-11-01
|  | Construction of 15 girls friendly toilets in girls schools (demo-toilets): The girls friendly toilets will be constructed in 15 schools for demonstration to be adopted by the government in girls schools. These toilets will have the proper system to disposing-off the sanitary pads as well as facility for changing the pads during the menstruation. The cost includes a full toilets construction will all material and accessories. | 22500 | 1500 |  | 15 demo latrienes are constructed benefiting 1,500 girls | 2017-11-01
1,000 girls from different schools will be trained on MHM and making of low cost sanitary napkins while 1,500 girls will be benefited via construction of 15 girls friendly latrines. The average strrength of a girls school is taken as 150 students.
TOTAL |  |  | 32500
The skills of the children at schools are not given a chance to be explored. Their thinking and innovations needs a platform | To advocate the efforts of school children at district level | WASH Exhibition of schools at district level. Two exhibition will be arranged by engagging 200 students from 100 schools. These events are expected to be participated by estimated 1,000 children from other schools of the district. | 1000 | 200 | 1000 | 2 exhibition held participated by 300 students and skills of the students are explored | 2017-09-01
TOTAL |  |  | 1000
GRAND TOTAL |  |  | 47400