## Summary Sheet
Project Budget Vs Actual Expenses Report
VOLUNTEETRS COMMUNITY NEPAL Kattunje -2, Bhaktapur
Prjoect:- School Reconstruction and Health & Sanitation Awareness Program for Earthquake Victims' Relief Support
Amount In NPR( 150NPR=1GBP)
Sources of Fund | Budgeted | Actual Receipt | Budgeted Balance | Actual Balance | Notes for Variation | Application of Fund | Budgeted | Actual | Variation (Excess/Shortage) | Schedule of Actual Expenses
Amount Received for the Project | 1022587 | 1121575 | 98988 | 82775 | Out of NPR 98,988 amount of Rs 16213 used aditionally | Block 1
[6 empty] | ROOFING |  |  |  | SCH_1
[6 empty] | TRUSS‐(12'X19') | 38780.95 | 39110 | 329.05
[6 empty] | 28 GAUGE ROOFING SHEET | 27940 | 28200 | 260
[6 empty] | 9" WALL |  |  |  | SCH_2
[6 empty] | 9" BRICK WALL | 156240 | 159800 | 3560
[6 empty] | OPENINGS |  |  |  | SCH_3
[6 empty] | DOOR | 17000 | 17500 | 500
[6 empty] | WINDOW | 28000 | 27600 | -400
[6 empty] | PCC AND PUNNING |  |  |  | SCH_4
[6 empty] | SOLING+PCC+PUNNING | 14592 | 15200 | 608
[6 empty] | LABOUR |  |  |  | SCH_5
[6 empty] | SKILLED | 16500 | 16500 | 0
[6 empty] | UNSKILLED | 20250 | 25000 | 4750
[6 empty] | Subtotal | 319302.95 | 328910 | 9607.05
Block 2
[6 empty] | ROOFING |  |  |  | SCH_6
[6 empty] | TRUSS‐(12'X36') | 66786.95 | 70150 | 3363.05
[6 empty] | 28 GAUGE G.I. ROOFING SHEET | 51689 | 49500 | -2189
[6 empty] | 9" WALL |  |  |  | SCH_7
[6 empty] | 9" 1ST CLASS BRICK WALL | 272160 | 273620 | 1460
[6 empty] | OPENINGS |  |  |  | SCH_8
[6 empty] | WOODEN PANEL DOOR WOODEN FRAME WINDOW | 17000 | 17800 | 800
[6 empty] | WOODEN FRAME WINDOW | 28000 | 27500 | -500
[6 empty] | PCC AND PUNNING |  |  |  | SCH_9
[6 empty] | SOLING+PCC+PUNNING | 27648 | 29820 | 2172
[6 empty] | LABOUR |  |  |  | SCH_10
[6 empty] | SKILLED | 33000 | 33000 | 0
[6 empty] | UNSKILLED | 27000 | 28500 | 1500
[6 empty] | Subtotal | 523283.95 | 529890 | 6606.05
[6 empty] | Staff Cost | 180000 | 180000 | 0
[6 empty] | Actual Balance in Hand |  | 82775
Total | [5 empty] | Total | 1022586.9 | 1038800 | 16213.1
For Reviewing Main Budget sheet Please Click Below
Main Budget Sheet
Note on B6: Total estimated budget for 2nd Phase Project at Gyan Bikas School
Note on C6: Received in Bank as 2nd installment NPR 968,126 AND NPR 153449 Transferred from 1st Phase Project
Note on E6: Refer Application of Fund end portion

## Schedules of Actual Expenses
Schedules of Actual Expenses
Schedule_1
Roofing
S.No | Particulars |  |  | Amount
TRUSS‐(12'X19')
1 | Purling |  |  | 18720
2 | MS Metal Piping |  |  | 5510
3 | Metal Primer |  |  | 4305
4 | Hilty SS Crew |  |  | 3200
5 | Site Sheet Covering |  |  | 7375
Subtotal |  |  |  | 39110
28 GAUGE ROOFING SHEET
1 | 28 Gauge G.I. Roofing Sheet |  |  | 22000
2 | Roofing Sheet Painting |  |  | 3750
3 | Roofing Sheet SS Crew |  |  | 2450
Subtotal |  |  |  | 28200
Schedule_2
9" Brick Wall
S.No | Particulars |  |  | Amount
1 | Brick 5" |  |  | 30420
2 | Cement,Sand,Grables |  |  | 45240
3 | Metal Framing |  |  | 36120
4 | Cement Board |  |  | 30100
5 | Fall Celling Framing |  |  | 7320
6 | Plastering & Painting |  |  | 10600
Total |  |  |  | 159800
Schedule_3
Openings
S.No | Particulars |  |  | Amount
1 | Door |  |  | 16000
2 | Window |  |  | 25500
3 | Painting & Puttings |  |  | 3600
Total |  |  |  | 45100
Schedule_4
PCC & Punnings
S.No | Particulars |  |  | Amount
1 | Cement |  |  | 8000
2 | Sand |  |  | 2000
3 | Grabbles |  |  | 3500
4 | Stone |  |  | 1700
Total |  |  |  | 15200
Schedule_5
Labour wages
S.No | Particulars | Amount | TDS Expenses( @1%) | Total
1 | Skilled (Mechanic) | 16665 | 165 | 16500
2 | Unskilled ( Helper) | 25250 | 250 | 25000
Total |  |  |  | 41500
Schedule_6
Roofing
S.No | Particulars |  |  | Amount
TRUSS‐(12'X19')
1 | Purling |  |  | 33577
2 | MS Metal Piping |  |  | 9883.0606
3 | Metal Primer |  |  | 7721.7016
4 | Hilty SS Crew |  |  | 5739.7085
5 | Site Sheet Covering |  |  | 13228.2345
Subtotal |  |  |  | 70149.7052
28 GAUGE ROOFING SHEET
1 | 28 Gauge G.I. Roofing Sheet |  |  | 38617.0213
2 | Roofing Sheet Painting |  |  | 6582.4468
3 | Roofing Sheet SS Crew |  |  | 4300.5319
Subtotal |  |  |  | 49500
Schedule_7
9" Brick Wall
S.No | Particulars |  |  | Amount
1 | Brick 5" |  |  | 52087.1114
2 | Cement,Sand,Grables |  |  | 77462.8836
3 | Metal Framing |  |  | 61847.0238
4 | Cement Board |  |  | 51539.1865
5 | Fall Celling Framing |  |  | 12533.7822
6 | Plastering & Painting |  |  | 18150.0125
Total |  |  |  | 273620
Schedule_8
Openings
S.No | Particulars |  |  | Amount
1 | Door |  |  | 17000
2 | Window |  |  | 26000
3 | Painting & Puttings |  |  | 2300
Total |  |  |  | 45300
Schedule_9
PCC & Punnings
S.No | Particulars |  |  | Amount
1 | Cement |  |  | 15694.7368
2 | Sand |  |  | 3923.6842
3 | Grabbles |  |  | 6866.4474
4 | Stone |  |  | 3335.1316
Total |  |  |  | 29820
Schedule_10
Labour wages
S.No | Particulars | Amount | TDS Expenses( @1%) | Total
1 | Skilled (Mechanic) | 33330 | 330 | 33000
2 | Unskilled ( Helper) | 28785 | 285 | 28500
Total |  |  |  | 61500
Schedule_11
Staff Cost
S.No | Particulars | Amount | TDS Expenses( @1%) | Total
1 | Project Coordinator (Full Time) (Salary 25,000 per months for 3 month with TDS Expenses ) | 74250 | 750 | 75000
2 | Construction Coordinator (Full Time)(Salary 20,000 per months for 3 month with TDS Expenses) | 59400 | 600 | 60000
3 | Accountant (Full Time)(Salary 15,000 per months for 3 month with TDS Expenses ) | 44550 | 450 | 45000
Total |  |  |  | 180000
Grand Total |  |  |  | 1038799.7052

## Main Budget Sheet
Prjoect:- School Reconstruction and Health & Sanitation Awareness Program for Earthquake Victims' Relief Support
Please Refer Yellow Highlighted Portion for Phase 2 Report
S.N. | Name of Organisation | Volunteers' Community Nepal
i. | Project Name | School Reconstruction and Health & Sanitation Awareness Program for Earthquake Victims' Relief Support
ii. | Total Cost of Project NPR | 3003895.53
iii. | Total Cost of Project GBP | 20025.9702
150 NRP = 1 GBP
S.N. | ITEM | 2016 | 2017 | Total Cost NRP | Total in GBP |  |  | Notes/Remarks
1 | CAPITAL EXPENDITURE FOR HEALTH AND SANITATION EDUCATION PROGRAM
1.1 | Purchase of one Projector |  | 45000 | 45000 | 300 |  |  | One LCD Porjector
1.2 | Purchase of one Laptop |  | 55000 | 55000 | 366.6667 |  |  | One Laptop for Awereness Programe and Other official purpose
1.3 | Installation of Power Back Up |  | 20000 | 20000 | 133.3333 |  |  | One Power Back for awerness /training class
1.4 | Training Stationaries |  | 50000 | 50000 | 333.3333 |  |  | Includes copy, Pen, Pencils, Chart Papers, Files and others
1.5 | Others |  | 30000 | 30000 | 200 |  |  | Other materials which might required during the awareness period
| Sub-Total 'A' |  | 200000 | 200000 | 1333.3333
2 | CAPITAL AND LABOR EXPENDITURE FOR CONSTRUCTION PROGRAM( Janapremi School)
| Roofing and Covering | 2016 | 2017 | Total Cost NRP | Total in GBP |  |  | 4 Classroom will be Constructed
2.1 | Truss-T1 | 122477.55 |  | 122477.55 | 816.517
2.2 | Truss-T2 | 58325.76 |  | 58325.76 | 388.8384
2.3 | Stair Cover | 30082.32 |  | 30082.32 | 200.5488
2.4 | 28 Gauge G.I. Roofing Sheet | 100496 |  | 100496 | 669.9733
2.5 | 4 MM THK Covering PVC Sheet | 146370 |  | 146370 | 975.8
Labour
2.6 | Skilled | 22000 |  | 22000 | 146.6667
2.7 | Unskilled | 27000 |  | 27000 | 180
| Sub-Total'B' | 506751.63 |  | 506751.63 | 3378.3442
3 | CAPITALAND LABOR EXPENDITURE FOR CONSTRUCTION PROGRAM(Gyanbikash School-Block-1)
| ROOFING |  |  |  |  | Actual Cost | Variation | 1 Program hall/combine learning centre for students in one Block will be constructed
3.1 | TRUSS‐(12'X19') | 38780.95 |  | 38780.95 | 258.5397 | 39110 | -329.05
3.2 | 28 GAUGE ROOFING SHEET | 27940 |  | 27940 | 186.2667 | 28200 | -260
| 9" WALL | [5 empty] | 0
3.3 | 9" BRICK WALL | 156240 |  | 156240 | 1041.6 | 159800 | -3560
| OPENINGS | [5 empty] | 0
3.4 | DOOR | 17000 |  | 17000 | 113.3333 | 17500 | -500
3.5 | WINDOW | 28000 |  | 28000 | 186.6667 | 27600 | 400
| PCC AND PUNNING | [5 empty] | 0
3.6 | SOLING+PCC+PUNNING | 14592 |  | 14592 | 97.28 | 15200 | -608
| LABOUR | [5 empty] | 0
3.7 | SKILLED | 16500 |  | 16500 | 110 | 16500 | 0
3.8 | UNSKILLED | 20250 |  | 20250 | 135 | 25000 | -4750
| Sub-total 'C' | 319302.95 |  | 319302.95 | 2128.6863 | 328910 | -9607.05
4 | CAPITAL EXPENDITURE AND LABOUR FOR CONSTRUCTION PROGRAM( Gyanbikash School-Block-2)
| ROOFING |  |  |  |  | Actual Cost | Variation | 3 Classroom in one Block will be constructed
4.1 | TRUSS‐(12'X36') | 66786.95 |  | 66786.95 | 445.2463 | 70150 | -3363.05
4.2 | 28 GAUGE G.I. ROOFING SHEET | 51689 |  | 51689 | 344.5933 | 49500 | 2189
| 9" WALL | [5 empty] | 0
4.3 | 9" 1ST CLASS BRICK WALL | 272160 |  | 272160 | 1814.4 | 273620 | -1460
| OPENINGS | [5 empty] | 0
4.4 | WOODEN PANEL DOOR WOODEN FRAME WINDOW | 17000 |  | 17000 | 113.3333 | 17800 | -800
4.5 | WOODEN FRAME WINDOW | 28000 |  | 28000 | 186.6667 | 27500 | 500
| PCC AND PUNNING | [5 empty] | 0
4.6 | SOLING+PCC+PUNNING | 27648 |  | 27648 | 184.32 | 29820 | -2172
| LABOUR | [5 empty] | 0
4.7 | SKILLED | 33000 |  | 33000 | 220 | 33000 | 0
4.8 | UNSKILLED | 27000 |  | 27000 | 180 | 28500 | -1500
| Sub-Total'D' | 523283.95 |  | 523283.95 | 3488.5597 | 529890 | -6606.05
5 | CAPITAL EXPENDITURE AND LABOUR FOR CONSTRUCTION PROGRAM( Subarneshwor School)
5.1 | Dismantling of wall | 0 |  | 0 |  |  |  | 3 class will be reconstructed, 8 classroom will undergo maintenance and one toilet completely reconstructed
5.2 | Scrap clearance and transportation | 3915 |  | 3915 | 26.1
| WALL |  |  |  | 0
5.3 | 9" WALL | 288000 |  | 288000 | 1920
| Class Room and Stairs Maintenanc |  |  |  | 0
5.4 | Rectro Mentainence | 44000 |  | 44000 | 293.3333
5.5 | Toilet dismissal and rebuilding | 97000 |  | 97000 | 646.6667
| FINISHING |  |  |  | 0 |  |  | Includes building wall, fitting pipes and panels, plaster and painting
5.6 | Plastering | 26100 |  | 26100 | 174
5.7 | Coloring | 18792 |  | 18792 | 125.28
| LABOUR |  |  |  | 0
5.8 | SKILLED | 33000 |  | 33000 | 220
5.9 | UNSKILLED | 33750 |  | 33750 | 225
| Sub-Total'E' | 544557 |  | 544557 | 3630.38
6 | PROJECT ACTIVITIES
6'E' | Awareness on Health and Sanitaion for 5 Schools | [6 empty] | 1200 students will benefited from the 5 schools
a. | General Health Awareness Program
b. | General Sanitation Awareness Program
c. | General Awareness about Safe drinking water
d. | General Awareness about Waste management training
e. | General Awareness about clean classroom environment training
f. | Video Documentary and Demnostration Program
g. | Full Training Programmes and Expenses (Includes 25,000 each for 5 schools) | 0 | 125000 | 125000 | 833.3333
h. | Trainers Fees ( Includes 25,000 each for 5 schools) | 0 | 125000 | 125000 | 833.3333
| Sub-total 'F" | 0 | 250000 | 250000 | 1666.6667
7 | ALL STAFF COSTS For each staff member please provide job title, location, and % time spent on the project expressed as a full time equivalent (FTE) | [5 empty] | No Variation
7.1 | Project Coordinator (Full Time) (Salary 25,000 per months for 8 month in 2016 and 3 month in 2017) | 200000 | 75000 | 275000 | 1833.3333 | 75000
7.2 | Construction Coordinator (Full Time)(Salary 20,000 per months for 8 month in 2016 and 3 month in 2017) | 1,60,000 | 60000 | 220000 | 1466.6667 | 60000
7.3 | Accountant (Full Time)(Salary 15,000 per months for 8 month in 2016 and 3 month in 2017) | 1,20,000 | 45000 | 165000 | 1100 | 45000
| Sub-total'G' | 200000 | 180000 | 660000 | 4400
8 | OTHER ADMINISTRATION COSTS | [6 empty] | Contribution by Volunteers' Community Nepal
8.1 | Program travel | 0 | 0 | 0 | 0
8.2 | Program communication (phone, internet etc) | 0 | 0 | 0 | 0
8.3 | Logistic, Rent, legel fees and office expenses, meetings | 0 | 0 | 0 | 0
8.4 | Webiste development | 0 | 0 | 0 | 0
| Sub-total'H' | 0 | 0 | 0 | 0
9 | MONITORING, EVALUATION & LESSON LEARNING | 0 | 0 | 0
9.1 | Contribute to prepare Disaster Accountability Tool Kit | 0 | 0 | 0 | 0 |  |  | Contribution by Volunteers' Community Nepal
9.2 | Program Reflection meetings with volunteers and Stakeholders | 0 | 0 | 0 | 0 |  |  | Contribution by Volunteers' Community Nepal
9.3 | Team meetings, field visit | 0 | 0 | 0 | 0 |  |  | Contribution by Volunteers' Community Nepal
| Grant Reporting |  |  | 0 | 0 |  |  | Included in staff costs above
| Sub-total'I' | 0 | 0 | 0 | 0
| Total{Sub-Total(A+B+C+D+E+F+G+H+I) | 2093895.53 | 630000 | 3003895.53 | 20025.9702