## Summary Sheet
Project Budget Vs Actual Expenses Report
VOLUNTEETRS COMMUNITY NEPAL Kattunje -2, Bhaktapur
Prjoect:- School Reconstruction and Health & Sanitation Awareness Program for Earthquake Victims' Relief Support
Amount In NPR
Sources of Fund | Budgeted | Actual Receipt | Variation | Notes for Variation | Application of Fund | Budgeted | Actual | Variation ( Excess/Shortage) | Schedule of Actual Expenses
Amount Received for the Project | 686752 | 862936 | 176184 | Out of 176184 Amount of Rs 22735 used in Current project as excess amount incurred and Rest of Amount Rs 153449 to be used for 2nd phase Projects | Truss-T1 | 122477.55 | 121978.02 | -499.53 | Sch_1
[5 empty] | Truss-T2 | 58325.76 | 57825 | -500.76 | Sch_2
[5 empty] | Stair Cover | 30082.32 | 31082 | 999.68 | Sch_3
[5 empty] | 28 Gauge G.I. Roofing Sheet | 100496 | 97496 | -3000 | Sch_4
[5 empty] | 4 MM THK Covering PVC Sheet | 146370 | 173105.5 | 26735.5 | Sch_5
[5 empty] | Labour |  |  |  | Sch_6
[5 empty] | Skilled | 22000 | 21000 | -1000
[5 empty] | Unskilled | 27000 | 27000 | 0
Project Staff Cost
[5 empty] | Project Coordinator | 75000 | 75000 | 0 | Sch_7
[5 empty] | Construction Coordinator | 60000 | 60000 | 0
[5 empty] | Accountant | 45000 | 45000 | 0
Total | 686752 | 862936 | 176184 |  | Total | 686751.63 | 709486.52 | 22734.89
For Reviewing Main Budget sheet Please Click Below
Main Budget Sheet

## Schedules of Actual Expenses
Schedules of Actual Expenses
Schedule_1
Truss-T1
S.No | Particulars |  |  | Amount
1 | Purling |  |  | 37727
2 | MS Metal Piping |  |  | 25151.02
3 | Metal Primer |  |  | 22325
4 | Hilty SS Crew |  |  | 15290
5 | Site Sheet Covering |  |  | 21485
Total |  |  |  | 121978.02
Schedule_2
Truss-T2
S.No | Particulars |  |  | Amount
1 | Celling Sheet Covering |  |  | 34695
2 | Falls Celling Sheet |  |  | 12721.5
3 | Fall Celling Framing |  |  | 10408.5
Total |  |  |  | 57825
Schedule_3
Stair Cover
S.No | Particulars |  |  | Amount
1 | MS Metal Piping |  |  | 12432.8
2 | Metal Primer |  |  | 3108.2
3 | Water Tank Framing |  |  | 4662.3
4 | G.I. Roofing Sheet |  |  | 10878.7
Total |  |  |  | 31082
Schedule_4
28 Gauge G I Roofing Sheet
S.No | Particulars |  |  | Amount
1 | 28 Gauge G.I. Roofing Sheet |  |  | 82871.6
2 | Roofing Sheet Painting |  |  | 9749.6
3 | Roofing Sheet SS Crew |  |  | 4874.8
Total |  |  |  | 97496
Schedule_5
4 MM Thick Covering PVC Sheet
S.No | Particulars |  |  | Amount
1 | 10 MM Thick Cement Covering Board |  |  | 121235.6
2 | SS Crew |  |  | 5193.15
3 | Metal Framing |  |  | 17311
4 | Metal Primer |  |  | 2000
5 | Wall Putting |  |  | 1400
6 | Wall Painting |  |  | 25965.75
Total |  |  |  | 173105.5
Schedule_6
Labour wages
S.No | Particulars | Amount | TDS Expenses( @1%) | Total
1 | Skilled (Mechanic) | 20790 | 210 | 21000
2 | Unskilled ( Helper) | 26730 | 270 | 27000
Total |  |  |  | 48000
Schedule_7
Staff Cost
S.No | Particulars | Amount | TDS Expenses( @1%) | Total
1 | Project Coordinator (Full Time) (Salary 25,000 per months for 3 month with TDS Expenses ) | 74250 | 750 | 75000
2 | Construction Coordinator (Full Time)(Salary 20,000 per months for 3 month with TDS Expenses) | 59400 | 600 | 60000
3 | Accountant (Full Time)(Salary 15,000 per months for 3 month with TDS Expenses ) | 44550 | 450 | 45000
Total |  |  |  | 180000
Grand Total |  |  |  | 709486.52

## Main Budget Sheet
Prjoect:- School Reconstruction and Health & Sanitation Awareness Program for Earthquake Victims' Relief Support
Please Refer Yellow Highlighted Portion for Phase 1 Report
S.N. | Name of Organisation | Volunteers' Community Nepal
i. | Project Name | School Reconstruction and Health & Sanitation Awareness Program for Earthquake Victims' Relief Support
ii. | Total Cost of Project NPR | 3003895.53
iii. | Total Cost of Project GBP | 20025.9702
150 NRP = 1 GBP
S.N. | ITEM | 2016 | 2017 | Total Cost NRP | Total in GBP |  |  | Notes/Remarks
1 | CAPITAL EXPENDITURE FOR HEALTH AND SANITATION EDUCATION PROGRAM
1.1 | Purchase of one Projector |  | 45000 | 45000 | 300 |  |  | One LCD Porjector
1.2 | Purchase of one Laptop |  | 55000 | 55000 | 366.6667 |  |  | One Laptop for Awereness Programe and Other official purpose
1.3 | Installation of Power Back Up |  | 20000 | 20000 | 133.3333 |  |  | One Power Back for awerness /training class
1.4 | Training Stationaries |  | 50000 | 50000 | 333.3333 |  |  | Includes copy, Pen, Pencils, Chart Papers, Files and others
1.5 | Others |  | 30000 | 30000 | 200 |  |  | Other materials which might required during the awareness period
| Sub-Total 'A' |  | 200000 | 200000 | 1333.3333
2 | CAPITAL AND LABOR EXPENDITURE FOR CONSTRUCTION PROGRAM( Janapremi School)
| Roofing and Covering | 2016 | 2017 | Total Cost NRP | Total in GBP | Actual Cost | Variation | 4 Classroom will be Constructed
2.1 | Truss-T1 | 122477.55 |  | 122477.55 | 816.517 | 121978.02 | -499.53
2.2 | Truss-T2 | 58325.76 |  | 58325.76 | 388.8384 | 57825 | -500.76
2.3 | Stair Cover | 30082.32 |  | 30082.32 | 200.5488 | 31082 | 999.68
2.4 | 28 Gauge G.I. Roofing Sheet | 100496 |  | 100496 | 669.9733 | 97496 | -3000
2.5 | 4 MM THK Covering PVC Sheet | 146370 |  | 146370 | 975.8 | 173105.5 | 26735.5
Labour
2.6 | Skilled | 22000 |  | 22000 | 146.6667 | 21000 | -1000
2.7 | Unskilled | 27000 |  | 27000 | 180 | 27000 | 0
| Sub-Total'B' | 506751.63 |  | 506751.63 | 3378.3442 | 529486.52 | 22734.89
3 | CAPITALAND LABOR EXPENDITURE FOR CONSTRUCTION PROGRAM(Gyanbikash School-Block-1)
| ROOFING | [6 empty] | 1 Program hall/combine learning centre for students in one Block will be constructed
3.1 | TRUSS‐(12'X19') | 38780.95 |  | 38780.95 | 258.5397
3.2 | 28 GAUGE ROOFING SHEET | 27940 |  | 27940 | 186.2667
9" WALL
3.3 | 9" BRICK WALL | 156240 |  | 156240 | 1041.6
OPENINGS
3.4 | DOOR | 17000 |  | 17000 | 113.3333
3.5 | WINDOW | 28000 |  | 28000 | 186.6667
PCC AND PUNNING
3.6 | SOLING+PCC+PUNNING | 14592 |  | 14592 | 97.28
LABOUR
3.7 | SKILLED | 16500 |  | 16500 | 110
3.8 | UNSKILLED | 20250 |  | 20250 | 135
| Sub-total 'C' | 319302.95 |  | 319302.95 | 2128.6863
4 | CAPITAL EXPENDITURE AND LABOUR FOR CONSTRUCTION PROGRAM( Gyanbikash School-Block-2)
| ROOFING | [6 empty] | 3 Classroom in one Block will be constructed
4.1 | TRUSS‐(12'X36') | 66786.95 |  | 66786.95 | 445.2463
4.2 | 28 GAUGE G.I. ROOFING SHEET | 51689 |  | 51689 | 344.5933
9" WALL
4.3 | 9" 1ST CLASS BRICK WALL | 272160 |  | 272160 | 1814.4
OPENINGS
4.4 | WOODEN PANEL DOOR WOODEN FRAME WINDOW | 17000 |  | 17000 | 113.3333
4.5 | WOODEN FRAME WINDOW | 28000 |  | 28000 | 186.6667
PCC AND PUNNING
4.6 | SOLING+PCC+PUNNING | 27648 |  | 27648 | 184.32
LABOUR
4.7 | SKILLED | 33000 |  | 33000 | 220
4.8 | UNSKILLED | 27000 |  | 27000 | 180
| Sub-Total'D' | 523283.95 |  | 523283.95 | 3488.5597
5 | CAPITAL EXPENDITURE AND LABOUR FOR CONSTRUCTION PROGRAM( Subarneshwor School)
5.1 | Dismantling of wall | 0 |  | 0 |  |  |  | 3 class will be reconstructed, 8 classroom will undergo maintenance and one toilet completely reconstructed
5.2 | Scrap clearance and transportation | 3915 |  | 3915 | 26.1
| WALL |  |  |  | 0
5.3 | 9" WALL | 288000 |  | 288000 | 1920
| Class Room and Stairs Maintenanc |  |  |  | 0
5.4 | Rectro Mentainence | 44000 |  | 44000 | 293.3333
5.5 | Toilet dismissal and rebuilding | 97000 |  | 97000 | 646.6667
| FINISHING |  |  |  | 0 |  |  | Includes building wall, fitting pipes and panels, plaster and painting
5.6 | Plastering | 26100 |  | 26100 | 174
5.7 | Coloring | 18792 |  | 18792 | 125.28
| LABOUR |  |  |  | 0
5.8 | SKILLED | 33000 |  | 33000 | 220
5.9 | UNSKILLED | 33750 |  | 33750 | 225
| Sub-Total'E' | 544557 |  | 544557 | 3630.38
6 | PROJECT ACTIVITIES
6'E' | Awareness on Health and Sanitaion for 5 Schools | [6 empty] | 1200 students will benefited from the 5 schools
a. | General Health Awareness Program
b. | General Sanitation Awareness Program
c. | General Awareness about Safe drinking water
d. | General Awareness about Waste management training
e. | General Awareness about clean classroom environment training
f. | Video Documentary and Demnostration Program
g. | Full Training Programmes and Expenses (Includes 25,000 each for 5 schools) | 0 | 125000 | 125000 | 833.3333
h. | Trainers Fees ( Includes 25,000 each for 5 schools) | 0 | 125000 | 125000 | 833.3333
| Sub-total 'F" | 0 | 250000 | 250000 | 1666.6667
7 | ALL STAFF COSTS For each staff member please provide job title, location, and % time spent on the project expressed as a full time equivalent (FTE) | [5 empty] | No Variation
7.1 | Project Coordinator (Full Time) (Salary 25,000 per months for 8 month in 2016 and 3 month in 2017) | 200000 | 75000 | 275000 | 1833.3333 | 75000
7.2 | Construction Coordinator (Full Time)(Salary 20,000 per months for 8 month in 2016 and 3 month in 2017) | 1,60,000 | 60000 | 220000 | 1466.6667 | 60000
7.3 | Accountant (Full Time)(Salary 15,000 per months for 8 month in 2016 and 3 month in 2017) | 1,20,000 | 45000 | 165000 | 1100 | 45000
| Sub-total'G' | 200000 | 180000 | 660000 | 4400
8 | OTHER ADMINISTRATION COSTS | [6 empty] | Contribution by Volunteers' Community Nepal
8.1 | Program travel | 0 | 0 | 0 | 0
8.2 | Program communication (phone, internet etc) | 0 | 0 | 0 | 0
8.3 | Logistic, Rent, legel fees and office expenses, meetings | 0 | 0 | 0 | 0
8.4 | Webiste development | 0 | 0 | 0 | 0
| Sub-total'H' | 0 | 0 | 0 | 0
9 | MONITORING, EVALUATION & LESSON LEARNING | 0 | 0 | 0
9.1 | Contribute to prepare Disaster Accountability Tool Kit | 0 | 0 | 0 | 0 |  |  | Contribution by Volunteers' Community Nepal
9.2 | Program Reflection meetings with volunteers and Stakeholders | 0 | 0 | 0 | 0 |  |  | Contribution by Volunteers' Community Nepal
9.3 | Team meetings, field visit | 0 | 0 | 0 | 0 |  |  | Contribution by Volunteers' Community Nepal
| Grant Reporting |  |  | 0 | 0 |  |  | Included in staff costs above
| Sub-total'I' | 0 | 0 | 0 | 0
| Total{Sub-Total(A+B+C+D+E+F+G+H+I) | 2093895.53 | 630000 | 3003895.53 | 20025.9702