MEDITECH GROUP

RECEADIT

ALL ABOUT YOUR HEALTH

MEDITECH GROUP

CEMADIT

ALL ABOUT YOUR HEALTH

Research Center for Analytic Diagnosis and Imaging Trends (RECEADIT)

School of Health, Biomedical and Computer Sciences (SHBCS)

2016-2017 Academic Year

P.O. Box 19, Belo-Kom, Belo Sub-Division, Boyo Division, Cameroon, North-West Region,

West Africa - Tel: (237) 79 13 91 04

CEMADIT@yahoo.com  http://www.meditech-group.org

Motto:  Health Care Research and Education for Services to Humanity

Ministry of Higher Education                                                          Ministry of Public Health                                       Registration No. 3342 of August 31, 2011                                                           Registration No. 4042 of August 31, 2011

Research Center for Analytic Diagnosis and Imaging Trends (RECEADIT)

School of Health, Biomedical and Computer Sciences (SHBCS) Belo-Kom, Cameroon

Email: CEMADITT@yahoo.com . Website: http://www.meditech-group.org

RECEADIT Community Health Care Services Project at Muteff

1) Project Title: Bringing Health Care Services to the Remote, Rural Community of Muteff

2) URL: http://www.meditech-group.org;  Email: CEMADITT@yahoo.com; ngwainmbijilly@yahoo.com

3) Project Summary

The Muteff Community Health Care Services Project is designed to bring sustained and dependable health care services to our fellow human beings, our brothers and sisters, of the remote, rural community of Muteff  in the Boyo Division in the North-West Region of the Republic of Cameroon, West Africa. Specifically, it will involve the purchasing of a small plot of land and the actual construction of a small Health Care Facility within this Community.

There is simply no health care facility in this community with very difficult and challenging roads and transportation system and sick members of the community, especially the elderly, expecting mothers and infants, have to walk or be transported on Indian bamboo stretchers to where a motor cycle can then transport them to the nearest health care facility twenty to twenty five miles away.

Based on the repeated requests from the members of this community between 2011 and 2013, RECEADIT decided to assist this community with health care services in 2013. RECEADIT rented a small house, employed two community health care workers and set up a community health care facility. However, due to financial difficulties, RECEADIT has not been able to provide these health services consistently and dependably since 2013 and as a result the community health care workers have had to go on for some months with no pay and when the landlord increased the rents in 2014, the health services were moved to a smaller rental facility.

In order to assist members of this Community with sustained and dependable health care services, we shall: 1) purchase a small plot of land; 2) construct a small well-designed Health Care Facility; 3) employ two (one female and one male) well-trained medical personnel (one nurse/midwife and one medical laboratory technician) of this Community who have received their medical training from our School of Health, Biomedical and Computer Sciences (SHBCS); and 4) provide needed basic medical supplies and medication monthly.

4) Requested Funding Amount

$30,000

5) Donations Options

- $30 Will purchase six bags of cement

- $100  Will pay a worker the digging of the foundation

- $200 Will pay a builder for the construction of the foundation

- $300 Will buy the building plot

- $700 Will pay for one trip of stones and one trip of sand

- $1,500 Will pay the builder for the construction and plastering of the walls

- $3,000 Will purchase basic, needed drugs/medication for the Health Care Facility

- $4,000 Will pay for the training of two medical personnel from this Community

Donate using a credit card, payPal, or gift card

We also accept donations by check, mobile phone, wire transfers, money order and more.

6) What is the issue, problem, or challenge?

Many people within Muteff, especially the elderly, expecting mothers  and infants, have no access to basic health care services and many are dying in this remote, difficult-to-reach rural community from very easily treatable illnesses/diseases, such as malaria, infected wounds, cough, childbirth etc. The main problem is sustained and dependable access to medical services. For example, an expecting mother has to walk for over 25 miles in order to gain access to prenatal care and give birth and those who attempt to do so end up losing their lives and the baby. For many of us who are blessed with easily accessible medical care facilities and the ability to afford medical treatment, we do not really realize the seriousness of this problem or challenge until we actually visit these communities and interact with its members about their horrible experiences, as I have been doing over the past four years.

7) How will this project solve this problem?

This project is designed to solve this problem through: 1)  the actual construction of a small Health Care Facility within the Community in Muteff; 2) the training and employment of two medical personnel (one nurse/midwife and one medical laboratory technician) of from this Community; and 3) the purchase of basic, needed drug/medication and medical supplies for the Health Care Facility. This will ensure that members of this Community have sustained, dependable, permanent access to needed health care services. The minimal consultation and treatment fees collected from the patients already treated, whom we expect will be healthy enough to continue their farming activities thanks to our intervention, will be used to pay the salaries of the two health care workers and continue to purchase and supply needed medication and supplies for the Health Care Facility.

8) Potential Long Term Impact

Your donation to this project will: 1) literally save lives; 2) provide medical training and employment for two medical personnel (one nurse/midwife and one medical laboratory technician) from this community; 3) assist in the construction of a permanent, small health care facility in this remote, Community of Muteff; and 4) enable the people of this community to improve and increase their farming productivity. A healthy population ensures increased farming activity, an improved rural economy and much more improved health and life.

9) Project Message

Access to basic health care and treatment in this remote, rural Community is our main goal. Expecting mothers do not have to walk 15 to 25 miles to get prenatal care and to give birth to their baby safely. Together we shall make this dream a reality

Jilly M. Ngwainmbi,  Director, Research Center for Analytic Diagnosis and Imaging Trends (RECEADIT) / School of Health, Biomedical and Computer Sciences (SHBCS).

10) Key Words

RECEADIT;  Muteff Community Health; Health Care; Health Care Workers; Community Worker

11) Additional Documentation

Additional documentation of this project has been provided in a PDF file (Microsoft ward).->Provide exact file name.

12) Primary Photo and Photo Gallery

13) Web Resources

http://www.meditech-group.org

CEMADITT@yahoo.com

Facebook page

Twitter page

14) Organization: Research Center for Analytic Diagnosis and Imaging Trends (RECEADIT)

Belo-Kom, North-West Region, Republic of Cameroon

http://www.meditech-group.org

15) Project Leader

Dr. Jilly M. Ngwainmbi /Dr. Tembon Divine Tende

CEMADIT Clinic

Belo-Kom

15) Where is this Project located?

Muteff, Kom, North-West Region, Republic of Cameroon, West Africa

Dr. Jilly M. Ngwainmbi, President, Board of Directors

Research Center for Analytic Diagnosis and

Imaging Trends Inc. (RECEADIT),

906 Southview Circle

Fayetteville, North Carolina 28311

Tel: (910) 482-3462

Email Address: ngwainmbijilly@yahoo.com