## SCH
TIMELINE OF THE PERMANENT SCHOOL
PROJECT | : PERMANENT SCHOOL
LOCATION | : OUTER ISLAND - INDONESIA
PERIOD | : 160 DAYS
NO. | JENIS PEKERJAAN |  | PERCENTAGE (%) | MOUNTH 1 |  |  |  | MOUNTH 2 |  |  |  | MOUNTH 3 |  |  |  | MOUNTH 4 |  |  |  | SCALE | NOTE
2018
|  |  |  | W - 1 | W- 2 | W - 3 | W - 4 | W - 5 | W - 6 | W - 7 | W- 8 | W - 9 | W- 10 | W - 11 | W - 12 | W - 13 | W - 14 | W - 15 | W - 16
I | CLASS ROOM PER 3 LOCAL | 748203000 | 30.6358 | 2.7851 | 2.7851 | 2.7851 | 2.7851 | 2.7851 | 2.7851 | 2.7851 | 2.7851 | 2.7851 | 2.7851 | 2.7851 | [5 empty] | 100%
II | CLASS ROOM PER 3 LOCAL | 748203000 | 30.6358 |  |  | 2.7851 | 2.7851 | 2.7851 | 2.7851 | 2.7851 | 2.7851 | 2.7851 | 2.7851 | 2.7851 | 2.7851 | 2.7851
50%
III | TEACHER ROOM , TOILET AND HEADMASTER ROOM | 643572000 | 26.3516 |  |  |  | 2.196 | 2.196 | 2.196 | 2.196 | 2.196 | 2.196 | 2.196 | 2.196 | 2.196 | 2.196 | 2.196 | 2.196
IV | LIBRARY ROOM | 302272000 | 12.3768 | 2018 W- 10: 1.7681; 2018 W - 11: 1.7681; 2018 W - 12: 1.7681; 2018 W - 13: 1.7681; 2018 W - 14: 1.7681; 2018 W - 15: 1.7681; 2018 W - 16: 1.7681 | 0%
[22 empty] | 0 | 0
|  | 2442250000 | 100
NOTE : |  | Weekly Plan |  | 2.7851 | 2.7851 | 5.5701 | 7.7661 | 7.7661 | 7.7661 | 7.7661 | 7.7661 | 7.7661 | 9.5342 | 9.5342 | 6.7492 | 6.7492 | 3.9641 | 3.9641 | 1.7681 | 0
| = PLAN | Weekly Cumulative Plan |  | 2.7851 | 5.5701 | 11.1403 | 18.9064 | 26.6725 | 34.4386 | 42.2047 | 49.9709 | 57.737 | 67.2712 | 76.8054 | 83.5546 | 90.3037 | 94.2678 | 98.2319 | 100
| = REALIZATION | Weekly Realization
Weekly Cumulative Plan
Deviation

## RECAPITULATION
BUDGET RECAPITULATION
PROJECT |  | : PERMANENT SCHOOL
LOCATION |  | : OUTER ISLAND - INDONESIA
No. | PROJECT |  |  | TOTAL PRICE | TOTAL PRICE
|  |  |  | (Rp.) | (USD)
I | CLASS ROOM PER 3 LOCAL |  |  | 748203000 | 55422.4444
II | CLASS ROOM PER 3 LOCAL |  |  | 748203000 | 55422.4444
III | TEACHER ROOM , TOILET AND HEADMASTER ROOM |  |  | 643572000 | 47672
IV | LIBRARY ROOM |  |  | 302272000 | 22390.5185
V | MEUBELAIR CLASS AND LIBRARY |  |  | 192610000 | 14267.4074
|  |  | TOTAL | 2634860000 | 195174.8148
|  |  | TOTAL | 2634860000 | 195174.8148
|  |  | ROUNDED OFF | 2634860000 | 195174 | 195174

## LOCAL PER 3 CLASSES
RECAPITULATION BUDGET
LOCAL CLASS ROOM 7M X 8M PER 3 LOCAL
PROJECT |  | : PERMANENT SCHOOL
LOCATION |  | : OUTER ISLAND - INDONESIA
LARGE |  | : 216 M2
No. | PROJECT |  |  |  |  | Total Price | Total Price
[6 empty] | (Rp.) | (USD)
I | PREPARATION |  |  |  |  | 71865501.4 | 5323.3705
II | GROUND AND SAND WORK |  |  |  |  | 23772566.664 | 1760.9309
III | STICKING WORK |  |  |  |  | 168422927.42 | 12475.7724
IV | CONCRETE WORK |  |  |  |  | 99214854.5354 | 7349.2485
V | FLOOR WORK |  |  |  |  | 64090811.4 | 4747.4675
VI | CEILING AND ETERNIT WORK |  |  |  |  | 64426982.4 | 4772.3691
VII | WINDOW WORK |  |  |  |  | 67461234.5491 | 4997.1285
VIII | PAINTING WORK |  |  |  |  | 34017024.096 | 2519.7796
IX | ELECTRICITY WORK |  |  |  |  | 5005000 | 370.7407
X | ROOF AND OTHERS |  |  |  |  | 149926793.896 | 11105.6884
[5 empty] | NOMINAL TOTAL | 748203696.3604 | 55422.496
[5 empty] | TOTAL | 748203696.3604 | 55422.496
[5 empty] | ROUNDED OFF | 748203000 | 55422
DETAIL OF BUDGETING
PROJECT |  | : PERMANENT SCHOOL
LOACTION |  | : OUTER ISLAND - INDONESIA
No. | PROJECT |  | Volume |  | Unit Price | Total Price | Unit Price | Total Price
[5 empty] | (Rp.) | (Rp.) | (USD) | (USD)
I | PREPARATION WORK
1 | Barracks materials and workers |  | 1 | Ls | 3850000 | 3850000 | 285.1852 | 285.1852
2 | Mobilization workers |  | 1 | Ls | 55770000 | 55770000 | 4131.1111 | 4131.1111
3 | Cleaning location |  | 1 | Ls | 4950000 | 4950000 | 366.6667 | 366.6667
4 | Uiset and bowplank |  | 66 | M' | 110537.9 | 7295501.4 | 8.188 | 540.4075
| PANJANG |  | 108 |  | 0 |  | 0 | 0
| LUAS |  | 216
|  | TOTAL OF SUB I MOVED TO RECAPITULATION |  |  |  | 71865501.4 |  | 5323.3705
II | GROUND AND SAND WORK
1 | Excavated lane foundation soil |  | 68.04 | M3 | 56060.4 | 3814349.616 | 4.1526 | 282.5444
2 | Urug pasir bawah pondasi |  | 29.16 | M3 | 159364.7 | 4647074.652 | 11.8048 | 344.2278
3 | Urug tanah kembali |  | 22.68 | M3 | 26869.7 | 609404.796 | 1.9903 | 45.1411
4 | Urugan Tanah |  | 64.8 | M3 | 173757.1 | 11259460.08 | 12.8709 | 834.0341
5 | Urug pasir bawah lantai |  | 21.6 | M3 | 159364.7 | 3442277.52 | 11.8048 | 254.9835
|  | TOTAL OF SUB II MOVED TO RECAPITULATION |  |  |  | 23772566.664 |  | 1760.9309
III | PLESTERANT WORK
1 | Install stone foundation |  | 45.9 | M3 | 881669.8 | 40468643.82 | 65.3089 | 2997.6773
2 | Install bricks |  | 292.38 | M2 | 178748.9 | 52262603.382 | 13.2407 | 3871.304
3 | Plastering walls |  | 668.06 | M2 | 69743.3 | 46592708.998 | 5.1662 | 3451.3118
4 | Plastering angles and sponges |  | 749 | M' | 21741.5 | 16284383.5 | 1.6105 | 1206.2506
5 | Work floor concrete rebates |  | 10.8 | M3 | 1186535.9 | 12814587.72 | 87.8915 | 949.2287
|  | TOTAL OF SUB III MOVED TO RECAPITULATION |  |  |  | 168422927.42 |  | 12475.7724
IV | CONCRETE WORKS
1 | Sloof concrete |  | 3.24 | M3 | 6912113.5336 | 22395247.8489 | 512.0084 | 1658.9072
2 | Concrete column 15/20 |  | 3.57 | M3 | 8779844.26 | 31344044.0082 | 650.3588 | 2321.781
3 | Concrete latei |  | 1.71 | M3 | 7988732.8664 | 13660733.2015 | 591.758 | 1011.9062
4 | Ringbalk concrete 15/20 |  | 3.24 | M3 | 7863668.3664 | 25478285.5071 | 582.494 | 1887.2804
5 | Concrete Beams of Mountains |  | 0.8058 | M3 | 7863668.3664 | 6336543.9696 | 582.494 | 469.3736
|  | TOTAL OF SUB IV MOVED TO RECAPITULATION |  |  |  | 99214854.5354 |  | 7349.2485
V | FLOOR WORK
1 | Ceramic floor tiles 40/40 |  | 216 | M2 | 244132.9 | 52732706.4 | 18.0839 | 3906.1264
2 | Ceramic tile plinthes 10/40 |  | 114 | M1 | 99632.5 | 11358105 | 7.3802 | 841.3411
|  | TOTAL OF SUB V MOVED TO RECAPITULATION |  |  |  | 64090811.4 |  | 4747.4675
VI | CEILING AND ETHERNITE WORK
1 | Plafond gypsum |  | 288 | M2 | 223704.8 | 64426982.4 | 16.5707 | 4772.3691
|  | TOTAL OF SUB VI MOVED TO RECAPITULATION |  |  |  | 64426982.4 |  | 4772.3691
VII | KUZEN INSTALLATION WORK
1 | Wooden Frame |  |  |  | 0
| P2 |  | 0.22248 | M3 | 10132314.5 | 2254237.33 | 750.5418 | 166.9805
| J3 |  | 1.6038 | M3 | 10132314.5 | 16250205.9951 | 750.5418 | 1203.719
2 | Wooden doors and Equipment
| Lintel Door P2 |  | 8.19 | M2 | 2087399.6 | 17095802.724 | 154.6222 | 1266.3558
| Lintel Window |  | 18 | M2 | 1045000 | 18810000 | 77.4074 | 1393.3333
| Rear glass |  | 27.75 | M2 | 164626 | 4568371.5 | 12.1945 | 338.3979
| Sloot pintu |  | 3 | Set | 295869.2 | 887607.6 | 21.9162 | 65.7487
| Door hinges |  | 6 | Set | 90792.9 | 544757.4 | 6.7254 | 40.3524
| Window Hinges |  | 30 | Set | 104660.6 | 3139818 | 7.7526 | 232.5791
| Window latch |  | 30 | Bh | 50582.4 | 1517472 | 3.7468 | 112.4053
| Window holder |  | 60 | Set | 39882.7 | 2392962 | 2.9543 | 177.2564
|  | TOTAL OF SUB VII MOVED TO RECAPITULATION |  |  |  | 67461234.5491 |  | 4997.1285
VIII | PAINTING WORK
1 | Wall paint |  | 668.06 | M2 | 29327.1 | 19592262.426 | 2.1724 | 1451.2787
2 | Special gypsum ceiling paint |  | 288 | M2 | 29327.1 | 8446204.8 | 2.1724 | 625.6448
3 | Wood paint |  | 90.69 | M2 | 65923 | 5978556.87 | 4.8832 | 442.8561
|  | TOTAL OF SUB VIII MOVED TO RECAPITULATION |  |  |  | 34017024.096 |  | 2519.7796
IX | ELECTRICITY WORK
1 | Lamp 18 watt + vitting |  | 12 | Set | 82500 | 990000 | 6.1111 | 73.3333
2 | Electric socket |  | 4 | Point | 38500 | 154000 | 2.8519 | 11.4074
3 | Switch |  | 6 | Point | 38500 | 231000 | 2.8519 | 17.1111
4 | Electrical installation wiring eterna quality |  | 10 | Point | 275000 | 2750000 | 20.3704 | 203.7037
5 | Move the old meter |  | 1 | Set | 550000 | 550000 | 40.7407 | 40.7407
6 | Fuse box |  | 1 | Set | 330000 | 330000 | 24.4444 | 24.4444
|  | TOTAL OF SUB IX MOVED TO RECAPITULATION |  |  |  | 5005000 |  | 370.7407
X | ROOF AND OTHERS
1 | Mild steel frame |  | 316.68 | M2 | 271591.1 | 86007469.548 | 20.1179 | 6370.9237
2 | Multiroof tile |  | 316.68 | M' | 177871.1 | 56328219.948 | 13.1756 | 4172.4607
3 | Multiroof Tile Ridge |  | 26 | M' | 115119.4 | 2993104.4 | 8.5274 | 221.7114
4 | kalsiplang |  | 76 | M' | 60500 | 4598000 | 4.4815 | 340.5926
|  | TOTAL OF SUB X MOVED TO RECAPITULATION |  |  |  | 149926793.896 |  | 11105.6884

## TEACHER'S ROOM, PRINCIPAL...
RECAPITULATION BUDGET
TEACHER'S ROOM, TOILET AND PRINCIPAL OFFICE
PERIOD |  | : PERMANENT SCHOOL
LOCATION |  | : OUTER ISLAND - INDONESIA
LARGE |  | : 144 M2
No. | Project |  |  |  |  | Total Price | Total Price
[6 empty] | (Rp.) | (USD)
I | PREPARATION |  |  |  |  | 57226895 | 4239.0293
II | GROUND AND SAND WORK |  |  |  |  | 18200074.2 | 1348.1536
III | STICKING WORK |  |  |  |  | 157215651.01 | 11645.6038
IV | CONCRETE WORK |  |  |  |  | 96523049.4336 | 7149.8555
V | FLOOR WORK |  |  |  |  | 58493267.25 | 4332.8346
VI | CEILING AND ETERNIT WORK |  |  |  |  | 44740960 | 3314.1452
VII | WINDOW WORK |  |  |  |  | 48662696.9242 | 3604.6442
VIII | PAINTING WORK |  |  |  |  | 30605535.356 | 2267.0767
IX | ELECTRICITY WORK |  |  |  |  | 5797000 | 429.4074
X | SANITATION WORK |  |  |  |  | 21865401.8 | 1619.6594
XI | ROOF AND OTHERS |  |  |  |  | 104242241.928 | 7721.6476
[5 empty] | NOMIINAL TOTAL | 643572772.9017 | 47672.0573
[5 empty] | TOTAL | 643572772.9017 | 47672.0573
[5 empty] | Rounded off | 643572000 | 47672
Detail of Budget
PROJCET |  | : PERMANENT SCHOOL
LOCATION |  | : OUTER ISLAND - INDONESIA
No. | Pekerjaan |  | Volume |  | Unit Price | Total Price | Unit Price | Total Price
[5 empty] | (Rp.) | (Rp.) | (USD) | (USD)
I | PREPARATION WORK
1 | Barracks materials and workers |  | 1 | Ls | 3850000 | 3850000 | 285.1852 | 285.1852
2 | Mobilization workers |  | 1 | Ls | 42900000 | 42900000 | 3177.7778 | 3177.7778
3 | Cleaning location |  | 1 | Ls | 4950000 | 4950000 | 366.6667 | 366.6667
4 | Uiset and bowplank |  | 50 | M' | 110537.9 | 5526895 | 8.188 | 409.3996
| PANJANG |  | 100 |  | 0 |  | 0 | 0
| LUAS |  | 144
|  | TOTAL OF SUB I MOVED TO RECAPITULATION |  |  |  | 57226895 |  | 4239.0293
II | LAND AND SAND WORK
1 | Excavated lane foundation soil |  | 63 | M3 | 56060.4 | 3531805.2 | 4.1526 | 261.6152
2 | Urug pasir bawah pondasi |  | 27 | M3 | 159364.7 | 4302846.9 | 11.8048 | 318.7294
3 | Urug tanah kembali |  | 21 | M3 | 26869.7 | 564263.7 | 1.9903 | 41.7973
4 | Urugan Tanah |  | 43.2 | M3 | 173757.1 | 7506306.72 | 12.8709 | 556.0227
5 | Urug pasir bawah lantai |  | 14.4 | M3 | 159364.7 | 2294851.68 | 11.8048 | 169.989
|  | TOTAL OF SUB II MOVED TO RECAPITULATION |  |  |  | 18200074.2 |  | 1348.1536
III | PLESTERANT WORK
1 | Install stone foundation |  | 42.5 | M3 | 881669.8 | 37470966.5 | 65.3089 | 2775.6271
2 | Install bricks |  | 299.38 | M2 | 178748.9 | 53513845.682 | 13.2407 | 3963.9886
3 | Plastering walls |  | 657.56 | M2 | 69743.3 | 45860404.348 | 5.1662 | 3397.067
4 | Plastering angles and sponges |  | 544 | M' | 21741.5 | 11827376 | 1.6105 | 876.1019
5 | Work floor concrete rebates |  | 7.2 | M3 | 1186535.9 | 8543058.48 | 87.8915 | 632.8191
|  | TOTAL OF SUB III MOVED TO RECAPITULATION |  |  |  | 157215651.01 |  | 11645.6038
IV | CONCRETE WORK
1 | Sloof concrete |  | 3 | M3 | 6912113.5336 | 20736340.6008 | 512.0084 | 1536.0252
2 | Concrete column 15/15 |  | 0.7875 | M3 | 8779844.26 | 6914127.3547 | 650.3588 | 512.1576
3 | Concrete column 15/20 |  | 2.52 | M3 | 8779844.26 | 22125207.5352 | 650.3588 | 1638.9043
4 | Concrete latei |  | 1.89 | M3 | 7988732.8664 | 15098705.1175 | 591.758 | 1118.4226
5 | Ringbalk concrete 15/20 |  | 3 | M3 | 7863668.3664 | 23591005.0992 | 582.494 | 1747.4819
6 | Concrete Beams of Mountains |  | 0.8058 | M3 | 9999582.6832 | 8057663.7261 | 740.7098 | 596.864
|  | TOTAL OF SUB IV MOVED TO RECAPITULATION |  |  |  | 96523049.4336 |  | 7149.8555
V | FLOOR WORK
1 | Ceramic floor tiles 40/40 |  | 133.5 | M2 | 244132.9 | 32591742.15 | 18.0839 | 2414.2031
2 | Ceramic tile plinthes 10/40 |  | 96 | M1 | 99632.5 | 9564720 | 7.3802 | 708.4978
3 | Ceramic wall toilet t :1.5 m |  | 39 | M2 | 334688.2 | 13052839.8 | 24.7917 | 966.877
4 | Ceramic toilet floor |  | 10.5 | M2 | 312758.6 | 3283965.3 | 23.1673 | 243.2567
|  | TOTAL OF SUB V MOVED TO RECAPITULATION |  |  |  | 58493267.25 |  | 4332.8346
VI | CEILING AND ETHERNITE WORK
1 | Plafond gypsum |  | 200 | M2 | 223704.8 | 44740960 | 16.5707 | 3314.1452
|  | TOTAL OF SUB VI MOVED TO RECAPITULATION |  |  |  | 44740960 |  | 3314.1452
VII | KUZEN INSTALLATION WORK
1 | Wooden Frame |  |  |  | 0
| P1 |  | 0.1152 | M3 | 10132314.5 | 1167242.6304 | 750.5418 | 86.4624
| Pkm |  | 0.2232 | M3 | 10132314.5 | 2261532.5964 | 750.5418 | 167.5209
| P2 |  | 0.14832 | M3 | 10132314.5 | 1502824.8866 | 750.5418 | 111.3204
| J3 |  | 0.85536 | M3 | 10132314.5 | 8666776.5307 | 750.5418 | 641.9834
2 | Wooden doors and Equipment
| Lintel Door P1 |  | 3.36 | M2 | 1035309 | 3478638.24 | 76.6896 | 257.6769
| Lintel Door Pkm |  | 6.3 | M2 | 1035309 | 6522446.7 | 76.6896 | 483.1442
| Lintel Door P2 |  | 5.46 | M2 | 1035309 | 5652787.14 | 76.6896 | 418.725
| Lintel Window |  | 9.6 | M2 | 1035309 | 9938966.4 | 76.6896 | 736.2197
| Rear glass |  | 14.8 | M2 | 164626 | 2436464.8 | 12.1945 | 180.4789
| Sloot pintu |  | 8 | Set | 295869.2 | 2366953.6 | 21.9162 | 175.3299
| Door hinges |  | 10 | Set | 90792.9 | 907929 | 6.7254 | 67.254
| Window Hinges |  | 16 | Set | 104660.6 | 1674569.6 | 7.7526 | 124.0422
| Window latch |  | 16 | Bh | 50582.4 | 809318.4 | 3.7468 | 59.9495
| Window holder |  | 32 | Set | 39882.7 | 1276246.4 | 2.9543 | 94.5368
|  | TOTAL OF SUB VII MOVED TO RECAPITULATION |  |  |  | 48662696.9242 |  | 3604.6442
VIII | PAINTING WORK
1 | Wall paint |  | 657.56 | M2 | 29327.1 | 19284327.876 | 2.1724 | 1428.4687
2 | Special gypsum ceiling paint |  | 200 | M2 | 29327.1 | 5865420 | 2.1724 | 434.4756
3 | Wood paint |  | 82.76 | M2 | 65923 | 5455787.48 | 4.8832 | 404.1324
|  | JUMLAH SUB VIII DIPINDAHKAN KE REKAPITULASI |  |  |  | 30605535.356 |  | 2267.0767
IX | ELECTRICITY WORK
1 | Lamp 18 watt + vitting |  | 14 | Set | 82500 | 1155000 | 6.1111 | 85.5556
2 | Electric socket |  | 6 | Point | 38500 | 231000 | 2.8519 | 17.1111
3 | Switch |  | 6 | Point | 38500 | 231000 | 2.8519 | 17.1111
4 | Electrical installation wiring eterna quality |  | 12 | Point | 275000 | 3300000 | 20.3704 | 244.4444
5 | Move the old meter |  | 1 | Set | 550000 | 550000 | 40.7407 | 40.7407
6 | Fuse box |  | 1 | Set | 330000 | 330000 | 24.4444 | 24.4444
|  | TOTAL OF SUB IX MOVED TO RECAPITULATION |  |  |  | 5797000 |  | 429.4074
X | SANITATION WORK
1 | Squat toilet |  | 3 | Unit | 881707.2 | 2645121.6 | 65.3116 | 195.9349
2 | Septiktank |  | 1 | Unit | 5500000 | 5500000 | 407.4074 | 407.4074
3 | Dirty water infiltration well |  | 1 | Unit | 2310000 | 2310000 | 171.1111 | 171.1111
4 | Water reservoir + buffer |  | 1 | Unit | 6380000 | 6380000 | 472.5926 | 472.5926
5 | zimitshu-quality pumping machines |  | 1 | Unit | 825000 | 825000 | 61.1111 | 61.1111
6 | PVC 2,5" dirty water |  | 15 | M' | 102652 | 1539780 | 7.6039 | 114.0578
7 | PVC 1" Clean Water |  | 25 | M' | 70265.8 | 1756645 | 5.2049 | 130.1219
8 | PVC 3/4" Clean Water |  | 4 | M' | 61795.8 | 247183.2 | 4.5775 | 18.3099
9 | Floordrain |  | 4 | Bh | 82507.7 | 330030.8 | 6.1117 | 24.4467
10 | Water faucet |  | 4 | Bh | 82910.3 | 331641.2 | 6.1415 | 24.566
|  | TOTAL OF SUB X MOVED TO RECAPITULATION |  |  |  | 21865401.8 |  | 1619.6594
XI | ROOF AND OTHERS
1 | Mild steel frame |  | 219.24 | M2 | 271591.1 | 59543632.764 | 20.1179 | 4410.6395
2 | Multiroof tile |  | 219.24 | M' | 177871.1 | 38996459.964 | 13.1756 | 2888.6267
3 | Multiroof Tile Ridge |  | 18 | M' | 115119.4 | 2072149.2 | 8.5274 | 153.4925
4 | kalsiplang |  | 60 | M' | 60500 | 3630000 | 4.4815 | 268.8889
|  | TOTAL OF SUB XI MOVED TO RECAPITULATION |  |  |  | 104242241.928 |  | 7721.6476

## LIBRARY
Budget Recapitulation
LIBRARY
PROJECT |  | : PERMANENT SCHOOL
LOACTION |  | : OUTER ISLAND - INDONESIA
LARGE |  | : 64 M2
No. | PROJECT |  |  |  |  | TOTAL PRICE | TOTAL PRICE
[6 empty] | (Rp.) | (USD)
I | PREPARATION |  |  |  |  | 36206137 | 2681.9361
II | GROUND AND SAND WORK |  |  |  |  | 8428123.836 | 624.3055
III | STICKING WORK |  |  |  |  | 70451120.85 | 5218.6015
IV | CONCRETE WORK |  |  |  |  | 43252794.9107 | 3203.9107
V | FLOOR WORK |  |  |  |  | 21363603.8 | 1582.4892
VI | CEILING AND ETERNIT WORK |  |  |  |  | 25949756.8 | 1922.2042
VII | WINDOW WORK |  |  |  |  | 19556724.845 | 1448.6463
VIII | PAINTING WORK |  |  |  |  | 14106704.216 | 1044.9411
IX | ELECTRICITY WORK |  |  |  |  | 2464000 | 182.5185
X | ROOF AND OTHERS |  |  |  |  | 60493689.96 | 4481.0141
[5 empty] | NOMINAL TOTAL | 302272656.2177 | 22390.5671
[5 empty] | TOTAL | 302272656.2177 | 22390.5671
[5 empty] | Rounded Off | 302272000 | 22390
DETAIL OF BUDGET
PERIOD |  | : PERMANENT SCHOOL
LOCATION |  | : OUTER ISLAND - INDONESIA
No. | PROJECT |  | Volume |  | Unit Price | Total Price | Unit Price | Total Price
[5 empty] | (Rp.) | (Rp.) | (USD) | (USD)
I | PREPARATION WORK
1 | Barracks materials and workers |  | 1 | Ls | 3850000 | 3850000 | 285.1852 | 285.1852
2 | Mobilization workers |  | 1 | Ls | 25740000 | 25740000 | 1906.6667 | 1906.6667
3 | Cleaning location |  | 1 | Ls | 3300000 | 3300000 | 244.4444 | 244.4444
4 | Uiset and bowplank |  | 30 | M' | 110537.9 | 3316137 | 8.188 | 245.6398
| PANJANG |  | 42 |  | 0 |  | 0 | 0
| LUAS |  | 72 |  | 0
|  | TOTAL OF SUB I MOVED TO RECAPITULATION |  |  |  | 36206137 |  | 2681.9361
II | LAND AND SAND WORK
1 | Excavated lane foundation soil |  | 26.46 | M3 | 56060.4 | 1483358.184 | 4.1526 | 109.8784
2 | Urug pasir bawah pondasi |  | 11.34 | M3 | 159364.7 | 1807195.698 | 11.8048 | 133.8663
3 | Urug tanah kembali |  | 8.82 | M3 | 26869.7 | 236990.754 | 1.9903 | 17.5549
4 | Urugan Tanah |  | 21.6 | M3 | 173757.1 | 3753153.36 | 12.8709 | 278.0114
5 | Urug pasir bawah lantai |  | 7.2 | M3 | 159364.7 | 1147425.84 | 11.8048 | 84.9945
|  | TOTAL OF SUB II MOVED TO RECAPITULATION |  |  |  | 8428123.836 |  | 624.3055
III | PLESTERANT WORK
1 | Install stone foundation |  | 17.85 | M3 | 881669.8 | 15737805.93 | 65.3089 | 1165.7634
2 | Install bricks |  | 131.38 | M2 | 178748.9 | 23484030.482 | 13.2407 | 1739.5578
3 | Plastering walls |  | 297.06 | M2 | 69743.3 | 20717944.698 | 5.1662 | 1534.6626
4 | Plastering angles and sponges |  | 287 | M' | 21741.5 | 6239810.5 | 1.6105 | 462.2082
5 | Work floor concrete rebates |  | 3.6 | M3 | 1186535.9 | 4271529.24 | 87.8915 | 316.4096
|  | TOTAL OF SUB III MOVED TO RECAPITULATION |  |  |  | 70451120.85 |  | 5218.6015
IV | CONCRETE WORKS
1 | Sloof concrete |  | 1.26 | M3 | 6912113.5336 | 8709263.0523 | 512.0084 | 645.1306
2 | Concrete column 15/20 |  | 1.47 | M3 | 8779844.26 | 12906371.0622 | 650.3588 | 956.0275
3 | Concrete latei |  | 0.675 | M3 | 7988732.8664 | 5392394.6848 | 591.758 | 399.4366
4 | Ringbalk concrete 15/20 |  | 1.26 | M3 | 7863668.3664 | 9908222.1417 | 582.494 | 733.9424
5 | Concrete Beams of Mountains |  | 0.8058 | M3 | 7863668.3664 | 6336543.9696 | 582.494 | 469.3736
|  | TOTAL OF SUB IVMOVED TO RECAPITULATION |  |  |  | 43252794.9107 |  | 3203.9107
V | FLOOR WORK
1 | Ceramic floor tiles 40/40 |  | 72 | M2 | 244132.9 | 17577568.8 | 18.0839 | 1302.0421
2 | Ceramic tile plinthes 10/40 |  | 38 | M1 | 99632.5 | 3786035 | 7.3802 | 280.447
|  | TOTAL OF SUB V MOVED TO RECAPITULATION |  |  |  | 21363603.8 |  | 1582.4892
VI | CEILING AND ETHERNITE WORK
1 | Plafond gypsum |  | 116 | M2 | 223704.8 | 25949756.8 | 16.5707 | 1922.2042
|  | TOTAL OF SUB VI MOVED TO RECAPITULATION |  |  |  | 25949756.8 |  | 1922.2042
VII | KUZEN INSTALLATION WORK
1 | Wooden Frame |  |  |  | 0
| P2 |  | 0.07416 | M3 | 10132314.5 | 751412.4433 | 750.5418 | 55.6602
| J3 |  | 0.5346 | M3 | 10132314.5 | 5416735.3317 | 750.5418 | 401.2397
2 | Wooden doors and accessories
| Lintel Door P2 |  | 2.73 | M2 | 1035309 | 2826393.57 | 76.6896 | 209.3625
| Lintel Window |  | 6 | M2 | 1035309 | 6211854 | 76.6896 | 460.1373
| Rear glass |  | 9.25 | M2 | 164626 | 1522790.5 | 12.1945 | 112.7993
| Sloot pintu |  | 1 | Set | 295869.2 | 295869.2 | 21.9162 | 21.9162
| Door hinges |  | 2 | Set | 90792.9 | 181585.8 | 6.7254 | 13.4508
| Window Hinges |  | 10 | Set | 104660.6 | 1046606 | 7.7526 | 77.5264
| Window latch |  | 10 | Bh | 50582.4 | 505824 | 3.7468 | 37.4684
| Window holder |  | 20 | Set | 39882.7 | 797654 | 2.9543 | 59.0855
|  | TOTAL OF SUB VII MOVED TO RECAPITULATION |  |  |  | 19556724.845 |  | 1448.6463
VIII | PAINTING WORK
1 | Wall paint |  | 297.06 | M2 | 29327.1 | 8711908.326 | 2.1724 | 645.3265
2 | Special gypsum ceiling paint |  | 116 | M2 | 29327.1 | 3401943.6 | 2.1724 | 251.9958
3 | Wood paint |  | 30.23 | M2 | 65923 | 1992852.29 | 4.8832 | 147.6187
|  | TOTAL OF SUB VIII MOVED TO RECAPITULATION |  |  |  | 14106704.216 |  | 1044.9411
IX | ELECTRICITY WORK
1 | Lamp 18 watt + vitting |  | 4 | Set | 82500 | 330000 | 6.1111 | 24.4444
2 | Electric socket |  | 2 | Point | 38500 | 77000 | 2.8519 | 5.7037
3 | Switch |  | 2 | Point | 38500 | 77000 | 2.8519 | 5.7037
4 | Electrical installation wiring eterna quality |  | 4 | Point | 275000 | 1100000 | 20.3704 | 81.4815
5 | Move the old meter |  | 1 | Set | 550000 | 550000 | 40.7407 | 40.7407
6 | Fuse box |  | 1 | Set | 330000 | 330000 | 24.4444 | 24.4444
|  | TOTAL OF SUB IX MOVED TO RECAPITULATION |  |  |  | 2464000 |  | 182.5185
X | ROOF AND OTHERS
1 | Mild steel frame |  | 121.8 | M2 | 271591.1 | 33079795.98 | 20.1179 | 2450.3553
2 | Multiroof tile |  | 121.8 | M' | 177871.1 | 21664699.98 | 13.1756 | 1604.7926
3 | Multiroof Tile Ridge |  | 10 | M' | 115119.4 | 1151194 | 8.5274 | 85.2736
4 | kalsiplang |  | 76 | M' | 60500 | 4598000 | 4.4815 | 340.5926
|  | TOTAL OF SUB X MOVED TO RECAPITULATION |  |  |  | 60493689.96 |  | 4481.0141

## MEUBELAIR
BUDGET RECAPITULATION
MEUBELAIR CLASS AND LIBRARY
PROJECT |  | : PERMANENT SCHOOL
LOCATION |  | : OUTER ISLAND - INDONESIA
No. | Description of Activities |  | Quantity |  |  |  | Unit Price (Rp) | Total (Rp) | Unit Price (USD) | Total USD) | Note
|  |  | Loc | Qty | Frek | Unit
| 1 | MEUBELAIR
|  | CHAIR AND TABLE FOR STUDENT | 1 | 6 | 1 | location/Class/frequent | 23100000 | 138600000 | 1711.1111 | 10266.6667 | 30 student/class
|  | CHAIR AND TABLE FOR TEACHER | 1 | 6 | 1 | location/Class/frequent | 880000 | 5280000 | 65.1852 | 391.1111
|  | WHITEBOARD,MARKER , ERASER | 1 | 6 | 1 | location/Class/frequent | 1155000 | 6930000 | 85.5556 | 513.3333
| 2 | LIBRARY EQUIPMENT (minimalis)
|  | CHAIR AND TABLE FOR SIRCULATION | 1 | 1 | 1 | location/package/frequent | 2200000 | 2200000 | 162.963 | 162.963
|  | TABLE GROUP | 1 | 3 | 1 | location/unit/frequent | 1100000 | 3300000 | 81.4815 | 244.4444
|  | CUPBOARD FOR BOOK | 1 | 8 | 1 | location/unit/frequent | 2200000 | 17600000 | 162.963 | 1303.7037
|  | CHAIR | 1 | 10 | 1 | location/unit/frequent | 220000 | 2200000 | 16.2963 | 162.963
|  | STUDY BOOK PACKAGE | 1 | 6 | 1 | location/package/frequent | 1650000 | 9900000 | 122.2222 | 733.3333
|  | GENERAL BOOK PACKAGE | 1 | 1 | 1 | location/package/frequent | 6600000 | 6600000 | 488.8889 | 488.8889
| BUDGET TOTAL PROGRAM | [6 empty] | 192610000 |  | 14267.4074

## Analysis
DAFTAR ANALISA
1 M3 Entrenchment Land.
0.4 | Man | Worker | @ | Rp. | 109600 | = | Rp. | 43840
0.04 | Man | Foreman | @ | Rp. | 178100 | = | Rp. | 7124 | +
[5 empty] | Total | = | Rp. | 50964
[5 empty] | Total | = | Rp. | 50964
[5 empty] | Rounded off | = | Rp. | 50964
1 M3 Entrenchment Deep soil 2-3 m
1.05 | Man | Worker | @ | Rp. | 109600 | = | Rp. | 115080
0.067 | Man | Foreman | @ | Rp. | 178100 | = | Rp. | 11932.7 | +
[5 empty] | Total | = | Rp. | 127012.7
[5 empty] | Total | = | Rp. | 127012.7
[5 empty] | Rounded off | = | Rp. | 127012.7
1M' Bowplank measurements and pairs
0.012 | m3 | Local wood5/7 | @ | Rp. | 3425000 | = Rp. | Rp. | 41100
0.02 | kg | Nail | @ | Rp. | 27400 | = Rp. | Rp. | 548
0.007 | m3 | Wooden formwork board | @ | Rp. | 4110000 | = Rp. | Rp. | 28770
|  |  |  | Rp. | [6 empty] | 70418
0.1 | Man | Carpenter | @ | Rp. | 164400 | = Rp. | Rp. | 16440
0.01 | Man | Chief carpenter | @ | Rp. | 178100 | = Rp. | Rp. | 1781
0.1 | Man | Worker | @ | Rp. | 109600 | = Rp. | Rp. | 10960
0.005 | Man | Foreman | @ | Rp. | 178100 | = Rp. | Rp. | 890.5
|  |  |  | - |  | - | - | 30071.5 | + |  | 70418 | = | Rp. | 100489.5
|  |  |  | Total | [7 empty] | = | Rp. | 100489.5
|  |  |  | Rounded off | [7 empty] | = | Rp. | 100489
1 M3 Land levelling
0.192 | Man | Worker | @ | Rp. | 109600 | = | Rp. | 21043.2
0.019 | Man | Foreman | @ | Rp. | 178100 | = | Rp. | 3383.9 | +
[5 empty] | Total | = | Rp. | 24427.1
[5 empty] | Total | = | Rp. | 24427.1
[5 empty] | Rounded off | = | Rp. | 24427
1 M3 Mengurug Tanah mendatangkan
1.2 | m3 | Tanah Urug | @ | Rp. | 102750 | = Rp. | Rp. | 123300
0.3 | OH | Worker | @ | Rp. | 109600 | = | Rp. | 32880
0.01 | OH | Foreman | @ | Rp. | 178100 | = | Rp. | 1781
[5 empty] | Total | = | Rp. | 157961
[5 empty] | Total | = | Rp. | 157961
[5 empty] | Rounded off | = | Rp. | 157961
1 M3 Urugan dan Pemadatan tanah
1.2 | m3 | Tanah mendatangkan | @ | Rp. | 102750 | = Rp. | Rp. | 123300
0.0248 | jam | motor grader | @ | Rp. | 260300 | = Rp. |  | 6455.44
0.08 | jam | tandem roller | @ | Rp. | 260300 | = Rp. |  | 20824
0.064 | jam | bulldozer | @ | Rp. | 260300 | = Rp. |  | 16659.2
0.104 | jam | vibrator roller | @ | Rp. | 260300 | = Rp. |  | 27071.2
0.0184 | OH | Foreman | @ | Rp. | 109600 | = Rp. | Rp. | 2016.64
[5 empty] | Total | = | Rp. | 196326.48
[5 empty] | Total | = | Rp. | 196326.48
[5 empty] | Rounded off | = | Rp. | 196326
1 M3 excavated sand.
1.1 | M3 | Excavated sand | @ | Rp. | 102750 |  |  |  | + | Rp. | 113025
0.25 | Org | Worker | @ | Rp. | 109600 | = | Rp. | 27400
0.025 | Org | Foreman | @ | Rp. | 178100 | = | Rp. | 4452.5 | [6 empty] | +
[5 empty] | Total | = | Rp. | 31852.5 | + | Rp. | 113025 | = | Rp. | 144877.5
[5 empty] | Total | [6 empty] | = | Rp. | 144877.5
[5 empty] | Rounded off | [6 empty] | = | Rp. | 144877
1 M3 Install the Split Rock. 1Pc : 5Ps.
1.1 | M3 | Stone Spilt | @ | Rp. | 171250 |  |  |  | + | Rp. | 188375
136 | Kg | Pc | @ | Rp. | 1918 |  |  |  | + | Rp. | 260848
0.544 | M3 | Sand Plug | @ | Rp. | 119875 |  |  |  | + | Rp. | 65212
0.6 | Org | Mason | @ | Rp. | 164400 | = | Rp. | 98640
0.06 | Org | Chief Mason | @ | Rp. | 178100 | = | Rp. | 10686
1.5 | Org | Worker | @ | Rp. | 109600 | = | Rp. | 164400
0.075 | Org | Foreman | @ | Rp. | 178100 | = | Rp. | 13357.5 | [6 empty] | +
[5 empty] | Total | = | Rp. | 287083.5 | + | Rp. | 514435 | = | Rp. | 801518.5
[5 empty] | Total | [6 empty] | = | Rp. | 801518.5
[5 empty] | Rounded off | [6 empty] | = | Rp. | 801518
1 M2 Trasram Bata Camp. 1Pc : 4Ps
70 | Bh | Red brick | @ | Rp. | 1164.5 |  |  |  | + | Rp. | 81515
11.5 | Kg | Pc | @ | Rp. | 1918 |  |  |  | + | Rp. | 22057
0.043 | M3 | Sand Plug | @ | Rp. | 119875 |  |  |  | + | Rp. | 5154.625
0.1 | Org | mason | @ | Rp. | 164400 | = | Rp. | 16440
0.01 | Org | Chief Mason | @ | Rp. | 178100 | = | Rp. | 1781
0.3 | Org | Worker | @ | Rp. | 109600 | = | Rp. | 32880
0.015 | Org | Foreman | @ | Rp. | 178100 | = | Rp. | 2671.5 | [6 empty] | +
[5 empty] | Total | = | Rp. | 53772.5 | + | Rp. | 108726.625 | = | Rp. | 162499.125
[5 empty] | Total | [6 empty] | = | Rp. | 162499.125
[5 empty] | Rounded off | [6 empty] | = | Rp. | 162499
1 M2 Thick Plaster 1,5 Camp. 1Pc : 4Ps
5.2 | Kg | Pc | @ | Rp. | 1918 |  |  |  | + | Rp. | 9973.6
0.02 | M3 | Sand Plug | @ | Rp. | 119875 |  |  |  | + | Rp. | 2397.5
0.15 | Org | Mason | @ | Rp. | 164400 | = | Rp. | 24660
0.015 | Org | Chief Mason | @ | Rp. | 178100 | = | Rp. | 2671.5
0.2 | Org | Worker | @ | Rp. | 109600 | = | Rp. | 21920
0.01 | Org | Foreman | @ | Rp. | 178100 | = | Rp. | 1781 | [6 empty] | +
[5 empty] | Total | = | Rp. | 51032.5 | + | Rp. | 12371.1 | = | Rp. | 63403.6
[5 empty] | Total | [6 empty] | = | Rp. | 63403.6
[5 empty] | Rounded off | [6 empty] | = | Rp. | 63403
1 M2 Corner Plaster / Sponging
1.3 | Kg | Pc | @ | Rp. | 1918 |  |  |  | + | Rp. | 2493.4
0.0042 | M3 | Sand | @ | Rp. | 119875 |  |  |  | + | Rp. | 503.475
0.04 | Org | Mason | @ | Rp. | 164400 | = | Rp. | 6576
0.004 | Org | Chief Mason | @ | Rp. | 178100 | = | Rp. | 712.4
0.08 | Org | Worker | @ | Rp. | 109600 | = | Rp. | 8768
0.004 | Org | Foreman | @ | Rp. | 178100 | = | Rp. | 712.4
[5 empty] | Total | = | Rp. | 16768.8 | + | Rp. | 2996.875 | = | Rp. | 19765.675
[5 empty] | Total | [6 empty] | = | Rp. | 19765.675
[5 empty] | Rounded off | [6 empty] | = | Rp. | 19765
1 M3 Making and installing door / window sills
1.1 | m3 | Local Wood | @ | Rp. | 4110000 |  |  |  | + | Rp. | 4521000
1.25 | kg | Worn nails 80 x 3,8 mm | @ | Rp. | 27400 |  |  |  | + | Rp. | 34250
21 | org | Carpenter | @ | Rp. | 164400 | = | Rp. | 3452400
2.1 | org | Chief carpenter | @ | Rp. | 178100 | = | Rp. | 374010
7 | org | Worker | @ | Rp. | 109600 | = | Rp. | 767200
0.35 | org | Foreman | @ | Rp. | 178100 | = | Rp. | 62335
[5 empty] | Total | = | Rp. | 4655945 | + | Rp. | 4555250 | = | Rp. | 9211195
[5 empty] | Total | [6 empty] | = | Rp. | 9211195
[5 empty] | Rounded off | [6 empty] | = | Rp. | 9211195
1 M2 Windor/door lintel installation
0.064 | m3 | Local Wood | @ | Rp. | 4110000 |  |  |  | + | Rp. | 263040
0.5 | kg | Wood glue (putih) Fox | @ | Rp. | 26030 |  |  |  | + | Rp. | 13015
3 | org | Carpenter | @ | Rp. | 164400 | = | Rp. | 493200
0.3 | org | Chief carpenter | @ | Rp. | 178100 | = | Rp. | 53430
1 | org | Worker | @ | Rp. | 109600 | = | Rp. | 109600
0.05 | org | Foreman | @ | Rp. | 178100 | = | Rp. | 8905
[5 empty] | Total | = | Rp. | 665135 | + | Rp. | 276055 | = | Rp. | 941190
[5 empty] | Total | [6 empty] | = | Rp. | 941190
[5 empty] | Rounded off | [6 empty] | = | Rp. | 941190
1 m' Alumunium door sill installation
1.1 | m1 | Profil alumunium | @ | Rp. | 150700 |  |  |  | + | Rp. | 165770
2 | bh | Fixer couplers | @ | Rp. | 1918 |  |  |  | + | Rp. | 3836
0.06 | tube | Sealent | @ | Rp. | 119875 |  |  |  | + | Rp. | 7192.5
0.043 | org | Aluminumian | @ | Rp. | 164400 | = | Rp. | 7069.2
0.0043 | org | Chief | @ | Rp. | 178100 | = | Rp. | 765.83
0.043 | org | Worker | @ | Rp. | 109600 | = | Rp. | 4712.8
0.0021 | org | Foreman | @ | Rp. | 178100 | = | Rp. | 374.01
[5 empty] | Total | = | Rp. | 12921.84 | + | Rp. | 176798.5 | = | Rp. | 189720.34
[5 empty] | Total | [6 empty] | = | Rp. | 189720.34
[5 empty] | Rounded off | [6 empty] | = | Rp. | 189720
1 m2 Alumunium-framed glass window installation
4.4 | m1 | Aluminum door | @ | Rp. | 150700 |  |  |  | + | Rp. | 663080
4.5 | m1 | Profil Glass | @ | Rp. | 1918 |  |  |  | + | Rp. | 8631
0.27 | tube | Sealent | @ | Rp. | 119875 |  |  |  | + | Rp. | 32366.25
0.085 | org | Aluminumian | @ | Rp. | 164400 | = | Rp. | 13974
0.009 | org | Chief | @ | Rp. | 178100 | = | Rp. | 1602.9
0.085 | org | Worker | @ | Rp. | 109600 | = | Rp. | 9316
0.005 | org | Foreman | @ | Rp. | 178100 | = | Rp. | 890.5
[5 empty] | Total | = | Rp. | 25783.4 | + | Rp. | 704077.25 | = | Rp. | 729860.65
[5 empty] | Total | [6 empty] | = | Rp. | 729860.65
[5 empty] | Rounded off | [6 empty] | = | Rp. | 729860
1 M2Rear glass installation 5 mm
1.1 | m2 | Mirror 5 mm | @ | Rp. | 89050 |  |  |  | + | Rp. | 97955
2.2 | m ' | List of plain wood glass | @ | Rp. | 10275 |  |  |  | + | Rp. | 22605
0.15 | Org | Carpenter | @ | Rp. | 164400 | = | Rp. | 24660
0.015 | Org | Chief carpenter | @ | Rp. | 178100 | = | Rp. | 2671.5
0.015 | Org | Worker | @ | Rp. | 109600 | = | Rp. | 1644
0.0007 | Org | Foreman | @ | Rp. | 178100 | = | Rp. | 124.67
[5 empty] | Total | = | Rp. | 29100.17 | + | Rp. | 120560 | = | Rp. | 149660.17
[5 empty] | Total | [6 empty] | = | Rp. | 149660.17
[5 empty] | Rounded off | [6 empty] | = | Rp. | 149660
Door bolt/latch installation 1 Bh
1 | bh | Sloot key | @ | Rp. | 205500 |  |  |  | + | Rp. | 205500
0.2 | org | Carpenter | @ | Rp. | 164400 |  |  |  | + | Rp. | 57540
0.02 | org | Chief carpenter | @ | Rp. | 178100 | = | Rp. | 3562
0.02 | org | Worker | @ | Rp. | 109600 | = | Rp. | 2192
0.001 | org | Foreman | @ | Rp. | 178100 | = | Rp. | 178.1
[5 empty] | Total | = | Rp. | 5932.1 | + | Rp. | 263040 | = | Rp. | 268972.1
[5 empty] | Total | [6 empty] | = | Rp. | 268972.1
[5 empty] | Rounded off | [6 empty] | = | Rp. | 268972
Door hinge installation 1 Bh
1 | bh | Door hinges | @ | Rp. | 20550 |  |  |  | + | Rp. | 20550
0.15 | org | Carpenter | @ | Rp. | 164400 |  |  |  | + | Rp. | 57540
0.015 | org | Chief carpenter | @ | Rp. | 178100 | = | Rp. | 2671.5
0.015 | org | Worker | @ | Rp. | 109600 | = | Rp. | 1644
0.00075 | org | Foreman | @ | Rp. | 178100 | = | Rp. | 133.575
[5 empty] | Total | = | Rp. | 4449.075 | + | Rp. | 78090 | = | Rp. | 82539.075
[5 empty] | Total | [6 empty] | = | Rp. | 82539.075
[5 empty] | Rounded off | [6 empty] | = | Rp. | 82539
Window hinge installation 1 Bh
1 | bh | Window hinges | @ | Rp. | 17810 |  |  |  | + | Rp. | 17810
0.1 | org | Carpenter | @ | Rp. | 164400 |  |  |  | + | Rp. | 57540
0.1 | org | Chief carpenter | @ | Rp. | 178100 | = | Rp. | 17810
0.01 | org | Worker | @ | Rp. | 109600 | = | Rp. | 1096
0.005 | org | Foreman | @ | Rp. | 178100 | = | Rp. | 890.5
[5 empty] | Total | = | Rp. | 19796.5 | + | Rp. | 75350 | = | Rp. | 95146.5
[5 empty] | Total | [6 empty] | = | Rp. | 95146.5
[5 empty] | Rounded off | [6 empty] | = | Rp. | 95146
Window Latches Installation 1 Bh
1 | Bh | Window Latch | @ | Rp. | 20550 |  |  |  | + | Rp. | 20550
35 | % | Equipment Prices | @ | Rp. | 13700 |  |  |  | + | Rp. | 4795
0.1 | Org | Chief carpenter | @ | Rp. | 178100 | = | Rp. | 17810
0.01 | Org | Carpenter | @ | Rp. | 164400 | = | Rp. | 1644
0.01 | Org | Worker | @ | Rp. | 109600 | = | Rp. | 1096
0.0005 | Org | Foreman | @ | Rp. | 178100 | = | Rp. | 89.05
[5 empty] | Total | = | Rp. | 20639.05 | + | Rp. | 25345 | = | Rp. | 45984.05
[5 empty] | Total | [6 empty] | = | Rp. | 45984.05
[5 empty] | Rounded off | [6 empty] | = | Rp. | 45984
Window holder installattion 1 Bh
1 | Bh | Window holder | @ | Rp. | 20550 |  |  |  | + | Rp. | 20550
35 | % | Equipment Prices | @ | Rp. | 13700 |  |  |  | + | Rp. | 4795
0.05 | Org | Chief carpenter | @ | Rp. | 178100 | = | Rp. | 8905
0.005 | Org | Carpenter | @ | Rp. | 164400 | = | Rp. | 822
0.01 | Org | Worker | @ | Rp. | 109600 | = | Rp. | 1096
0.0005 | Org | Foreman | @ | Rp. | 178100 | = | Rp. | 89.05
[5 empty] | Total | = | Rp. | 10912.05 | + | Rp. | 25345 | = | Rp. | 36257.05
[5 empty] | Total | [6 empty] | = | Rp. | 36257.05
[5 empty] | Rounded off | [6 empty] | = | Rp. | 36257
Window Handles Installation 1 Bh
1 | Bh | Window Handles | @ | Rp. | 20550 |  |  |  | + | Rp. | 20550
35 | % | Equipment Prices | @ | Rp. | 13700 |  |  |  | + | Rp. | 4795
0.05 | Org | Chief carpenter | @ | Rp. | 178100 | = | Rp. | 8905
0.005 | Org | Carpenter | @ | Rp. | 164400 | = | Rp. | 822
0.01 | Org | Worker | @ | Rp. | 109600 | = | Rp. | 1096
0.0005 | Org | Foreman | @ | Rp. | 178100 | = | Rp. | 89.05
[5 empty] | Total | = | Rp. | 10912.05 | + | Rp. | 25345 | = | Rp. | 36257.05
[5 empty] | Total | [6 empty] | = | Rp. | 36257.05
[5 empty] | Rounded off | [6 empty] | = | Rp. | 36257
1 M2 Ceramic flooring installation 40/40
1 | M2 | Ceramics 40 X 40 | @ | Rp. | 95900 |  |  |  | + | Rp. | 95900
4.08 | Kg | Pc | @ | Rp. | 1918 |  |  |  | + | Rp. | 7825.44
0.6 | Kg | Pc Colour | @ | Rp. | 20550 |  |  |  | + | Rp. | 12330
0.009 | M3 | Sand | @ | Rp. | 119875 |  |  |  | + | Rp. | 1078.875
0.25 | Org | mason | @ | Rp. | 164400 | = | Rp. | 41100
0.025 | Org | chief mason | @ | Rp. | 178100 | = | Rp. | 4452.5
0.5 | Org | Worker | @ | Rp. | 109600 | = | Rp. | 54800
0.025 | Org | Foreman | @ | Rp. | 178100 | = | Rp. | 4452.5
[5 empty] | Total | = | Rp. | 104805 | + | Rp. | 117134.315 | = | Rp. | 221939.315
[5 empty] | Total | [6 empty] | = | Rp. | 221939.315
[5 empty] | Rounded off | [6 empty] | = | Rp. | 221939
1 m' Ceramic plint installation size 10 x 40 cm
2.5 | bh | Artistic ceramic plint | @ | Rp. | 23975 |  |  |  | + | Rp. | 59937.5
1.14 | kg | Portland Cement (PC) | @ | Rp. | 1918 |  |  |  | + | Rp. | 2186.52
0.003 | m3 | Sand Plug | @ | Rp. | 119875 |  |  |  | + | Rp. | 359.625
0.05 | kg | Color cement | @ | Rp. | 20550 |  |  |  | + | Rp. | 1027.5
0.09 | org | mason | @ | Rp. | 164400 | = | Rp. | 14796
0.009 | org | Chief | @ | Rp. | 178100 | = | Rp. | 1602.9
0.09 | org | Worker | @ | Rp. | 109600 | = | Rp. | 9864
0.0045 | org | Foreman | @ | Rp. | 178100 | = | Rp. | 801.45
[5 empty] | Total | = | Rp. | 27064.35 | + | Rp. | 63511.145 | = | Rp. | 90575.495
[5 empty] | Total | [6 empty] | = | Rp. | 90575.495
[5 empty] | Rounded off | [6 empty] | = | Rp. | 90575
1 M2 Ceramic flooring installation 30 X 30
1 | M2 | Ceramics 30/30 | @ | Rp. | 82200 |  |  |  | + | Rp. | 82200
10 | kg | Portland Cement (PC) | @ | Rp. | 1918 |  |  |  | + | Rp. | 19180
0.045 | m3 | Sand Plug | @ | Rp. | 119875 |  |  |  | + | Rp. | 5394.375
1.5 | kg | Color cement | @ | Rp. | 20550 |  |  |  | + | Rp. | 30825
0.35 | org | mason | @ | Rp. | 164400 | = | Rp. | 57540
0.035 | org | Chief | @ | Rp. | 178100 | = | Rp. | 6233.5
0.7 | org | Worker | @ | Rp. | 109600 | = | Rp. | 76720
0.035 | org | Foreman | @ | Rp. | 178100 | = | Rp. | 6233.5
[5 empty] | Total | = | Rp. | 146727 | + | Rp. | 137599.375 | = | Rp. | 284326.375
[5 empty] | Total | [6 empty] | = | Rp. | 284326.375
[5 empty] | Rounded off | [6 empty] | = | Rp. | 284326
1 M2 ceramic walls installation 25 X 40
1 | M2 | Ceramics 20 X 25 | @ | Rp. | 123300 |  |  |  | + | Rp. | 123300
4.68 | Kg | Pc | @ | Rp. | 1918 |  |  |  | + | Rp. | 8976.24
1 | Kg | Pc Warna | @ | Rp. | 20550 |  |  |  | + | Rp. | 20550
0.009 | M3 | Sand | @ | Rp. | 119875 |  |  |  | + | Rp. | 1078.875
0.5 | Org | mason | @ | Rp. | 164400 | = | Rp. | 82200
0.05 | Org | Chief | @ | Rp. | 178100 | = | Rp. | 8905
0.5 | Org | Worker | @ | Rp. | 109600 | = | Rp. | 54800
0.025 | Org | Foreman | @ | Rp. | 178100 | = | Rp. | 4452.5
[5 empty] | Total | = | Rp. | 150357.5 | + | Rp. | 153905.115 | = | Rp. | 304262.615
[5 empty] | Total | [6 empty] | = | Rp. | 304262.615
[5 empty] | Rounded off | [6 empty] | = | Rp. | 304262
1 M2 Light-steel roof frame installation
0.1 | Kg | Nail 1/2"-1" | @ | Rp. | 27400 |  |  |  | + | Rp. | 2740
1 | M2 | Light steel | @ | Rp. | 191800 |  |  |  | + | Rp. | 191800
0.145 | Org | Carpenter | @ | Rp. | 164400 | = | Rp. | 23838
0.015 | Org | Chief carpenter | @ | Rp. | 178100 | = | Rp. | 2671.5
0.218 | Org | Worker | @ | Rp. | 109600 | = | Rp. | 23892.8
0.011 | Org | Foreman | @ | Rp. | 178100 | = | Rp. | 1959.1
[5 empty] | Total | = | Rp. | 52361.4 | + | Rp. | 194540 | = | Rp. | 246901.4
[5 empty] | Total | [6 empty] | = | Rp. | 246901.4
[5 empty] | Rounded off | [6 empty] | = | Rp. | 246901
1 M2 roof installation metal zinc type primaroof
1.02 | M2 | Metal tile | @ | Rp. | 109600 |  |  |  | + | Rp. | 111792
0.2 | Kg | Anti-rust nails | @ | Rp. | 47950 |  |  |  | + | Rp. | 9590
0.2 | OH | Worker | @ | Rp. | 109600 | = | Rp. | 21920
0.1 | OH | Carpenter | @ | Rp. | 164400 | = | Rp. | 16440
0.01 | OH | Chief carpenter | @ | Rp. | 178100 | = | Rp. | 1781
0.001 | OH | Foreman | @ | Rp. | 178100 | = | Rp. | 178.1
[5 empty] | Total | = | Rp. | 40319.1 | + | Rp. | 121382 | = | Rp. | 161701.1
[5 empty] | Total | [6 empty] | = | Rp. | 161701.1
[5 empty] | Rounded off | [6 empty] | = | Rp. | 161701
1 M2 Installing metal roof tiles U type primaroof
1.1 | bh | Metal Nok | @ | Rp. | 41100 |  |  |  | + | Rp. | 45210
0.05 | Kg | Anti-rust nails | @ | Rp. | 47950 |  |  |  | + | Rp. | 2397.5
0.25 | OH | Worker | @ | Rp. | 109600 | = | Rp. | 27400
0.15 | OH | Carpenter | @ | Rp. | 164400 | = | Rp. | 24660
0.015 | OH | Chief carpenter | @ | Rp. | 178100 | = | Rp. | 2671.5
0.013 | OH | Foreman | @ | Rp. | 178100 | = | Rp. | 2315.3
[5 empty] | Total | = | Rp. | 57046.8 | + | Rp. | 47607.5 | = | Rp. | 104654.3
[5 empty] | Total | [6 empty] | = | Rp. | 104654.3
[5 empty] | Rounded off | [6 empty] | = | Rp. | 104654
1 m2 Gypsum board ceiling with size (1200 x 2400 x 9) mm
0.364 | lbr | Gypsum board | @ | Rp. | 92475 |  |  |  | + | Rp. | 33660.9
0.11 | kg | Screw nails | @ | Rp. | 47950 |  |  |  | + | Rp. | 5274.5
0.05 | org | Carpenter | @ | Rp. | 164400 | = | Rp. | 8220
0.005 | org | Chief carpenter | @ | Rp. | 178100 | = | Rp. | 890.5
0.1 | org | Worker | @ | Rp. | 109600 | = | Rp. | 10960
0.005 | org | Foreman | @ | Rp. | 178100 | = | Rp. | 20070.5
[5 empty] | Total | = | Rp. | 40141 | + | Rp. | 38935.4 | = | Rp. | 79076.4
[5 empty] | Total | [6 empty] | = | Rp. | 79076.4
[5 empty] | Rounded off | [6 empty] | = | Rp. | 79076
1 m2 Hollow frame ceiling
4.5 | m1 | Hollow pipe | @ | Rp. | 9247.5 |  |  |  | + | Rp. | 41613.75
0.04 | kg | Screw nails | @ | Rp. | 47950 |  |  |  | + | Rp. | 1918
5 | m1 | Wire hanging hollow frame | @ | Rp. | 959 |  |  |  | + | Rp. | 4795
0.32 | org | Carpenter | @ | Rp. | 164400 | = | Rp. | 52608
0.032 | org | Chief carpenter | @ | Rp. | 178100 | = | Rp. | 5699.2
0.14 | org | Worker | @ | Rp. | 109600 | = | Rp. | 15344
0.007 | org | Foreman | @ | Rp. | 178100 | = | Rp. | 73651.2
[5 empty] | Total | = | Rp. | 147302.4 | + | Rp. | 48326.75 | = | Rp. | 195629.15
[5 empty] | Total | [6 empty] | = | Rp. | 195629.15
[5 empty] | Rounded off | [6 empty] | = | Rp. | 195629
1 m2 Thick gypsum board ceiling 9 mm, rangka 60 x 120 kayu lokal
0.013 | m3 | Local Wood | @ | Rp. | 4110000 |  |  |  | + | Rp. | 53430
0.36 | lbr | Gypsum board 9 mm | @ | Rp. | 92475 |  |  |  | + | Rp. | 33291
0.05 | roll | Gypsum gauze | @ | Rp. | 13700 |  |  |  | + | Rp. | 685
0.45 | kg | Gypsum flour | @ | Rp. | 34250 |  |  |  | + | Rp. | 15412.5
0.003 | kg | Alkasit | @ | Rp. | 10960 |  |  |  | + | Rp. | 32.88
0.05 | kg | Gypsum nails | @ | Rp. | 27400 |  |  |  | + | Rp. | 1370
0.12 | kg | Worn nails | @ | Rp. | 27400 |  |  |  | + | Rp. | 3288
0.37 | org | Carpenter | @ | Rp. | 164400 | = | Rp. | 60828
0.037 | org | Chief carpenter | @ | Rp. | 178100 | = | Rp. | 6589.7
0.24 | org | Worker | @ | Rp. | 109600 | = | Rp. | 26304
0.012 | org | Foreman | @ | Rp. | 178100 | = | Rp. | 2137.2
[5 empty] | Total | = | Rp. | 95858.9 | + | Rp. | 107509.38 | = | Rp. | 203368.28
[5 empty] | Total | [6 empty] | = | Rp. | 203368.28
[5 empty] | Rounded off | [6 empty] | = | Rp. | 203368
1 m' Install the wide gypsum cornees profile list 5 - 10 cm
1.1 | m1 | List of cornees gypsum profiles | @ | Rp. | 6576 |  |  |  | + | Rp. | 7233.6
0.875 | kg | Gypsum flour | @ | Rp. | 34250 |  |  |  | + | Rp. | 29968.75
0.0044 | kg | Alkasit | @ | Rp. | 10960 |  |  |  | + | Rp. | 48.224
0.0375 | org | Carpenter | @ | Rp. | 164400 | = | Rp. | 6165
0.0037 | org | Chief carpenter | @ | Rp. | 178100 | = | Rp. | 658.97
0.1125 | org | Worker | @ | Rp. | 109600 | = | Rp. | 12330
0.0065 | org | Foreman | @ | Rp. | 178100 | = | Rp. | 1157.65
[5 empty] | Total | = | Rp. | 20311.62 | + | Rp. | 37250.574 | = | Rp. | 57562.194
[5 empty] | Total | [6 empty] | = | Rp. | 57562.194
[5 empty] | Rounded off | [6 empty] | = | Rp. | 57562
1 M2 New wall painting (1 layer of plamir, 1 layer of base paint, 2 layers of cover paint)
0.1 | kg | Wall Plamir | @ | Rp. | 35072 |  |  |  | + | Rp. | 3507.2
0.1 | kg | Base paint | @ | Rp. | 30140 |  |  |  | + | Rp. | 3014
0.26 | kg | Cover paint 2 x | @ | Rp. | 30140 |  |  |  | + | Rp. | 7836.4
0.063 | org | Painter | @ | Rp. | 137000 | = | Rp. | 8631
0.0063 | org | Chief painter | @ | Rp. | 164400 | = | Rp. | 1035.72
0.02 | org | Worker | @ | Rp. | 109600 | = | Rp. | 2192
0.0025 | org | Foreman | @ | Rp. | 178100 | = | Rp. | 445.25
[5 empty] | Total | = | Rp. | 12303.97 | + | Rp. | 14357.6 | = | Rp. | 26661.57
[5 empty] | Total | [6 empty] | = | Rp. | 26661.57
[5 empty] | Rounded off | [6 empty] | = | Rp. | 26661
1 m2 New wood painting (1 layer of plamir), 1 layer of base paint, 2 layers of cover paint
0.2 | kg | Basic paint in wood | @ | Rp. | 89050 |  |  |  | + | Rp. | 17810
0.15 | kg | Fuji Plamur | @ | Rp. | 52608 |  |  |  | + | Rp. | 7891.2
0.17 | kg | Basic paint in wood | @ | Rp. | 43840 |  |  |  | + | Rp. | 7452.8
0.26 | kg | Cover paint | @ | Rp. | 89050 |  |  |  | + | Rp. | 23153
0.09 | org | Painter | @ | Rp. | 137000 | = | Rp. | 12330
0.006 | org | Chief painter | @ | Rp. | 164400 | = | Rp. | 986.4
0.07 | org | Worker | @ | Rp. | 109600 | = | Rp. | 7672
0.0025 | org | Foreman | @ | Rp. | 178100 | = | Rp. | 445.25
[5 empty] | Total | = | Rp. | 21433.65 | + | Rp. | 38497 | = | Rp. | 59930.65
[5 empty] | Total | [6 empty] | = | Rp. | 59930.65
[5 empty] | Rounded off | [6 empty] | = | Rp. | 59930
1 Bh squat toilet installation
1 | bh | Squat toilet | @ | Rp. | 137000 |  |  |  | + | Rp. | 137000
6 | kg | PC | @ | Rp. | 1918 |  |  |  | + | Rp. | 11508
0.01 | m3 | Sand Plug | @ | Rp. | 119875 |  |  |  | + | Rp. | 1198.75
1.5 | org | Mason | @ | Rp. | 164400 | = | Rp. | 246600
1.5 | org | Chief Mason | @ | Rp. | 178100 | = | Rp. | 267150
1 | org | Worker | @ | Rp. | 109600 | = | Rp. | 109600
0.16 | org | Foreman | @ | Rp. | 178100 | = | Rp. | 28496
[5 empty] | Total | = | Rp. | 651846 | + | Rp. | 149706.75 | = | Rp. | 801552.75
[5 empty] | Total | [6 empty] | = | Rp. | 801552.75
[5 empty] | Rounded off | [6 empty] | = | Rp. | 801552
1 M ' Pipe installation PVC Dia 4 "
1.2 | M' | Pipe PVC 4 " | @ | Rp. | 56512.5 |  |  |  | + | Rp. | 67815
0.35 |  | Pipe Fittings | @ | Rp. | 19779.375 |  |  |  | + | Rp. | 6922.7812
0.135 | Org | Mason | @ | Rp. | 164400 | = | Rp. | 22194
0.0135 | Org | Chief Mason | @ | Rp. | 178100 | = | Rp. | 2404.35
0.081 | Org | Worker | @ | Rp. | 109600 | = | Rp. | 8877.6
0.041 | Org | Foreman | @ | Rp. | 178100 | = | Rp. | 7302.1
[5 empty] | Total | = | Rp. | 40778.05 | + | Rp. | 74737.7812 | = | Rp. | 115515.8312
[5 empty] | Total | [6 empty] | = | Rp. | 115515.8312
[5 empty] | Rounded off | [6 empty] | = | Rp. | 115515
1 M ' Pipe installation PVC Dia 2,5 "
1.2 | M' | Pipe PVC 2,5 " | @ | Rp. | 39730 |  |  |  | + | Rp. | 47676
0.35 |  | Pipe Fittings | @ | Rp. | 13905.5 |  |  |  | + | Rp. | 4866.925
0.135 | Org | Mason | @ | Rp. | 164400 | = | Rp. | 22194
0.0135 | Org | Chief Mason | @ | Rp. | 178100 | = | Rp. | 2404.35
0.081 | Org | Worker | @ | Rp. | 109600 | = | Rp. | 8877.6
0.041 | Org | Foreman | @ | Rp. | 178100 | = | Rp. | 7302.1
[5 empty] | Total | = | Rp. | 40778.05 | + | Rp. | 52542.925 | = | Rp. | 93320.975
[5 empty] | Total | [6 empty] | = | Rp. | 93320.975
[5 empty] | Rounded off | [6 empty] | = | Rp. | 93320
1 M ' Pipe isntallation PVC Dia 1 "
1.2 | M' | Pipe PVC 1 " | @ | Rp. | 17467.5 |  |  |  | + | Rp. | 20961
0.35 |  | Pipe Fittings | @ | Rp. | 6113.625 |  |  |  | + | Rp. | 2139.7687
0.135 | Org | Mason | @ | Rp. | 164400 | = | Rp. | 22194
0.0135 | Org | Chief Mason | @ | Rp. | 178100 | = | Rp. | 2404.35
0.081 | Org | Worker | @ | Rp. | 109600 | = | Rp. | 8877.6
0.041 | Org | Foreman | @ | Rp. | 178100 | = | Rp. | 7302.1
[5 empty] | Total | = | Rp. | 40778.05 | + | Rp. | 23100.7687 | = | Rp. | 63878.8187
[5 empty] | Total | [6 empty] | = | Rp. | 63878.8187
[5 empty] | Rounded off | [6 empty] | = | Rp. | 63878
1 M ' Pipe Installation PVC Dia 3/4 "
1.2 | M' | Pipe PVC 3/4 " | @ | Rp. | 11645 |  |  |  | + | Rp. | 13974
0.35 |  | Pipe Fittings | @ | Rp. | 4075.75 |  |  |  | + | Rp. | 1426.5125
0.135 | Org | Mason | @ | Rp. | 164400 | = | Rp. | 22194
0.0135 | Org | Chief Mason | @ | Rp. | 178100 | = | Rp. | 2404.35
0.081 | Org | Worker | @ | Rp. | 109600 | = | Rp. | 8877.6
0.041 | Org | Foreman | @ | Rp. | 178100 | = | Rp. | 7302.1
[5 empty] | Total | = | Rp. | 40778.05 | + | Rp. | 15400.5125 | = | Rp. | 56178.5625
[5 empty] | Total | [6 empty] | = | Rp. | 56178.5625
[5 empty] | Rounded off | [6 empty] | = | Rp. | 56178
1 Water Faucet Installation
1 | Bh | Water faucet | @ | Rp. | 54800 |  |  |  | + | Rp. | 54800
0.025 | Kg | Seal Tape | @ | Rp. | 14659 |  |  |  | + | Rp. | 366.475
0.1 | Org | Mason | @ | Rp. | 164400 | = | Rp. | 16440
0.01 | Org | Chief Mason | @ | Rp. | 178100 | = | Rp. | 1781
0.01 | Org | Worker | @ | Rp. | 109600 | = | Rp. | 1096
0.005 | Org | Foreman | @ | Rp. | 178100 | = | Rp. | 890.5
[5 empty] | Total | = | Rp. | 20207.5 | + | Rp. | 55166.475 | = | Rp. | 75373.975
[5 empty] | Total | [6 empty] | = | Rp. | 75373.975
[5 empty] | Rounded off | [6 empty] | = | Rp. | 75373
1 Sink water faucets Installation
1 | Bh | Water faucet | @ | Rp. | 287700 |  |  |  | + | Rp. | 287700
0.025 | Kg | Seal Tape | @ | Rp. | 164400 |  |  |  | + | Rp. | 4110
0.1 | Org | Mason | @ | Rp. | 14659 | = | Rp. | 1465.9
0.01 | Org | Chief Mason | @ | Rp. | 164400 | = | Rp. | 1644
0.01 | Org | Worker | @ | Rp. | 178100 | = | Rp. | 1781
0.005 | Org | Foreman | @ | Rp. | 109600 | = | Rp. | 548
[5 empty] | Total | = | Rp. | 5438.9 | + | Rp. | 291810 | = | Rp. | 297248.9
[5 empty] | Total | [6 empty] | = | Rp. | 297248.9
[5 empty] | Rounded off | [6 empty] | = | Rp. | 297248
1 Buah floordrain Installation
1 | Bh | floordrain | @ | Rp. | 54800 |  |  |  | + | Rp. | 54800
0.1 | Org | Mason | @ | Rp. | 164400 | = | Rp. | 16440
0.01 | Org | Chief Mason | @ | Rp. | 178100 | = | Rp. | 1781
0.01 | Org | Worker | @ | Rp. | 109600 | = | Rp. | 1096
0.005 | Org | Foreman | @ | Rp. | 178100 | = | Rp. | 890.5
[5 empty] | Total | = | Rp. | 20207.5 | + | Rp. | 54800 | = | Rp. | 75007.5
[5 empty] | Total | [6 empty] | = | Rp. | 75007.5
[5 empty] | Rounded off | [6 empty] | = | Rp. | 75007
1 m3 quality concrete f’c = 14,5 MPa (K 175), slump (12 ± 2) cm, w/c = 0,66 satuan m3
a. 1 m3 quality concrete f’c = 14,5 MPa (K 175)
326 | kg | Portland Cement (PC) | @ | Rp. | 1918 |  |  |  | + | Rp. | 625268
0.54286 | m3 | Concrete sand | @ | Rp. | 119875 |  |  |  | + | Rp. | 65075
0.76222 | m3 | Split D 1 - 2 cm | @ | Rp. | 411000 |  |  |  | + | Rp. | 313273.3333
1.65 | OH | Worker | @ | Rp. | 109600 | = | Rp. | 180840
0.275 | OH | Mason | @ | Rp. | 164400 | = | Rp. | 45210
0.0275 | OH | Chief Mason | @ | Rp. | 178100 | = | Rp. | 4897.75
0.0825 | OH | Foreman | @ | Rp. | 178100 | = | Rp. | 14693.25 | [6 empty] | +
[5 empty] | Total | = | Rp. | 245641 | + | Rp. | 1003616.3333 | = | Rp. | 1249257.3333
[5 empty] | Total | [6 empty] | = | Rp. | 1249257.3333
[5 empty] | Rounded off | [6 empty] | = | Rp. | 1249257
b. 1 Kg Pembesian Dengan Besi Polos / Ulir
1.05 | Kg | Bone Iron (Proporsional ) | @ | Rp. | 19180 |  |  |  | + | Rp. | 20139
0.015 | Kg | Bendrat. | @ | Rp. | 34250 |  |  |  | + | Rp. | 513.75
0.007 | Org | Blacksmith | @ | Rp. | 164400 | = | Rp. | 1150.8
0.0007 | Org | Chief Blacksmith | @ | Rp. | 164400 | = | Rp. | 115.08
0.007 | Org | Worker | @ | Rp. | 109600 | = | Rp. | 767.2 | [6 empty] | +
0.0003 | Org | Foreman | @ | Rp. | 178100 | = | Rp. | 53.43
[5 empty] | Total | = | Rp. | 2086.51 | + | Rp. | 20652.75 | = | Rp. | 22739.26
[5 empty] | Total | [6 empty] | = | Rp. | 22739.26
[5 empty] | Rounded off | [6 empty] | = | Rp. | 22739
Stutwerk for 1 M3 Iron , High 3 - 4 M ( Using Scalfolding )
32 | Unit | Scalfolding | @ | Rp. | 34250 |  |  |  | + | Rp. | 1096000
3.5 | Org | Carpenter | @ | Rp. | 164400 | = | Rp. | 575400
2.2 | Org | Worker | @ | Rp. | 109600 | = | Rp. | 241120
0.35 | Org | Chief carpenter | @ | Rp. | 178100 | = | Rp. | 62335
0.12 | Org | Foreman | @ | Rp. | 178100 | = | Rp. | 21372
[5 empty] | Total | = | Rp. | 900227 | + | Rp. | 1096000 | = | Rp. | 1996227
[5 empty] | Total | [6 empty] | = | Rp. | 1996227
[5 empty] | Rounded off | [6 empty] | = | Rp. | 1996227
1 M2 Begesting Installation
0.347 | Lbr | Multiplek 9 mm | @ | Rp. | 171250 |  |  |  | + | Rp. | 59423.75
0.017 | M3 | Wood | @ | Rp. | 4795000 |  |  |  | + | Rp. | 81515
0.4 | Kg | Nails | @ | Rp. | 27400 |  |  |  | + | Rp. | 10960
0.5 | Org | Carpenter | @ | Rp. | 164400 | = | Rp. | 82200
0.2 | Org | Worker | @ | Rp. | 109600 | = | Rp. | 21920
0.05 | Org | Chief carpenter | @ | Rp. | 178100 | = | Rp. | 8905
0.01 | Org | Foreman | @ | Rp. | 178100 | = | Rp. | 1781 | [6 empty] | +
[5 empty] | Total | = | Rp. | 114806 | + | Rp. | 151898.75 | = | Rp. | 266704.75
[5 empty] | Total | [6 empty] | = | Rp. | 266704.75
[5 empty] | Rounded off | [6 empty] | = | Rp. | 266704
d. Unloading Cast.
4 | Worker |  | @ | Rp. | 109600 | = | Rp. | 438400 | +
[5 empty] | Total | = | Rp. | 438400
[5 empty] | Total | = | Rp. | 438400
[5 empty] | Rounded off | = | Rp. | 438400
1 M3 Reinforced Concrete For Food plat Camp. 1 Pc : 2Ps : 3Split.
a. Concrete K175 |  |  | 1 | M3 | 1249257 | = | Rp. | 1249257
b. Bone Iron |  |  | 125 | Kg | 22739 | = | Rp. | 2842375
c. Begesting |  |  |  | M2 | 266704 | = | Rp. | 0
d. Unloading Cast. |  |  | 1 | Ls | 438400 | = | Rp. | 438400
[5 empty] | Total | = | Rp. | 4530032
1 M3 Reinforced Concrete ForSloof 15/20 Camp. 1 Pc : 2Ps : 3Split.
a. Concrete K175 |  |  | 1 | M3 | 1249257 | = | Rp. | 1249257
b. Bone Iron |  |  | 150 | Kg | 22739 | = | Rp. | 3410850
c. Begesting |  |  | 4.444 | M2 | 266704 | = | Rp. | 1185232.576
d. Unloading Cast. |  |  | 1 | Ls | 438400 | = | Rp. | 438400
[5 empty] | Total | = | Rp. | 6283739.576
1 M3 Reinforced Concrete For practical column12/12 Camp. 1 Pc : 2Ps : 3Split. | [7 empty] | 0
a. Concrete K175 |  |  | 1 | M3 | 1249257 | = | Rp. | 1249257
b. Bone Iron |  |  | 190 | Kg | 22739 | = | Rp. | 4320410
c. Begesting |  |  | 7.4 | M2 | 266704 | = | Rp. | 1973609.6
d. Unloading Cast. |  |  | 1 | Ls | 438400 | = | Rp. | 438400
[5 empty] | Total | = | Rp. | 7981676.6
1 M3 Reinforced Concrete For Colum 30/30 Camp. 1 Pc : 2Ps : 3Split.
a. Concrete K175 |  |  | 1 | M3 | 1249257 | = | Rp. | 1249257
b. Bone Iron |  |  | 150 | Kg | 22739 | = | Rp. | 3410850
c. Scalfolding |  |  | 1 | Unt | 1996227 | = | Rp. | 1996227
c. Begesting |  |  | 5.92 | M2 | 266704 | = | Rp. | 1578887.68
d. Unloading Cast. |  |  | 1 | Ls | 438400 | = | Rp. | 438400
[5 empty] | Total | = | Rp. | 8673621.68
1 M3Reinforced Concrete For Beams 12/20 Camp. 1 Pc : 2Ps : 3Split.
a. Concrete K175 |  |  | 1 | M3 | 1249257 | = | Rp. | 1249257
b. Bone Iron |  |  | 175 | Kg | 22739 | = | Rp. | 3979325
c. Begesting |  |  | 5.556 | M2 | 266704 | = | Rp. | 1481807.424
d. Unloading Cast. |  |  | 1 | Ls | 438400 | = | Rp. | 438400
[5 empty] | Total | = | Rp. | 7148789.424
1 M3 Reinforced Concrete For Beams 12/30 Camp. 1 Pc : 2Ps : 3Split.
a. Concrete K175 |  |  | 1 | M3 | 1249257 | = | Rp. | 1249257
b. Bone Iron |  |  | 170 | Kg | 22739 | = | Rp. | 3865630
c. Scalfolding |  |  | 1 | Unt | 1996227 | = | Rp. | 1996227
c. Begesting |  |  | 5.778 | M2 | 266704 | = | Rp. | 1541015.712
d. Unloading Cast. |  |  | 1 | Ls | 438400 | = | Rp. | 438400
[5 empty] | Total | = | Rp. | 9090529.712
1 M3 Reinforced Concrete For Trucks Beams 12/15 Camp. 1 Pc : 2Ps : 3Split.
a. Concrete K175 |  |  | 1 | M3 | 1249257 | = | Rp. | 1249257
b. Bone Iron |  |  | 180 | Kg | 22739 | = | Rp. | 4093020
c. Begesting |  |  | 5.556 | M2 | 266704 | = | Rp. | 1481807.424
d. Unloading Cast. |  |  | 1 | Ls | 438400 | = | Rp. | 438400
[5 empty] | Total | = |  | 7262484.424
1 M3 Reinforced Concrete For Thick Plates 5 Cm Camp. 1 Pc : 2Ps : 3Split.
a. Concrete K175 |  |  | 1 | M3 | 1249257 | = | Rp. | 1249257
b. Bone Iron |  |  | 50 | Kg | 22739 | = | Rp. | 1136950
c. Begesting |  |  | 6.667 | M2 | 266704 | = | Rp. | 1778115.568
d. Unloading Cast. |  |  | 1 | Ls | 438400 | = | Rp. | 438400
[5 empty] | Total | = | Rp. | 4602722.568
1 M3 Reinforced Concrete For Thick Plates 10 Cm Camp. 1 Pc : 2Ps : 3Split.
a. Concrete K175 |  |  | 1 | M3 | 1249257 | = | Rp. | 1249257
b. Bone Iron |  |  | 115 | Kg | 22739 | = | Rp. | 2614985
c. Scalfolding |  |  | 1 | Unt | 1996227 | = | Rp. | 1996227
c. Begesting |  |  | 6.667 | M2 | 266704 | = | Rp. | 1778115.568
d. Unloading Cast. |  |  | 1 | Ls | 438400 | = | Rp. | 438400
[5 empty] | Total | = | Rp. | 8076984.568
Analys G.33a : 1 M3Mashed Concrete Camp. 1 : 3 : 5.
218 | Kg | PC | @ | Rp. | 1918 |  |  |  | + | Rp. | 418124
0.52 | M2 | Pasir Pasang | @ | Rp. | 119875 |  |  |  | + | Rp. | 62335
0.87 | M3 | Split 2/3 Cm. | @ | Rp. | 411000 |  |  |  | + | Rp. | 357570
1.65 | Worker |  | @ | Rp. | 109600 | = | Rp. | 180840
0.08 | Foreman |  | @ | Rp. | 178100 | = | Rp. | 14248
0.25 | Mason |  | @ | Rp. | 164400 | = | Rp. | 41100
0.025 | Chief Mason |  | @ | Rp. | 178100 | = | Rp. | 4452.5 | [6 empty] | +
[5 empty] | Total | = | Rp. | 240640.5 | + | Rp. | 838029 | = | Rp. | 1078669.5
[5 empty] | Total | [6 empty] | = | Rp. | 1078669.5
[5 empty] | Rounded off | [6 empty] | = | Rp. | 1078669

## Unit Price
LIST OF BUILDING MATERIALS PRICE LIST
37
NO. | TYPES OF BUILDING MATERIALS |  | Unit | Price
(Rp.)
A. |  | ADHESIVE MATERIALS
1 |  | PC. ( Portland Cement) | Zak | 95900 | 70000 | 37 | 25900
2 |  | PC. Colour | Kg | 20550 | 15000 | 37 | 5550
3 |  | PC. Holcim | Kg | 1918 | 1400 | 37 | 518
|  |  |  | 0 |  | 37 | 0
B. |  | NATURAL STONE AND AGGREGATE |  | 0 |  | 37 | 0
1 |  | Pasir Pasang | M3 | 119875 | 87500 | 37 | 32375
2 |  | Pasir Urug. | M3 | 102750 | 75000 | 37 | 27750
3 |  | Stone Split ( Split ) 2/3 cm. | M3 | 411000 | 300000 | 37 | 111000
4 |  | Split Rock | M3 | 171250 | 125000 | 37 | 46250
5 |  | Tanah Urug | M3 | 102750 | 75000 | 37 | 27750
|  |  |  | 0 |  | 37 | 0
C. |  | CERAMIC MATERIALS. |  | 0 |  | 37 | 0
1 |  | Ceramic 40 X 40 | M2 | 95900 | 70000 | 37 | 25900
2 |  | Ceramic 30 X 30 | M2 | 82200 | 60000 | 37 | 22200
3 |  | Ceramic 25 X 40 | M2 | 123300 | 90000 | 37 | 33300
4 |  | Red brick | Bh | 1164.5 | 850 | 37 | 314.5
|  |  |  | 0 |  | 37 | 0
D |  | IRON AND ALLUMINUM. |  | 0 |  | 37 | 0
1 |  | Rebar | Kg | 19180 | 14000 | 37 | 5180
2 |  | Bendrat Iron. | Kg | 34250 | 25000 | 37 | 9250
3 |  | Nail | Kg | 27400 | 20000 | 37 | 7400
4 |  | Anti-rust nails | Kg | 47950 | 35000 | 37 | 12950
5 |  | Angkur Iron | kg | 21920 | 16000 | 37 | 5920
6 |  | Concrete steel screw | kg | 23153 | 16900 | 37 | 6253
7 |  | Thick iron strip 5mm | kg | 24660 | 18000 | 37 | 6660
8 |  | Alluminium door | M2 | 363050 | 265000 | 37 | 98050
9 |  | Light steel | M2 | 191800 | 140000 | 37 | 51800
10 |  | Alluminium | M' | 150700 | 110000 | 37 | 40700
11 |  | Mutiroof roof tile | M2 | 109600 | 80000 | 37 | 29600
12 |  | Multiroof tile roofs | M' | 41100 | 30000 | 37 | 11100
13 |  | Hollow pipe | M' | 9247.5 | 6750 | 37 | 2497.5
14 |  | Hanging wire | M' | 959 | 700 | 37 | 259
|  |  |  | 0 |  | 37 | 0
G |  | WOOD AND BAMBOO MATERIALS |  | 0 |  | 37 | 0
1 |  | Wood beams | m3 | 4795000 | 3500000 | 37 | 1295000
2 |  | Kaso-kaso (5x7)cm Glugu | m3 | 3425000 | 2500000 | 37 | 925000
3 |  | Kaso-kaso (5x7)cm Kayu Lokal | m' | 11987.5 | 8750 | 37 | 3237.5
4 |  | Local Beams | m3 | 4110000 | 3000000 | 37 | 1110000
5 |  | Dolken wood Ø 8 - 10/400 cm | btg | 106860 | 78000 | 37 | 28860
6 |  | Wood Begesting Class III | m3 | 3425000 | 2500000 | 37 | 925000
7 |  | Local board wood | m3 | 4110000 | 3000000 | 37 | 1110000
8 |  | Siding plank | M' | 34250 | 25000 | 37 | 9250
9 |  | Lath wood (2x3 )cm Lokal | m3 | 4110000 | 3000000 | 37 | 1110000
10 |  | Plywood tebal 9 mm | lbr | 171250 | 125000 | 37 | 46250
11 |  | List of plain wood glass | m' | 10275 | 7500 | 37 | 2775
12 |  | Gypsumboard | lbr | 92475 | 67500 | 37 | 24975
13 |  | Gauze | roll | 13700 | 10000 | 37 | 3700
14 |  | Gypsum flour | kg | 34250 | 25000 | 37 | 9250
15 |  | Alkasit | kg | 10960 | 8000 | 37 | 2960
16 |  | List gypsum | m' | 6576 | 4800 | 37 | 1776
17 |  | Multiplex 9 mm | Lbr | 171250 | 125000 | 37 | 46250
18 |  | Wood Begesting / Cast Boards. | M3 | 4110000 | 3000000 | 37 | 1110000
19 |  | Schafolding | Unit | 34250 | 25000 | 37 | 9250
20 |  | Wood glue | Kg | 26030 | 19000 | 37 | 7030
21 |  | Glass 5 mm | M2 | 89050 | 65000 | 37 | 24050
22 |  | Slot Pintu | Bh | 205500 | 150000 | 37 | 55500
23 |  | Equipment | Bh | 13700 | 10000 | 37 | 3700
24 |  | Door hinges | Bh | 20550 | 15000 | 37 | 5550
25 |  | Window hinges | Bh | 17810 | 13000 | 37 | 4810
26 |  | Door latch | Bh | 20550 | 15000 | 37 | 5550
27 |  | window latch | Bh | 20550 | 15000 | 37 | 5550
28 |  | Window holder hooks | Bh | 20550 | 15000 | 37 | 5550
29 |  | Window Handle | Bh | 20550 | 15000 | 37 | 5550
|  |  |  | 0 |  | 37 | 0
|  | PAINT MATERIALS |  | 0 |  | 37 | 0
1 |  | Wall paint | Kg | 30140 | 22000 | 37 | 8140
2 |  | Wood paint | Kg | 89050 | 65000 | 37 | 24050
3 |  | Meni Paint | Kg | 43840 | 32000 | 37 | 11840
4 |  | Natural stone coating | Kg | 71240 | 52000 | 37 | 19240
5 |  | Wood filler | Kg | 52608 | 38400 | 37 | 14208
6 |  | Wall filler | Kg | 35072 | 25600 | 37 | 9472
7 |  | Sandpaper | Lbr | 4110 | 3000 | 37 | 1110
8 |  | Paintbrush roll | Bh | 52608 | 38400 | 37 | 14208
9 |  | Brush | Bh | 26304 | 19200 | 37 | 7104
|  |  |  | 0 |  | 37 | 0
|  | SANITATION MATERIALS |  | 0 |  | 37 | 0
1 |  | Pipa PVC Wavin Dia. 4 " sekualitas | M ' | 56512.5 | 41250 | 37 | 15262.5
2 |  | Pipa PVC Wavin Dia. 2,5 " sekualitas | M ' | 39730 | 29000 | 37 | 10730
3 |  | Pipa PVC Wavin Dia. 1 " sekualitas | M ' | 17467.5 | 12750 | 37 | 4717.5
4 |  | Pipa PVC Wavin Dia. 3 / 4 " sekualitas | M ' | 11645 | 8500 | 37 | 3145
5 |  | Squat toilet | Bh | 137000 | 100000 | 37 | 37000
6 |  | Floordrain | Bh | 54800 | 40000 | 37 | 14800
7 |  | Garden faucet and ablution area | Bh | 54800 | 40000 | 37 | 14800
8 |  | Sink water faucets | Bh | 287700 | 210000 | 37 | 77700
9 |  | INA quality sink | Bh | 822000 | 600000 | 37 | 222000
10 |  | Dishes container | Bh | 479500 | 350000 | 37 | 129500
11 |  | Asesories | set | 34250 | 25000 | 37 | 9250
12 |  | Sealtape | kg | 14659 | 10700 | 37 | 3959
|  |  |  | 0 |  | 37 | 0
|  | RENT TOOL |  | 0 |  | 37 | 0
1 |  | Motor grader | Ours | 260300 | 190000 | 37 | 70300
2 |  | tandem roller | Ours | 260300 | 190000 | 37 | 70300
3 |  | bulldozer | Ours | 260300 | 190000 | 37 | 70300
4 |  | vibrator roller | Ours | 260300 | 190000 | 37 | 70300
[6 empty] | 37 | 0
[6 empty] | 37 | 0
[6 empty] | 37 | 0
LIST OF WAGES | [5 empty] | 37 | 0
[6 empty] | 37 | 0
NO. | TYPES OF BUILDING MATERIALS |  | Unit | Price |  | 37 | 0
|  |  |  | (Rp.) |  | 37 | 0
[6 empty] | 37 | 0
1 |  | Foreman | / day | 178100 | 130000 | 37 | 48100
2 |  | Chief Carpenter | / day | 178100 | 130000 | 37 | 48100
3 |  | Carpenter | / day | 164400 | 120000 | 37 | 44400
4 |  | Kepala Tukang Batu | / day | 178100 | 130000 | 37 | 48100
5 |  | Mason | / day | 164400 | 120000 | 37 | 44400
6 |  | Chief Mason | / day | 164400 | 120000 | 37 | 44400
7 |  | Blacksmith | / day | 164400 | 120000 | 37 | 44400
8 |  | Chief Painter | / day | 164400 | 120000 | 37 | 44400
9 |  | Painter | / day | 137000 | 100000 | 37 | 37000
10 |  | Chief Alluminium Artisan | / day | 164400 | 120000 | 37 | 44400
11 |  | Alluminiumian | / day | 137000 | 100000 | 37 | 37000
10 |  | Worker | / day | 109600 | 80000 | 37 | 29600