Mailing Address:

P.O.BOX 705 Mukono,

Uganda

Phone:

+256-414-670686

+256-751-241079

+256-775-053641

+256-754-772065

+256-712-848448

Fax:

+256-414-290341

E-mail:

youthsintechug@gmail.com

Blog:

http://yitug.wordpress.com

Twitter:

@youthsintechug

Our Ref:………………….

Your Ref:………………...

Date:……………………...

Youths In Technology and Development-Uganda (YITEDEV)

NPO. Reg. No.: 214843

Empowering youths with ICT skills leading to Sustainable Community Development.

PROJECT TITLE    : YOUTH SUSTAINABLE SKILLS AND EMPOWERMENT

PROGRAM

IMPLEMENTING AGENCY      :            YOUTHS IN TECHNOLOGY AND

DEVELOPMENT       UGANDA

C/o YITEDEV-Uganda

P. O. BOX 705 Mukono,

TEL: +256754772065, +256751241079, +256702848448

Email:youthsintechug@gmail.com,

Registration Number 214843

LOCATION                   :                     Mukono

PROGRAM COST         :                    24746.39 dollars

ACCOUNT NUMBER             :       1021016020000464

ACCOUNT NAME                  :       YOUTHS IN TECHNOLOGY AND

DEVELOPMENT    UGANDA LTD.

BANK   NAME                        :      DFCU BANK

BANK   BRANCH                   :      MUKONO BRANCH

SUBMITTED

CONTACT PERSON                :   ROBERT KIBAYA   (Director)

Email, robkib@gmail.com, call: +256 702848448

PAUL KASOMA       (Project Coordinator)

Email, paulkasoma01@gmail.com  call: +256754772065

STEPHEN KALYESUBULA (Project Manager)

Email, skalyesubula@gmail.com call: +256751241079

List of Acronyms:

- YSP ……………………………… Youth Sustainable Skill and Empowerment Program

- HIV …………………………........... Human Immune-defiance Virus

- AIDS …………………………........ Acquired Immune Deficiency Syndrome

- OVC …………………………........ Orphan Vulnerable Children

- CBV …………………………......... Community Based Volunteers

- VTC …………………………......... Vocational Training Clubs

- CBO …………………………........ Community Based Organizations

- NGOs ……………………….......... Non Government Organizations

- CBSS ……………………………… Community Based Support Structures

- FBS ……………………………. Family based structures

- YIP ……………............................. Youth Intervention Programs

- MDG …………………………........ Millennium Development Goals

- CM …………………………........... Child Mortality

- FBSG …………………………....... Family Based Supports Groups

- LPS ………………………….. ........Life Planning Skills

- BCC …………………………......... Behavior Change and Communication

- IEC ………………………… Information Education and Communication Materials

- YSVSE........................... Youth Sustainable Vocational Skills and Empowerment

- UYAAS........................................ Uganda Youth Anti-AIDS Association

- WVU………………………………  World Vision Uganda

- YDGY ………………………… Youth with Disabilities and Girl youth

- CLF…………………………….  Candle Light Foundation.

- Ppts …………..………………..… Participants

- Pple ……….……………………… People

- YITEDEV……………………….Youths in Technplogy and Development Uganda

- YVSTAEDS ………. …Youth Vocational Skills Training Advocacy, Establishment, Development and sustainability

PROJECT SUMMARY:

According to the mapping report, government programs were identified with activities related to technical work at regional/district levels in Uganda.  Youth sustainable vocational skills and empowerment interventions can be increased through collaboration of the existing organizations with Government in order to scale up the interventions at community level. The categories of young people who need vocational skills interventions are those who are orphans, especially related to the HIV/AIDS, Conflicts/wars, Politics, among others. Youths are in dire need of basic needs and supplementary benefits as Ugandans. These service points can hence be used to create opportunities to the target group who are in and out schools.

In the project are, nearly a half of the safety cases, drug practitioners, induced abortion, poor parenting occurred among the youths aged 10-25 years. A third of the national population is made of young people and also a half of manpower to most sectors are of young people; therefore the need for action to control the above crises has never been more agent than now in the country.

The vocational skills and empowerment project is not clearly established to youths due to the fact that it is not in their careers and usually contributes to unsafe environment to future citizen. This project therefore seeks a total of US Dollars 24746.39 to support a one year project for youth sustainable vocational skills and empowerment. The project duration will run for a period of 12 months

INTRODUCTION:

1.0. Organization Background:

Youths in Technology and Development Uganda is a Non- Governmental Organization that was formed in 2014 and registered in 2016. YITEDEV was registered with the mandate of Capacity building of young people and the community. Working to reduce and eradicate human suffering by responding to Physical and Emotional needs of youths. Our offices are in Mukono, Tabula plaza opposite Centenary Bank

Youths in Technology and Development Uganda is Youth driven, Volunteer-run, independent, nonprofit organization dedicated to deliver inclusive, innovative, sustainable programs and services to support Youth empowerment and community development. YITEDEV is a human service organization that identifies the approach of effective means to involve young people in local development decision-making, giving them voice and influencing power, with benefits for themselves and their communities.

Indented to nurturing human potential, the capacity-building organization is made up of vibrant youths who exist to help youths and communities to access the skills, tools, and information they need to get going and do what they do best. We're about building effective and lasting relationships with people and organizations from all sectors so that together we can lend a helping hand and allow the thousands of Youths in localities across Uganda to reach their full potential.

"Youth understand their issues best; they have the agency, capacity and commitment to develop appropriate solutions for themselves and their communities.”

Youths in Technology and Development Uganda is operated by a number of volunteers from various parts of Uganda.  At the core of the Organization’s activities is a customized system of Youth with intent to create more opportunities for our communities to prosper. Through our benevolent services we aim to get the right people talking to each other. YITEDEV, a youthful lively & vigorous movement also implements several extensive human service projects to support individual growth, revitalize the youth potential, rebuild communities, and restore the environment We believe that by building these bonds and spreading the resources and skill sets through volunteering, awareness and sensitization, limitless guidance, providing skills training and support that drives employment and entrepreneurship and other useful services, we are helping to build the type of dynamic workforce that will promote shared growth and create peak physical, mental, and emotional wellbeing, many of our local communities can really thrive.

In the wider sector we listen to, respond and represent the needs of Youths so that the world they operate in works to support them.

It's this ethos that allows Youths in Technology and Development Uganda as a liberal organization to really empower Youths to provide core services that tackle those rare maladaptive concerns , combat those difficult social issues and address those neglected causes in our local communities.

When youth participation is well supported, young people can gain much by involving in Community-Driven Development. These operations provide an opportunity to increase youth voice, empowerment and employment. In return, youth involvement can enhance the quality and transparency of Community-Driven Development., improving community representation and bringing youthful qualities of optimism, energy and creativity into finding solutions to local development challenges.

Through trainings, young people are taught different skills in carpentry, Paper bag making, Environment management, Sewing and Tailoring, Knitting, Brick-laying concrete and Practice, Leather Tanning, Hand Craft training, Computer training, Plumbing, Mechanics and Party Decoration among others. After their training, they are expected to be able to produce good quality products leading to increase in Gross Domestic product and profitability. Secondly they will be able to effectively work in their village settings able to creating jobs among themselves.

2.0 Problem Statement:

Lack of Vocational training services has the devastating potential to create a severe of economic impacts. Young people have straggled with life and they need a hand that can support them through vocational training that can equip them with constructive Knowledge and reliable Skills. It is noticed that 60% of youths in their productive years, lack direction which has contributed greatly in affecting the development and economic out-put of the country. In Uganda, youths contribute 80% to the economy of the country.

Environment – For decades, the war that raged in the north of the country for more than twenty years led to the displacement of 1.6 million people from their villages and increased pressure on environment especially in Kampala suburbs and the neighboring districts like Wakiso, Mpigi, Mukono, Luwero etc.

Uganda remains one of the poorest countries in the world. The average daily income hovers below one dollar a day. While 40% of the populations in the south are living below the poverty line, in the north this figure rises as high as 70%. A large proportion of young people in Uganda have received little or no formal schooling. Most of them are unemployed. They are being denied even the most basic, most practical vocational education and their chances of ever finding a paid job are very slim indeed.

Accessing young people with practical vocational trainings and thus to the job market; In Uganda, the projects take place not close to the rightful locations/people. This means that over 45% of youths are forced to leave their social and cultural environment, which thus makes training and education even more difficult.  In the countryside, there is a heavy emphasis on various programs for the adults than youth manual vocations. The skills are being taught to meet country's demands.

The project is particularly keen to foster communities in which no training and educational opportunities have previously existed. The goal is to motivate to make up to 30% of the participants mainly girls, by the end of 2017, over 200 youths will be working either independently, as self-employed operators, or in newly created jobs.

A number of initiatives have been created to support and provide services to the community. These include a wide range of Skills including farming, horticulture and craft making. All these groups are important but mainly with lots of gaps; for example women groups. These women had taken the initiative, regardless of the physical cost, to seek to earn a living to feed and cloth their children. This means that young people are left with-out any developmental plan especially OVC, Youth with Disabilities and Girl youth.

The Organization will work together with local communities and other agencies that have the same interest  to implement the Sustainable Development Goals(SDG) within the communities which include the Eradication of extreme poverty and hunger, achievement of Universal primary education( Quality education), promoting Gender equality and empowerment, Reduction of child mortality, combating HIV / AIDS, Malaria and other diseases, ensuring Environmental sustainability and promotion of global partnerships for development.

YITEDEV Mission:

To contribute to the improvement of young people’s lives through school and community based Education in response to sustainable skills. As well as creating Tech Communities of practice in which appropriate use of technology creates opportunities for the youths leading to sustainable community development

- OBJECTIVES: -

- Overall Objective: To empower both in and out of school youths with Technology Skills,Vocational Skills and keeping them out of current dangers (HIV/AIDS, Early pregnancy), Breaking the York of vulnerability and having good working conducive environment to enable them obtain a successfully/desirable life so as to eradicate poverty in Uganda.

- Project Objectives

- To reduce vulnerability and dependency among the young people by 20% in rural community of our project catchments.

- To mobilize and sensitize over 12,000 youths in villages.

- To equip youths with IT Skills

- To advocate and mainstream vocational training skills with other trainings.

- To reduce the problem of unemployment by 10% of the youths.

- To provide 40% of Counseling and Guidance services to youths on psychosocial and economic issues.

- Creating an environment that provides support, enrichment and engagement for young adults to promote positive youth development.

- To work for the social uplift of the underprivileged and neglected communities through education on community development, and capacity building of community leaders.

- To promote and empower Schools, Universities, Organizations, Communities and individuals among other key community development programs to acquire up to date genuine Information and Communication Technologies (ICTs) and services suiting their work environments, and to provide affordable and environmentally sustainable ICT solutions.

- To participate in national and international forums and seminars to advocate our objectives and mission of the organization

- PROFILE OF THE PROJECT SITE:

Most societies are affected by the psychosocial and economic problems but among the chosen ones are Gulu,Wakiso, Mukono, and Mpigi.

The project sites were carefully selected taking into account regional variations, magnitude of the problem and proximity YITEDEV coordinating office for ease of monitoring and supervision as the Project has succeeded the pilot trial which has paved the way for replicating.

(a) Direct Beneficiaries:

The project is aiming at addressing youth sustainable skills and empowerment which are aimed at enabling them to access basic reliable skills through training workshops, counseling and promote positive behaviors. Currently, young people country-wide are so vulnerable to many dangers in the country due to a double influence as regards to political and poverty.

Therefore as a result from the above we have intensified our current efforts and services to young people affected with psychosocial and Economic factors. There is a need to involve youths in service delivery at all levels of project management in local areas. They will be equipped with knowledge about Positive change and effective planning in Kampala District.

(b)  Indirect Beneficiaries:

The project will also benefit men, women/widows based in project areas and their neighbors. Currently half of the new strategies are mismanaged by the rural settings in one way or the other. The rural community some times are money minded especially men of which has turned to be the major challenge.

The consequences of not having vocational training skills with in communities have not been thoroughly studied. Generally this lose future hope and increases vulnerability in various communities in project areas. Therefore this will aim at scaling up vocational training awareness among community people.

The International Conference on Population and Development on the Reproductive health rights for women, girls and boys, gender rights and development. There is more work that needs to be done to redress the need for access and utilization of services in communities in Uganda.

Kampala: Out of the total population in Uganda, Baganda makes up 5.5 million people, and approximately 16.9% are living in Kampala district. Many people have migrated; to Kampala due to seeking for jobs, social conflicts, inter-marriage, politics and industrialization. Young people covers a half of this population and most of them are jobless.

CAPACITY BUILDING OF YITEDEV:

Is a community based organization, YITEDEV has been implementing awareness activities in Kampala  targeting adolescents and young people aged (10 – 25 years) in and out of schools. It has well set organizational structured with professional and experienced staff in the field of vocational skill trainings and adolescent interests, well set tools. YITEDEV is under taking thorough Vocational trainings that include the following:-

- Conduct mobilization of youths on issues concerning Vocational trainings (income generating activities), Reproductive health (HIV/AIDS), Environment protection, Youth gender protection and development programs for example production of Soap making, Candle making, Paper bags, Carpentry, Charcoal stoves, Leather tanning and shoe making, Tailoring among others

- Counseling and guiding young people aimed at improving their capacity building on various income generating activities, Empowering youth and creating a positive community/school environment and consistent in their approach, hence development of an African Child career vocational trainings.

- Conduct community workshops which help families to realize the importance of child development and support them in their future planning skills.

- Carrying out home visits and having meetings with parents/families concerning young people in less formal way using IEC materials that most parents read and understand.

- Engaging and empowering parents in decision-making practices of advisory groups (such as local school-community improvement councils), school reform committees, advocacy and other school restructuring efforts.

- Conducting talk shows through radio and TV programs, community and center talk shows concerning the importance of YITEDEV in project areas.(district)

- Training community in ICT Related activities

- Monitoring and evaluation is one of our major activities because it helps to assess the progress of the project.

Above all a total of 900 youths were trained in paper bags production, 5 vocational training centers have been established hoping to establish more  2 this year at least in each and every neighboring district.

New Hope Primary School benefiting over 20 pupils, 5 workshops have been conducted advocating for young people’s Technology and vocational training skills, 13 Community Youth both girls and boys were trained in Candle making, Soap, Tailoring, Art and Crafts during the implementation of project activities.

PROJECT REQUIREMENTS:

  - Audio visual equipment (2set of TV and DVD)

  - Power Generator (2)

- Flip Chart Stands (2)

- 20 low energy consuming computers.

- A low powered projector and screen per Solar panels and backup batteries

PROJECT TEAM:

1. Project Coordinator (2)

2. Counselor (2)

3. Training Officers/Instructors (7)

Monitoring and Evaluation:

This will be a continuous process through out the project life. Monitoring activities will be conducted to ensure harmonious coordination of the project, its operation and proper implementation. This will bring out important information upon which decisions are sought and made.

Field workers will also visit and hold meeting with the trained leaders to assess the impact of the project activities and share their experiences and challenges accordingly. Monitoring activities will be conducted on monthly basis.

Evaluation will help the project to assess the extent to which implementation is meeting the set objectives. It helps the project team to review the implementation strategies in order to improve on the project performance and better resource utilization.

Impact Indicators:

The proposal is designed to improve youth’s way of life and create early awareness in our project areas. Our strategies for young people will enable them access sustainable skills and empowerment. Much focus will be put on those with in and out of schools as this brings more close all the young people categories into our sustainable skills web.

Increased number of young people participating in different vocational training activities and improving on their capacity building through mainstreaming sustainable training skills in various programs.

Implementation Plan: The following activities will be implemented under project areas;

YITEDEV will continue employing community friendly approaches to reach remote areas through static and mobile training workshops and sensitization programs. Also the approach will involve various levels of stakeholders. Each of the components of the project will be tackled technically by designing interventions that effectively and appropriately address vocational training skills and associated activities that can contribute to community development. It is anticipated that by the end of the project period, there will be realization of positive living and reduced levels of dependency among young people in project districts.

Activities:

The following activities will be implemented under this project:-

1.   Community mobilizations and identification of required youths: Over 12,000 people will be reached and the service will be managed jointly with community leaders, development workers and organizations and YITEDEV staff. It will still focus on assessing the nature of the community and the status of beneficiaries more especially young people. Mobilization will also be in preparation for identifying and forming family support groups (FSG) and youth vocational clubs in rural areas of operation. The clubs are thought to strengthen the sustainability of the project.

2.  Conducting community Mobilization and Sensitization on youth friendly concerning ICT and Vocational trainings (income generating activities, Reproductive health (HIV/AIDS), Environment programs, Youth gender protection and development programs

- Capacity Building: Empowering youth and creating a positive community/school environment and consistent in their approach, hence development of an African Child career through vocational training skills. Among the roles include the following:-

- 900 participants will be trained in sustainable activities both in and out of schools.

- 40% of Young people will be empowered with life planning skills and knowledge of positive planning.

- 180 participants will be trained in ICT tanning activities at community level.

- Training workshops for 20 parents and 20 teachers from each school targeting 20 schools of program district.

The above trainings of participants will be conducted at all levels as peer educators on the importance of family involvement, family development, human relations, child rights, Environmental protection, parenting strategies, child development and support them in their sustainable skills in catchments.

- Counseling: Counseling and guiding young people on various development aspects in such a way to recognize their potential skills relevant to their professional development. This will be successful through engaging and empowering parents in decision-making practices of advisory groups (such as local school-community improvement councils), school reform committees, advocacy and other school/community restructuring efforts

- Procuring and Distributing IEC Materials: Carrying out home visits and having meetings with parents/families concerning young people in less formal way of using IEC materials that most parents read and understand. This is aimed at reminding communities to implement young people's sustainable programs in their respective places. Therefore producing and distributing 20,000 IEC materials on empowerment and youth friendly programs will be in form of Brochures and Newsletters.

- Advocacy: Through Net-working services with other organizations like Net Squared, Internet Governance, Kikandwa Rural Communities Association, Mukono NGO forum, Uganda youth anti-AIDS Association (UYAAS), carrying out demonstration on simplicity of vocational skills sections establishment, Income generating activities, Community Seminars on vocational skills training Advocacy, Establishment, Development and Sustainability, Establishing vocational skills training centers and Tree planting in our catchments.

- Follow-up activities: Staff members will always go back to places where they have carried out the activities to meet young people to assess the changes that have occurred, guide beneficiaries in their respective activities, share with them experiences that they have met and get measures on them accordingly.

- Monitoring and Evaluation: This will be an on going activity throughout the project and will be carried out on monthly basis. It will be carried out to access the project implementation and will help to supervise the youth community based workers. Assessed management processes will view objectives, concepts, designs and methodologies of the project; it is an international management responsibility. This will be an on going activity throughout the project life. It will be routinely through monthly reports, meetings, check lists, surprise visits and support supervision visit.

THE PROJECT WORKPLAN

| No | Activity | Objective | Implementer | J | F | M | A | M | J | J | A | S | O | N | D |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Proposal Submission | To access fund facilitation | Management |  |  |  |  |  |  |  | * |  |  |  |  |
| 2. | Training of Community Resource persons. CBV, CBSS, & Teachers | To equip 230 people with basic knowledge and skills of leading others. | UYSTP Team |  | * | * | * |  |  |  |  |  |  |  |  |
| 3. | Production & Distribution of IEC Materials | To produce 20,000 IEC Materials to support project through information delivery | Counselors, Trainers/instructors and Community resourceful persons |  | * | * | * | * |  |  |  |  |  |  |  |
| 4. | Training youths on vocational skill and empowerment programs | To access over 900 youths with basic technical skills | Training team and volunteers |  |  | * | * | * | * | * | * | * | * |  |  |
| 5. | Counseling young people on career guidance and vocational training skills. | Empowering youths on positive planning | Counselors, & Resource persons | * | * | * | * | * | * | * | * | * | * | * |  |
| 6. | Monthly Radio talk shows. | To provide general knowledge on vocational trainings | YITEDEV and partners | * | * | * | * | * | * | * | * | * | * | * | * |
| 7. | Community Sensitization on sustainable skills in our catchments. | To Enhance youth’s Capacity Building on Technical and vocation trainings. | Project Team, CBV and local leaders |  | * | * |  |  | * |  |  | * | * |  |  |
| 8. | Networking Services | To strengthen the Relationship with our partners | YITEDEV Team | * | * | * | * | * | * | * | * | * | * | * | * |
| 8. | Follow-up on activities carried out | To assess the progress and weaknesses of the project | Project Team |  | * | * |  | * |  | * |  | * |  |  |  |
| 9. | Monitoring and Evaluation | To assess whether activity implementation is achieving the set objectives | YITEDEV M&E project officer | * | * | * | * | * | * | * | * | * | * | * | * |
| 9. | End of year Narrative and financial report. | To display the general project report. | Team leaders |  |  |  |  |  |  |  |  |  | * | * |  |
| 10. | Annual Audit |  |  |  |  |  |  |  |  |  |  |  |  |  | * |

The main goal is to integrate ICT and vocational trainings skills with other practices in communities and school syllabuses so as to improve the capacity building of young people (girls and boys) aged 10-25 years through empowering participants in all activities in Kampala suburbs.

- The project will be implemented in local areas of the project interests; beneficiaries of the project will be Approximately as follows:-

- 900 young people will be trained in various sustainable skills

- 20 parents and 20 teachers will be trained as community based support structures and they will also work as community resource owned persons.

- 30 youths will also be trained as community based volunteers. This team will work as middle men between service providers and community youths.

- The number of beneficiaries to reach by the end of one year is estimated 900 as it is justified in no1, above.

- The organization is planning to reach the target group(s) through CBSS, CBV, women and men in project catchments areas.

Recruiting procedures of participants

Regarding staff members are expected to apply in the beginning of the program, of which they will be short-listed for interviews which will be conducted by board and the best of all, will be declared as one of the staff. They will also be expected to be trained in the orientation of the program.

Volunteers will also apply and those with relevant papers will be considered and oriented in the field of vocational training skills hence considering the age as a very important key point in this aspect.

Community participants will be screened out with the help of community leaders, elders, teachers and church leaders. This exercise will be supported with research methodologies for effectiveness in recruiting participants.

SUSTAINABILITY:

For the effective sustainability of the project, YITEDEV team will ensure that FBSS, CBV and Empowered on the importance of the project to beneficiaries in their local areas. It is expected that the project will be sustained by initial active participation of beneficiaries in the project through CBV, Teachers and FBSS. Mentioned groups will be trained to support the project.

Due to lack of functional support groups, it has been difficult to implement such projects. However for now sustainability is assured because the family/community and school administration teams would be involved in every stage of project implementation.

It is thought that community approach of involving their participation can lead to good cause, it is expected that each community will be capable of handling youth friendly activities. It is expected that the selected CBV, FBSS and Teachers would continue offering support and sensitization services in their respective communities.

Regular follow ups and monitoring will be important to the sustainability of the project as it will help in supporting its stakeholders. Problems faced can easily be handled by the support groups and they can also play a great role in devising solutions. The support and motivation will be one of routine duties geared by  YITEDEV management to support groups in their communities.

The Logical Frame work for 2017– 2018 YSP projects

| Narrative summary | Objectively variable indicators | Means of variable indicators (verification) | Assumption |
| --- | --- | --- | --- |
| Purpose: Empowering young people in sustainable skills and other vocational trainings. | Outcome: - Over 40% of young people will access Sustainable skills and empowerments as well as knowing how to use ICT associated technologies efficiently - Increase 90% of YSP knowledge to youths in the project area - Over 40% of young people in and out of schools will adopt positive living in their communities | - YITEDEV evaluation and annual reports - Demand for more activity implementation by community leaders - The activeness of formed support groups (FBSS, CBV among others - Sample survey | -Establishment facilities will continue to provide on-going counseling services Training and care to young people -Other NGOs/CBOs dealing in YSP and empowerment services will be offering the services |
| - 2. Study which delineates specific efforts of YSP in particular: Decision making on psychosocial and economic access to YSP services and incidences of unemployment | - Study documents that will serve as a foundation for viable history in place - commitment to distribution a set number of IEC materials | - Observation - Review of YSP activities - Seminars reports - Report analysis | No un fore seen will disrupt YSP project in chosen areas No un fore seen events organization disrupt the seminars |
| 3. Daily Counseling and Career guidance services on youths sustainable activities | - Over 900 young people will be equipped and empowered with YSP in the project period |  Monthly reports  M&E reports, progressive quarterly report  Annual reports | -Adoption of positive planning - YITEDEV partners with Community will be Strengthened |
| 4.Community owned resource persons workshops | Community support groups will be equipped with knowledge and skills to ensure positive Planning | - Training Reports - Evaluation Reports - Family Support Structures Reports | -The Relationship between YSP staff and community members -Youth involvement in development programs |
| 5.20,000 IEC materials detailing current YSP activities among young people in project districts in Uganda | - 2 types of print materials in local and English language are appropriate to non literate and literate users and produced - Video documentary on youth vocational training. radio spots | - Observation - Reports - Active Talk shows participation - Observation | - Reduction of further vulnerabilities among young people - No un-fore seen events will disrupt the YSP facilitation process. - Broadcasting policies on Vocational skills |
| 6. Conducting workshops to strengthening psychosocial service net work and influence them to support young people empowerment Initiatives | - Networking workshops - Resolutions and commitments to support the initiatives made - Commitment and involvement in activities | -Observation -M&E Reports -Report analysis -Training reports | -No un-fore seen events at organization disrupt the Vocational trainings |
| 7. Men, women, opinion leaders at division and community levels will be sensitized & influenced sponsors young peoples programs (vocational skills) | - Monthly community sensitization seminars will be held on Vocational skills - Empowered seminars for community leaders every month in project areas | -Observation -Reports -Interview reports | -No un-fore seen events at organization will disrupt the seminars |
| 8. Monitoring and Evaluation activities | 12 M&E will be accessed to access the progress of the project for sustainability | -Monthly Reports -M&E Reports | -Willingness and cooperation of the target groups M&E Reports |
| 9. Annual Audit | Project staff hired | -Observation -Quarterly & annual Report |  |

Budget form

Programs funds requested

| Budget line | Q1, UGX | Q2,UGX | Q3,UGX | Q4,UGX | Subtotals,UGX |
| --- | --- | --- | --- | --- | --- |
| People and time (salaries) |  |  |  |  |  |
| Director | 600,000 | 600,000 | 600,000 | 600,000 | 2,400,000 |
| Field officers (2) | 1080,000 | 1080,000 | 1080,000 | 1080,000 | 4,320,000 |
| Instructors (4) | 1,800,000 | 1,800,000 | 1,800,000 | 1,800,000 | 7,200,000 |
| Accountant (1) | 750,000 | 750,000 | 750,000 | 750,000 | 3,000,000 |
| Office and administration |  |  |  |  |  |
| Office rent | 450,000 | 450,000 | 450,000 | 450,000 | 1,800,000 |
| Communication services (telephone, email, internet) | 500,000 | 450,000 | 450,000 | 450,000 | 1,850,000 |
| Administrative Cost | 1,100,000 | 1,100,000 | 1,100,000 | 1,100,000 | 4,400,000 |
| Capital/equipment |  |  |  |  |  |
| Audio Visual equipment and accessories (1set) | 8,00,000 |  |  |  | 8,00,000 |
| Computers Units (20) | 20,000,000 |  |  |  | 20,000,000 |
| Generator (1 item) | 8,00,000 |  |  |  | 8,00,000 |
| Flip Chart Stand (1tem) | 3,00,000 |  |  |  | 3,00,000 |
| Other (please specify) Program Costs |  |  |  |  |  |
| Training community workshops (5 trainings) | 3,050,000 | 3,050,000 | 3,050,000 | 3,050,000 | 12,200,000 |
| IEC Materials (20,000 copies) | 2,000,000 |  |  |  | 2,000,000 |
| Radio Program | 1,500,000 | 1,500,000 | 1,500,000 | 1,500,000 | 6,000,000 |
| Instructional Requirements | 3,548,750 | 3,548,750 | 3,548,750 | 3,548,750 | 14,195,000 |
| Community interaction meetings (5meetings) | 500,000 | 500,000 | 500,000 | 500,000 | 2,000,000 |
| T-Shirts | 1,499,400 |  |  |  | 1,499,400 |
| Certificate | 751,400 |  |  |  | 751,400 |
| Monitoring and Evaluation | 300,000 | 300,000 | 300,000 | 300,000 | 1,200,000 |
| Audit | 500,000 | 500,000 | 500,000 | 500,000 | 2,000,000 |
| TOTALS | 41829550 | 15,628,750 | 15,628,750 | 15,628,750 | 88,715,800 |

The total program cost for 1year is 24746.39 dollars (88,715,800 Ugandan shillings), but the program is expected to run 3years

Budget Notes:

- Program Costs:                                                                                                                     Training work shops for community support groups (Volunteers).                                                                                                               This is purposely to identify the potential youths who will be trained to restore consultation and sustainability in their respective communities.

- Facilitators transport                     :    2 officers x 30,000 = 60,000

- Participant break first                    :        50 ppts x 2,000 = 100,000

- Participants lunch                          :       50 ppts x 5,000 = 250,000

- Evening tea for participants           :               50 x 2000 =   100,000

- Venue (hire)                                  :    100,000 x 1 =         100,000

- Total =                                       :                                        610,000/=

The result will be 610,000/= x 5 days x 4 work shops = 12,200,000/=

Instructional requirements

- Carpentry (timber and accessories)

- Timber (12 x 1 ½ x 12               :        200 peaces x 20,000 = 4,000,000

- Adhesive (wood glue pono)      :                     tins x 7,000  =     175,000

- Drying  Agents                           :                                             =  50,000

- Nails ( assorted)                         :                      30 kg x 4,000 = 120,000

- Vanish (2 jyracan 40 Lt)            :                       100,000 x 2    = 200,000

- Sand Paper                                  :        3,000 per (M) x 20(M) = 60,000

- Ply wood  (10 peaces)                :                         20,000 x 10 = 200,000

- Total =                                       :                                             = 4,805,000/=

- Tailoring (rolls of clothes)

  - Sugar Paper (20 reams)                 :            20 x 60,000 = 1,200,000

  - Polyester material (24 rolls)          :               24 x 60,000 = 1,440,000

  - Accessories                                    :                                =     500,000

  - Total =                                           :                                 =  3,140,000/=

c) Shoe Making and other works:

Vegetable leather square foot                 :              5000 x 50 =      250,000

Close contact Adhesive (tough bond)     :         40,000 x 25 =     1,000,000

Soles (flat soles)                     : 40,000 x 2 sheets x 50 people = 4,000,000

Accessories                               :                                              = 1,000,000

Total                                       :                                                 =   6,250,000/=

Therefore all this will be 6,250,000 UGX for 4.quarters

All instruction materials will cost 14,195,000/= a full year

- Community interaction meetings:                                                                                                             This will be conducted targeting stake holders (community leaders/elders) who will be an eye for effective planning and implementation of the project.

Venue (hire)                                    :      100,000 x 1 = 100,000/

Refreshment                                    :                         3,000 x  80 = 240,000

Facilitators                                       :                           30,000 x 2 =   60,000                                         Total                                                                                              = 400,000/=

Therefore the meetings will cost 300,000 x 4 meetings =1, 200,000/

- Radio talk show                                                                                                   Vocational training programs will be conducted through sustainable skills awareness work shops, involvement of youths planning aspects, Radio programs running on monthly bases, talk shows organized at the center. Radio programs will be broken down as below:-

Radio programs                                     :               450,000 x 1 = 450,000   Technical officer allowance                  :                   50,000 x 1 =   50,000                 Total =                                                                                      = 500,000/=

All radio talk shows will be 12 x 500,000 = 6,000,000/=

5.  Project Monitoring and Evaluation (M $ E)

The project team will offer this M & E on monthly basis for one year. The break down is as follows:-

Officers Transport and Lunch                 :     50,000 x 2 officers = 100,000

Therefore, each M & E activity will be 100,000 x 12 months = 1,200,000/=

END. Thank You For Your Support

“Yitedev-Uganda”