**Peaceful Co-existence Program**

**Logical Framework 2018 – 2019**

|  |
| --- |
| **Goal: Contribute to promote peaceful co-existence, cohesion and harmony for all.** |
| **Objective 1: Increase capacities and leadership skills for young women and men to become capable Peace Agents.** |
| **Outcomes 1.1** | **Indicators** |
| Increased knowledge and leadership skills of Peace Agents on Concept on Peace and Conflict, Causes of Conflict, Tools to analyze conflicts, Conflicts resolution, Non-Active Violence  | 70% of 25 Peace Agents (30% female) increased knowledge in peace concept, Conflict, Causes of Conflict, Tools to analyze conflicts, Conflicts resolution, Non-Active Violence and Do No Harm.70% of 25 Peace Agents (30% female) increased capacities in conflict resolution |
| **Major Activities** | **Outputs** | **Mean of Verification** |
| Conduct a base line survey on people's knowledge Concept on Peace and Conflict. | One baseline survey on people's knowledge conducted. | Baseline report* Consulting contract
 |
| Review and revise training curriculum (manual) based on result of the survey for Peace Agents. | 5 training curriculums (Manuals) developed. | Final curriculum* Contract and receipt
 |
| Train Peace Agents on Peace Concept and leadership skills to deal with Conflict. | 25 Peace Agents (30% female) trained on Concept on Peace and leadership skills. | Training report/photos* Training agenda
 |
| Train Peace Agents on Causes of Conflict, tools to analyze conflicts, Conflicts resolution, and Active Non-Violence. | 25 Peace Agents (30% female) trained on cause of conflict, tools to analyze conflicts, Conflicts resolution, and Active Non-Violence | Training report/photosTraining agenda |

|  |  |
| --- | --- |
| **Outcomes 1.2** | **Indicators** |
| Increased capacity and culture of dialogue for Peace Agents. | 70% 25 Peace Agents (30% female) enhanced their capacities in dealing with Conflict, Causes of Conflict, tools to analyze conflicts, Conflicts resolution, and Active Non-Violence. |
| **Major Activities** | **Outputs** | **Mean of Verification** |
| Facilitate consultation meeting with Peace scholar to identify peace mapping. | One consultation meeting with Peace scholar to identify peace mapping held. | Attendant list* Report/photos
 |
| Organize inter-faith dialogue among religions at all levels. | 2 inter-faith dialogues organized | Report/Media trackPhotos/video clips |
| Facilitate Peace Table among conflict parties to suggest option for resolution. | 2-Peace Table among conflict parties organized. | Media track/report* Photos/video clips
 |
| Organize International Day of Peace (IDP) across border on September 21st.  | IDP organized with 500 participations | Media track/reportPhotos/video clips |
| Follow up on Peace Agents (mentoring & coaching session) | 2 mentoring and coaching sessions for Peace Agents conducted. | Report/photos* Attendant list
 |
| **Objective 2: Increase confidence of Peace Agents in promoting peaceful co-existence at national and regional levels.** |
| **Outcomes 2.1** | **Indicators** |
| Strengthened mechanism and networking with related peace institutions at national and regional level. | 70% of 25 Peace Agents (30% female) enhanced their confident in sharing peace value among and within their communityAt least 3 working modalities functioning for Peace Agents. |
| **Major Activities** | **Outputs** | **Mean of Verification** |
| Establish volunteer/internship program for youth peace builders with related peace institutions. | 5 of 25 Peace Agents (30% female) as intern with peace institutions for 3 months carried out. | Internship contract* Report
 |
| * + 1. Organize ASEAN Peace Journey to engage youth with conflict and effected communities.
 | ASEAN Peace Journey for 30 (30% female) young adults from ASEAN country organized. | Media track/reportPhotos/video clips |
| * + 1. Organize ASEAN Peace Camp for youth from difference cultures to learn to work and learn to live together,
 | ASEAN peace camp for 30 (30% female) young adults from ASEAN country organized. | Media track/reportPhotos/video clips |

**Peaceful Co-existence Program**

**Program Action Plan 2018 – 2019**

|  |  |  |
| --- | --- | --- |
| **Major Activities** | **2018-2019** | **Responsible** |
| Year 1 |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| **Objective 1: Increase capacities and leadership skills for young women and men to become capable Peace Agents.** |
| **Increased Peace Agents' knowledge and leadership skills.** |
| Conduct a base line survey on people's knowledge Concept on Peace and Conflict. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Review and revise training curriculum (manual) based on result of the survey for Peace Agents. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Train Peace Agents on Peace Concept and leadership skills to deal with Conflict. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Train Peace Agents on Causes of Conflict, tools to analyze conflicts, Conflicts resolution, and Active Non-Violence. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| **Increased capacity and culture of dialogue for Peace Agents.** |
| Facilitate consultation meeting with Peace scholar to identify peace mapping. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Organize inter-faith dialogue among religions at all levels. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Facilitate Peace Table among conflict parties to suggest option for resolution. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Organize International Day of Peace (IDP) across border on September 21st.  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Follow up on Peace Agents (mentoring & coaching session) |  |  |  |  |  |  |  |  |  |  |  |  |  |

|  |
| --- |
| **Objective 2: Increase confidence of Peace Agents in promoting peaceful co-existence at national and regional levels.** |
| **Strengthened mechanism and networking with related peace institutions at national and regional level.** |
| Establish volunteer/internship program for youth peace builders with related peace institutions. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| * + 1. Organize ASEAN Peace Journey to engage youth with conflict and effected communities.
 |  |  |  |  |  |  |  |  |  |  |  |  |  |
| * + 1. Organize ASEAN Peace Camp for youth from difference cultures to learn to work and learn to live together,
 |  |  |  |  |  |  |  |  |  |  |  |  |  |