ASRuD CAVA II HQCF PROJECT

MONTHLY WORKPLAN FOR FEBUARY 2015 - JUNE 2015

|  | MAIN OBJECTIVES | ACTIVITY | KEY ACTORS | TIME | KEY INPUTS | EXPECTED OUTPUTS |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Facilitate linkages to ensure that 80 farmer groups are consistently delivering at least one (1) tonne of fresh cassava per farmer per month into viable markets, 50% of which shall be for HQCF and the other 50% for other processed cassava products over the contract period. | - Field visits to educate farmers, to monitor production and sales. - Writing and submission of monthly reports. - Stakeholder Business meetings. . - Writing and submission of monthly reports. | ASRuD Field Staff | February March | Field allowances, Stationery, Transportation Refreshments Stationery Transportation Stationery Transportation | Data collected from the 80 Farmer groups Reports ready and submitted on schedule Seminars held farmers have understanding of processes. Reports ready and submitted on schedule |
| 2 | Facilitate linkages leading to the sales of at least 20 tonnes a month of processed cassava products by small medium and large scale enterprise being overseen by my organization: 50% of which is HQCF and 50% of other products | . Assess production capacity of processors Link processing groups to financial institutions for purchase of equipments Data collected for April and quarterly reports written and presented | ASRuD Field Staff | April | Stationery Refreshment Allowances Business plans and project proposals. Transportation, accommodation & field allowance. | Training sessions held. Plans developed and Linkages made. Financial assistance secured. Reports from 80 Farmer groups submitted |
| 3 | Facilitate the establishment of community out- grower schemes and 10 additional smalholder farmer groups and work with interested freelance farmers located near processors in specific catchments areas. | Organize training workshops for the identified new farmer groups Collect data for reports | ASRuD Field Staff | April | Transportation and Field allowances | Training organized. Reports submitted |
| 4 | Facilitate adoption of improved production technologies (e.g. agronomy varieties planting materials crop management, integrated disease management practices) and access to farm input supplies. | Refresher Workshop with groups, organized refresher training for farmer groups on appropriate agro practices. | ASRuD Field Staff | May | Transportation and Field allowances | Trainings organised Necessary data collected. |
| 5 | Develop systems to ensure that record books are periodically Monitored to ensure adherence to proper book keeping practices. | Organize refresher trainings for groups on rural enterprise development and record keeping. | ASRuD Field Staff | May | Transportation Allowances Stationery Communication | Internal project assessment done and reports written. . transportation systems for easy delivery of products Arranged, products delivered on schedules |
| 6 | Promote use of HQCF in improved version of local foods (domestically and in Hotels) | Organize end user training for potential cassava flour users in Hotels, chop bar keepers and home users, etc | ASRuD Field Staff | June | Transportation Allowances Stationery | Training held for 20 Hotels and 20 chop bar keepers, etc |
| 7 | Strengthen capacity of existing and new rural based entrepreneurs and community processing groups. | Training sessions on Cassava Value Chain and Rural Enterprise Management. Data collected for reports | ASRuD Field Staff | June | Transportation Field allowances | Training organized for rural entrepreneurs and Community processing groups |